## Communications Milestones
|  | 2016/17 Programme - Communications Milestones MASTER |  |  |  | KEY (Type)
|  | Project Name: All projects |  |  |  |  | Project milestone communications required
Project identified communications requirement
Communications team recommended action
Programme identified benefit
[13 empty] | 2016-01-01 | [31 empty] | 2016-02-01 | [28 empty] | 2016-03-01 | [28 empty] | 2016-04-01 | [30 empty] | 2016-05-01 | [30 empty] | 2016-06-01 | [29 empty] | 2016-07-01 | [31 empty] | 2016-08-01 | [29 empty] | 2016-09-01 | [29 empty] | 2016-10-01 | [30 empty] | 2016-11-01 | [29 empty] | 2016-12-01
| C.9 |  | Launch second offering in August - communications via email |  |  | Jemma Ball | 2016-06-28 | 2016-07-30 | 32 | 2016-05-20 | 71 | Not started | [179 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Overarching Transformation Campaigns
Transformation Change Campaign
|  |  | Concept and budget approval |  |  |  | 2016-04-01 | 2016-04-05 | 4 | 2016-05-20 |  | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1
|  |  | Design and develop |  |  |  | 2016-04-01 | 2016-05-01 | 30 | 2016-05-20 |  | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Workshops |  |  |  | 2016-04-12 | 2016-05-02 | 20 | 2016-05-20 |  | Not started | [102 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Launch |  |  |  | 2016-05-10 | 2016-05-11 | 1 | 2016-05-20 |  | Not started | [130 empty] | 1 | 1
Segment Level Changes Campaigns (mad stakeholder briefings such as GMs)
|  |  | Concept and budget approval |  |  |  | 2016-03-29 | 2016-04-05 | 7 | 2016-05-20 |  | Not started | [88 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Design and develop |  |  |  | 2016-04-01 | 2016-05-01 | 30 | 2016-05-20 |  | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Workshops |  |  |  | 2016-04-12 | 2016-05-02 | 20 | 2016-05-20 |  | Not started | [102 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Launch |  |  |  | 2016-05-10 | 2016-05-11 | 1 | 2016-05-20 |  | Not started | [130 empty] | 1 | 1
Website design
|  |  | Wireframe |  |  |  | 2016-04-01 | 2016-05-05 | 34 | 2016-05-20 |  | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Design and build |  |  |  | 2016-04-02 | 2016-05-06 | 34 | 2016-05-20 |  | Not started | [92 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Content development & signoff |  |  |  | 2016-04-03 | 2016-05-07 | 34 | 2016-05-20 |  | Not started | [93 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Transformation Communications Team recruitment | [11 empty] | 1
|  |  | Approval of recruitment |  |  |  | 2106-04-01 | 2106-04-01 | 0 | 2016-05-20 |  | Not started
|  |  | Recruitment process |  |  |  | 2016-04-01 | 2016-06-01 | 61 | 2016-05-20 |  | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Team in place |  |  |  | 2016-06-15 | 2017-05-15 | 334 | 2016-05-20 |  | Not started | [166 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Meetings | [11 empty] | 1
|  |  | Provide monthly content for corporate communications - core brief/Snr leaders |  |  |  | 2016-04-15 | 2017-04-15 | 365 | 2016-05-20 |  | Not started
|  |  | Set up bi-weekly meeting with SROs or project leads |  |  |  | 2016-04-15 | 2017-04-15 | 365 | 2016-05-20 |  | Not started | [105 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
PROGRAMME - WORKFORCE EFFECIENCY | [12 empty] | 0 | time axis 2016-05-29 to 2017-01-01
|  | Reducing Average unit cost pay - non-nursing and midwifery | [10 empty] | 1
Project 1: Salary Sacrifice
|  |  | Decide which methods of communication to the Trust will be the most effective |  |  | Comms | 2016-02-26 | 2016-02-28 | 2 | 2016-05-20 | -82 | Complete | [56 empty] | 1
| B.3 |  | Develop communication for first offering to be made in April |  |  | Jemma Ball | 2016-02-22 | 2016-03-04 | 11 | 2016-05-20 | -77 | Not started | [52 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| C.1 |  | Obtain promotion materials from options supplier |  |  | Jemma Ball | 2016-02-29 | 2016-03-11 | 11 | 2016-05-20 | -70 | Not started | [59 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| C.2 |  | Launch first offering in April - communications via email (and eG etc.) |  |  | Jemma Ball | 2016-02-29 | 2016-04-29 | 60 | 2016-05-20 | -21 | Not started | [59 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| C.3 |  | Hold roadshows across various sites to promote uptake of the offerings |  |  | Jemma Ball | 2016-02-29 | 2016-04-08 | 39 | 2016-05-20 | -42 | Not started | [59 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| C.5 |  | Assess most popular options and most effective methods of communication |  |  | Jemma Ball | 2016-05-02 | 2016-05-06 | 4 | 2016-05-20 | -14 | Not started | [122 empty] | 1 | 1 | 1 | 1 | 1
|  |  | Produce standard comms plan for each salary sacrifice window |  |  | Comms | 2016-03-15 | 2016-04-02 | 18 | 2016-05-20 | -48 | Not started | [74 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Communicate Salary Sacrifice first offering |  |  | Comms | 2016-03-12 | 2016-04-30 | 49 | 2016-05-20 | -20 | Not started | [71 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Communications team to support dissemination of marketing materials |  |  | Comms | 2016-03-15 | 2016-04-02 | 18 | 2016-05-20 | -48 | Not started | [74 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| C.7 |  | Develop communication for second offering to be made in August |  |  | Jemma Ball | 2016-06-21 | 2016-07-02 | 11 | 2016-05-20 | 43 | Not started | bar: 2016-06-21 to 2016-07-02
| C.8 |  | Obtain promotion materials from options supplier |  |  | Jemma Ball | 2016-06-28 | 2016-07-09 | 11 | 2016-05-20 | 50 | Not started | bar: 2016-06-28 to 2016-07-09
| C.9 |  | Launch second offering in August - communications via email |  |  | Jemma Ball | 2016-06-28 | 2016-07-30 | 32 | 2016-05-20 | 71 | Not started | bar: 2016-06-28 to 2016-07-30
| C.10 |  | Hold roadshows across various sites to promote uptake of the offerings |  |  | Jemma Ball | 2016-06-28 | 2016-07-30 | 32 | 2016-05-20 | 71 | Not started | bar: 2016-06-28 to 2016-07-30
| C.11 |  | Open window for second offering |  |  | Jemma Ball | 2016-08-01 | 2016-08-26 | 25 | 2016-05-20 | 98 | Not started | bar: 2016-08-01 to 2016-08-26
| C.12 |  | Assess most popular options and most effective methods of communication |  |  | Jemma Ball | 2016-08-29 | 2016-09-02 | 4 | 2016-05-20 | 105 | Not started | bar: 2016-08-29 to 2016-09-02
| C.13 |  | Review learning's to shape outline for third offering |  |  | Jemma Ball | 2016-09-19 | 2016-09-23 | 4 | 2016-05-20 | 126 | Not started | bar: 2016-09-19 to 2016-09-23
|  |  | Communications team to support dissemination of marketing materials |  |  | Comms | 2016-09-19 | 2016-09-23 | 4 | 2016-05-20 | 126 | Not started | bar: 2016-09-19 to 2016-09-23
|  |  | Develop communication for third offering to be made in November |  |  | Comms | 2016-09-26 | 2016-10-28 | 32 | 2016-05-20 | 161 | Not started | bar: 2016-09-26 to 2016-10-28
| C.11 |  | Open window for second offering |  |  | Jemma Ball | 2016-08-01 | 2016-08-26 | 25 | 2016-05-20 | 98 | Not started | bar: 2016-08-01 to 2016-08-26
| C.12 |  | Assess most popular options and most effective methods of communication |  |  | Jemma Ball | 2016-08-29 | 2016-09-02 | 4 | 2016-05-20 | 105 | Not started | bar: 2016-08-29 to 2016-09-02
| C.13 |  | Review learnings to shape outline for third offering |  |  | Jemma Ball | 2016-09-19 | 2016-09-23 | 4 | 2016-05-20 | 126 | Not started | bar: 2016-09-19 to 2016-09-23
| C.14 |  | Develop communication for third offering to be made in November |  |  | Jemma Ball | 2016-09-26 | 2016-10-28 | 32 | 2016-05-20 | 161 | Not started | bar: 2016-09-26 to 2016-10-28
| C.15 |  | Obtain promotion materials from options supplier |  |  | Jemma Ball | 2016-09-26 | 2016-10-07 | 11 | 2016-05-20 | 140 | Not started | bar: 2016-09-26 to 2016-10-07
| C.16 |  | Launch third offering in November - communications via email (eG etc.) |  |  | Jemma Ball | 2016-09-26 | 2016-10-28 | 32 | 2016-05-20 | 161 | Not started | bar: 2016-09-26 to 2016-10-28
| C.17 |  | Hold roadshows across various sites to promote uptake of the offerings |  |  | Jemma Ball | 2016-09-26 | 2016-10-28 | 32 | 2016-05-20 | 161 | Not started | bar: 2016-09-26 to 2016-10-28
|  |  | Communications team to support dissemination of marketing materials |  |  | Comms | 2016-10-28 | 2016-10-28 | 0 | 2016-05-20 | 161 | Not started | bar: 2016-10-28
| D.2 |  | Track benefits for first offering |  |  | PL/JB | 2016-05-02 | 2016-05-06 | 4 | 2016-05-20 | -14 | Not started
| D.4 |  | Track benefits for second offering |  |  | PL/JB | 2016-08-29 | 2016-09-02 | 4 | 2016-05-20 | 105 | Not started
| D.6 |  | Track benefits for third offering |  |  | PL/JB | 2016-11-28 | 2016-12-02 | 4 | 2016-05-20 | 196 | Not started
Project 2 : Apprentices
| A.4 |  | Contact at least one GM from each area that used apprentices during FY1516 to understand their experience Contact at least one GM from each area that used apprentices during FY1516 to understand their experience |  |  | MR | 2016-02-08 | 2016-02-19 | 11 | 2016-05-20 | -91 | Complete | [38 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Showcase apprentices achievements internally and on social media |  |  | Comms | 2016-03-01 | 2016-03-15 | 14 | 2016-05-20 | -66 | Not started | [60 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Identify potential media opportunities |  |  | Comms | 2016-04-15 | 2016-04-30 | 15 | 2016-05-20 | -20 | Not started | [105 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| B.1 |  | Design communications plan(targeted at divisions) to promote the use of apprentices across SGH for post Easter cohort |  |  | PL/MR & Comms | 2016-02-22 | 2016-03-04 | 11 | 2016-05-20 | -77 | Not started | [52 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| B.2 |  | Create FAQs answer sheet to dispel myths around use of apprentices |  |  | PL/MR & Comms | 2016-02-22 | 2016-03-04 | 11 | 2016-05-20 | -77 | Not started | [52 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | HR to ensure apprentices page on the new intranet | Intranet |  | HR & Comms | 2016-07-01 | 2016-08-01 | 31 | 2016-05-20 | 73 | Not started | bar: 2016-07-01 to 2016-08-01
| B.3 |  | Design road show to explain benefits of apprentices to the Trust |  |  | PL/MR | 2016-02-22 | 2016-03-04 | 11 | 2016-05-20 | -77 | Not started | [52 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| C.1 |  | Hold road show events in order to generate interest for the Easter cohort |  |  | PL/MR | 2016-03-07 | 2016-03-25 | 18 | 2016-05-20 | -56 | Not started | [66 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Create trust branded guidance and training materials for staff taking on apprentices their area |  |  | Comms | 2016-04-01 | 2016-04-30 |  | 2016-05-20 |  | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Invite apprentices to speak at AGM |  |  | Comms | 2016-06-15 | 2016-07-07 | 22 | 2016-05-20 | 48 | Not started | bar: 2016-06-15 to 2016-07-07
|  |  | Interview apprentices for social media and internal communications |  |  | Comms | 2016-06-15 | 2016-07-07 | 22 | 2016-05-20 | 48 | Not started | bar: 2016-06-15 to 2016-07-07
|  |  | Interview new apprentices recruited to the trust for internal communications |  |  | Comms | 2016-07-15 | 2016-07-16 | 1 | 2016-05-20 | 57 | Not started | bar: 2016-07-15 to 2016-07-16
|  |  | Interview new apprentices recruited to the trust for internal communications |  |  | Comms | 2016-11-15 | 2016-11-16 | 1 | 2016-05-20 | 180 | Not started | bar: 2016-11-15 to 2016-11-16
|  |  | Begin Trust-wide communication in advance of third FY1617 cohort |  |  | Comms | 2016-11-07 | 2016-11-11 | 4 | 2016-05-20 | 175 | Not started | bar: 2016-11-07 to 2016-11-11
| D.2 |  | Track benefits for first offering |  |  | PL/JB | 2016-05-02 | 2016-05-06 | 4 | 2016-05-20 | -14 | Not started | [122 empty] | 1 | 1 | 1 | 1 | 1 | [22 empty] | 2016-12-31: #REF!; 2017-01-01: #REF!
| D.4 |  | Track benefits for second offering |  |  | PL/JB | 2016-08-29 | 2016-09-02 | 4 | 2016-05-20 | 105 | Not started | bar: 2016-08-29 to 2016-09-02
| D.6 |  | Track benefits for third offering |  |  | PL/JB | 2016-11-28 | 2016-12-02 | 4 | 2016-05-20 | 196 | Not started | bar: 2016-11-28 to 2016-12-02
Project 3: Non nursing Agency Reductions
| B.5 |  | Design recruitment strategies with HR to maximise the conversion of agency to substantive - Admin & Clerical |  |  |  | 2016-02-22 | 2016-03-04 | 11 | 2016-05-20 | -77 | Not started | [52 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| B.6 |  | Design recruitment strategies with HR to maximise the conversion of agency to substantive - Additional Professional Groups |  |  | PJ/JW/CL | 2016-02-22 | 2016-03-04 | 11 | 2016-05-20 | -77 | Not started | [52 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| B.7 |  | Design recruitment strategies with HR to maximise the conversion of agency to substantive - Additional Clinical Services |  |  | PJ/JW/CL | 2016-02-22 | 2016-03-04 | 11 | 2016-05-20 | -77 | Not started | [52 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| B.8 |  | Design recruitment strategies with HR to maximise the conversion of agency to substantive - Medical and Dental |  |  | PJ/JW/CL | 2016-02-22 | 2016-03-04 | 11 | 2016-05-20 | -77 | Not started | [52 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Provide communication support to recruitment team to support to maximise the conversion of agency to substantive |  |  | PJ/JW/CL & Comms | 2016-02-22 | 2016-03-04 | 11 | 2016-05-20 | -77 | Not started | [52 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| B.9 |  | Design communications plan to clarify expectations across the Trust (non-use of agency staff) |  |  | PJ/JW/CL | 2016-02-22 | 2016-03-04 | 11 | 2016-05-20 | -77 | Not started | [52 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Communications team to work with HR to understand all expectations and influences such as agency cap to create comms plan |  |  | PJ/JW/CL & Comms | 2016-02-22 | 2016-03-04 | 11 | 2016-05-20 | -77 | Not started | [52 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Communications to ensure that plan is linked to e rostering campaign to educate staff on the benefits of rostering 8 weeks in advance | Comms plan | E rostering | Comms | 2016-02-22 | 2016-03-04 | 11 | 2016-05-20 | -77 | Not started | [52 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Implement communications plan | Comms plan |  | PJ/JW/CL & Comms | 2016-03-07 | 2016-03-11 | 4 | 2016-05-20 | -70 | Not started | [66 empty] | 1 | 1 | 1 | 1 | 1
|  |  | Create communications strategy to influence turnover levels where staff feel supported and want to stay | Comms strategy |  | Comms & HR | 2016-04-14 | 2016-05-15 | 31 | 2016-05-20 | -5 | Not started | [104 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Work with HR to illicit benefits for converting from agency to substantive staff |  |  | PJ/JW/CL & Comms | 2016-03-01 | 2016-03-07 | 6 | 2016-05-20 | -74 | Not started | [60 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Meet with HR to discuss overarching/messaging fairness, equality, transparency and patient facing time for 'Temporary staffing, staff benefits and apprentices' | Campaign |  | WB/HR/Comms | 2016-04-05 | 2016-04-30 |  | 2016-05-20 |  | Not started | [95 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Discuss use of agency staff by ward at chief nurse surgery (monthly) | Chief nurse surgery |  | Comms | 2016-04-14 | 2016-12-14 | 244 | 2016-05-20 | 208 | Not started | [104 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-12-14
| D.1 |  | Benefits to be tracked via monthly financials | Senior leaders briefing |  | Comms & Finance | 2016-04-04 | 2017-04-04 | 365 | 2016-05-20 | 319 | Not started | [94 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2017-01-01
|  |  | Communicate monthly financial benefits at Senior leaders briefing | Senior leaders briefing |  | Comms & Finance | 2016-04-04 | 2017-04-04 | 365 | 2016-05-20 | 319 | Not started | [94 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2017-01-01
|  |  | HR to present at each DMB use of agency/bank staff by division | DMB |  | HR | 2016-04-14 | 2016-12-14 | 244 | 2016-05-20 | 208 | Not started | [104 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-12-14
|  |  | Ensure communications plan links to new intranet redesign and information is posted to the home page such as current agency use | Internet |  | Comms | 2016-07-01 | 2016-07-01 | 0 | 2016-05-20 | 42 | Not started | bar: 2016-07-01
|  |  | Ensure workforce data is regularly published to the homepage on the intranet | Intranet |  | Comms | 2016-07-01 | 2016-07-01 | 0 | 2016-05-20 | 42 | Not started | bar: 2016-07-01
|  |  | Ensure communications messaging includes recommending apprentices to replace agency/bank staff | messaging | link to apprentices | Comms | 2016-05-01 | 2016-05-31 | 30 | 2016-05-20 | 11 | Not started | [121 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-05-31
|  |  | Undertake a review of the 'work with us' section on the website to improve recruitment | website | link to creating standardised recruitment protocol | Comms | 2016-06-01 | 2016-07-01 | 30 | 2016-05-20 | 42 | Not started | bar: 2016-06-01 to 2016-07-01
|  |  | Redesign work for us pages on the website | website |  | Comms | 2016-07-01 | 2016-08-01 | 31 | 2016-05-20 | 73 | Not started | bar: 2016-07-01 to 2016-08-01
|  |  | Utilise social media as an opportunity for recruitment and retention | social media |  | Comms | 2016-07-01 | 2016-08-01 | 31 | 2016-05-20 | 73 | Not started | bar: 2016-07-01 to 2016-08-01
|  |  | Design social media for recruitment strategy to reduce use of agency staff | social media |  | Comms | 2016-06-01 | 2016-08-01 | 61 | 2016-05-20 | 73 | Not started | bar: 2016-06-01 to 2016-08-01
|  |  | Design creative social media recruitment campaign i.e. 'we 100 nurses' | social media |  | Comms | 2016-06-01 | 2016-08-01 | 61 | 2016-05-20 | 73 | Not started | bar: 2016-06-01 to 2016-08-01
|  |  | Implement creative social media campaign | social media |  | Comms | 2016-08-01 | 2016-11-01 | 92 | 2016-05-20 | 165 | Not started | bar: 2016-08-01 to 2016-11-01
|  |  | Implement social media for recruitment strategy to reduce use of agency staff | social media |  | Comms | 2016-08-01 | 2017-03-01 | 212 | 2016-05-20 | 285 | Not started | bar: 2016-08-01 to 2017-01-01
Project 4: Local CEAs
| C.1 |  | Present EMT Paper proposing to remove budget |  |  | CL | 2016-02-02 | 2016-03-04 | 31 | 2016-05-20 | -77 | Not started | [32 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Work with medical director to address sensitivities, the impact on morale and wider messaging |  |  | Medical director & Comms | 2016-04-01 | 2016-04-30 | 29 | 2016-05-20 | -20 | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Meet with Medical director to discuss the most appropriate model for communications with consultants such as the Consultant meetings |  |  | Medical director & Comms | 2016-04-01 | 2016-04-01 | 0 | 2016-05-20 | -49 | Not started | [91 empty] | 1
|  |  | 1:1 meetings between managers and staff |  |  | tbc | 2016-04-01 | 2016-04-01 | 0 | 2016-05-20 | -49 | Not started | [91 empty] | 1
| D.1 |  | If agreement is reached, remove agreed portion of CEA budget |  |  | CL/TP | 2016-02-29 | 2016-03-04 | 4 | 2016-05-20 | -77 | Not started
Project 5: Payroll review
| B.1 |  | Design communications plan |  |  | PL/CJ/JW | 2016-02-01 | 2016-02-12 | 11 | 2016-05-20 | -98 | Not started | [31 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| B.2 |  | Implement communications plan |  |  | PL/CJ/JW | 2016-02-15 | 2016-02-26 | 11 | 2016-05-20 | -84 | Not started | [45 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Work with HR to understand messaging to support the reduce the level of unusually high special payment and ensure greater compliance with AfC T&Cs |  |  | Comms | 2016-04-01 | 2016-04-30 | 29 | 2016-05-20 | -20 | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| C.7 |  | EMT approval of controls to prevent further overpayments |  |  | EMT | 2016-04-11 | 2016-04-15 | 4 | 2016-05-20 |  | Not started | [101 empty] | 1 | 1 | 1 | 1 | 1
| C.9 |  | Implementation of controls to prevent overpayments, etc. |  |  | PL/CL/JW | 2016-04-18 | 2017-03-31 | 347 | 2016-05-20 |  | Not started | [108 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2017-01-01
|  |  | Design standardised communications to Trust staff impacted by the Payroll review These communications will need to be aligned to and signpost the Trust's overpayment policy and provide staff with guidance about how to safely repay overpayments |  |  | Comms | 2016-04-01 | 2016-04-30 | 29 | 2016-05-20 | -20 | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Create internal communications if system errors are highlighted within the payroll validation process with GMs resulting in redesigned / simplified SOPs and templates between the operational teams and payroll |  |  | Comms | 2016-04-01 | 2016-04-30 | 29 | 2016-05-20 | -20 | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Sign off repayment plans with individuals |  |  | CL/TP | 2016-04-18 | 2016-06-10 | 53 | 2016-05-20 | 21 | Not started | [108 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-06-10
|  |  | Communicate the benefits and outcomes of the repayment plans via corporate channels | Senior leaders briefing |  | Comms | 2016-07-01 | 2016-08-01 | 31 | 2016-05-20 | 73 | Not started | bar: 2016-07-01 to 2016-08-01
Reducing Average unit cost pay - Nursing and midwifery
Nursing Establishment Review - Phase 2 Nursing Bands 8+ senior nurses
Project 1: Day case Ward Establishment Review
To incorporate into overall communications plan for Phase 2 Nursing Bands 8+ senior nurses
Project 2: DDNG/ HoN / Matrons NER Phase 2
| B.21 |  | Communications plan outlined |  |  | Comms | 2016-01-25 | 2016-02-12 |  | 2016-05-20 | -98 | Not started | [24 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| C.15 |  | Communications Plan actioned |  |  | Comms | 2016-02-15 | 2016-02-19 |  | 2016-05-20 | -91 | Not started | [45 empty] | 1 | 1 | 1 | 1 | 1
|  |  | Meet with Chief Nurse/Deputy Chief nurse to understand outcomes from review |  |  | Comms | 2016-04-15 | 2016-04-30 |  | 2016-05-20 | -20 | Not started | [105 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Create targeted communications so that front line staff understand what is required to complete the projects |  |  | Comms | 2016-04-15 | 2016-04-30 |  | 2016-05-20 | -20 | Not started | [105 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Create targeted stakeholder communications |  |  | Comms | 2016-04-01 | 2016-08-01 |  | 2016-05-20 | 73 | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-08-01
|  |  | Ensure all relevant policies such as 'safe staffing' are accessible from the intranet |  |  | Comms | 2016-04-01 | 2016-05-01 |  | 2016-05-20 | -19 | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Project 3: Cancer CNS NER Phase 2
| B.23 |  | Communications plan outlined |  | 0 | Comms | 2016-01-25 | 2016-02-12 |  | 2016-05-20 | -98 | Not started | [24 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| C.16 |  | Communications Plan actioned |  | 0 | Comms | 2016-02-05 | 2016-02-19 |  | 2016-05-20 | -91 | Not started | [35 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Meet with Chief Nurse/Deputy Chief nurse to understand outcomes from review |  |  | Comms | 2016-04-15 | 2016-04-30 |  | 2016-05-20 | -20 | Not started | [105 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Create targeted communications so that front line staff understand what is required to complete the projects |  |  | Comms | 2016-04-15 | 2016-04-30 |  | 2016-05-20 | -20 | Not started | [105 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Create targeted stakeholder communications |  |  | Comms | 2016-04-01 | 2016-05-01 |  | 2016-05-20 | -19 | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Ensure all relevant policies such as 'safe staffing' are accessible from the intranet |  |  | Comms | 2016-04-01 | 2016-05-01 |  | 2016-05-20 | -19 | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Project 4: CNS NER Phase 2
| B.23 |  | Communications plan outlined |  | 0 | Comms | 2016-01-25 | 2016-02-12 |  | 2016-05-20 | -98 | Not started | [24 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| C.16 |  | Communications Plan actioned |  | 0 | Comms | 2016-02-05 | 2016-02-19 |  | 2016-05-20 | -91 | Not started | [35 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Meet with Chief Nurse/Deputy Chief nurse to understand outcomes from review |  |  | Comms | 2016-04-15 | 2016-04-30 |  | 2016-05-20 | -20 | Not started | [105 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Create targeted communications so that front line staff understand what is required to complete the projects |  |  | Comms | 2016-04-15 | 2016-04-30 |  | 2016-05-20 | -20 | Not started | [105 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Create targeted stakeholder communications |  |  | Comms | 2016-04-01 | 2016-05-01 |  | 2016-05-20 | -19 | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Ensure all relevant policies such as 'safe staffing' are accessible from the intranet |  |  | Comms | 2016-04-01 | 2016-05-01 |  | 2016-05-20 | -19 | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Project 5: PE and Clinical Teachers NER Phase 2
| B.23 |  | Communications plan outlined |  | 0 | Comms | 2016-01-25 | 2016-02-12 |  | 2016-05-20 | -98 | Not started | [24 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| C.16 |  | Communications Plan actioned |  | 0 | Comms | 2016-02-05 | 2016-02-19 |  | 2016-05-20 | -91 | Not started | [35 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Meet with Chief Nurse/Deputy Chief nurse to understand outcomes from review |  |  | Comms | 2016-04-15 | 2016-04-30 |  | 2016-05-20 | -20 | Not started | [105 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Create targeted communications so that front line staff understand what is required to complete the projects |  |  | Comms | 2016-04-15 | 2016-04-30 |  | 2016-05-20 | -20 | Not started | [105 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Create targeted stakeholder communications |  |  | Comms | 2016-04-01 | 2016-05-01 |  | 2016-05-20 | -19 | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Ensure all relevant policies such as 'safe staffing' are accessible from the intranet |  |  | Comms | 2016-04-01 | 2016-05-01 |  | 2016-05-20 | -19 | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Project 6: Nurse / Midwives Consultants NER Phase 2
| B.23 |  | Communications plan outlined |  | 0 | Comms | 2016-01-25 | 2016-02-12 |  | 2016-05-20 | -98 | Not started | [24 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| C.16 |  | Communications Plan actioned |  | 0 | Comms | 2016-02-05 | 2016-02-19 |  | 2016-05-20 | -91 | Not started | [35 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Meet with Chief Nurse/Deputy Chief nurse to understand outcomes from review |  |  | Comms | 2016-04-15 | 2016-04-30 |  | 2016-05-20 | -20 | Not started | [105 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Create targeted communications so that front line staff understand what is required to complete the projects |  |  | Comms | 2016-04-15 | 2016-04-30 |  | 2016-05-20 | -20 | Not started | [105 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Create targeted stakeholder communications |  |  | Comms | 2016-04-01 | 2016-05-01 |  | 2016-05-20 | -19 | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Ensure all relevant policies such as 'safe staffing' are accessible from the intranet |  |  | Comms | 2016-04-01 | 2016-05-01 |  | 2016-05-20 | -19 | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Project 7: Research Nurse NER Phase 2
| B.20 |  | Communications plan outlined |  | 0 | Comms | 2016-01-25 | 2016-02-12 |  | 2016-05-20 | -98 | Not started | [24 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| C.15 |  | Communications Plan actioned |  | 0 | Comms | 2016-02-05 | 2016-02-19 |  | 2016-05-20 | -91 | Not started | [35 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Meet with Chief Nurse/Deputy Chief nurse to understand outcomes from review |  |  | Comms | 2016-04-15 | 2016-04-30 |  | 2016-05-20 | -20 | Not started | [105 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Create targeted communications so that front line staff understand what is required to complete the projects |  |  | Comms | 2016-04-15 | 2016-04-30 |  | 2016-05-20 | -20 | Not started | [105 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Create targeted stakeholder communications |  |  | Comms | 2016-04-01 | 2016-05-01 |  | 2016-05-20 | -19 | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Ensure all relevant policies such as 'safe staffing' are accessible from the intranet |  |  | Comms | 2016-04-01 | 2016-05-01 |  | 2016-05-20 | -19 | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Project 8: Bed Managers NER Phase 2
| B.20 |  | Communications plan outlined |  | 0 | Comms | 2016-01-25 | 2016-02-12 |  | 2016-05-20 | -98 | Not started | [24 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| C.15 |  | Communications Plan actioned |  | 0 | Comms | 2016-02-05 | 2016-02-19 |  | 2016-05-20 | -91 | Not started | [35 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Meet with Chief Nurse/Deputy Chief nurse to understand outcomes from review |  |  | Comms | 2016-04-15 | 2016-04-30 |  | 2016-05-20 | -20 | Not started | [105 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Create targeted communications so that front line staff understand what is required to complete the projects |  |  | Comms | 2016-04-15 | 2016-04-30 |  | 2016-05-20 | -20 | Not started | [105 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Create targeted stakeholder communications |  |  | Comms | 2016-04-01 | 2016-05-01 |  | 2016-05-20 | -19 | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Ensure all relevant policies such as 'safe staffing' are accessible from the intranet |  |  | Comms | 2016-04-01 | 2016-05-01 |  | 2016-05-20 | -19 | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Project 9: Infection Control Nurses NER Phase 2
| B.20 |  | Communications plan outlined |  | 0 | Comms | 2016-01-25 | 2016-02-12 |  | 2016-05-20 | -98 | Not started | [24 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| C.15 |  | Communications Plan actioned |  | 0 | Comms | 2016-02-05 | 2016-02-19 |  | 2016-05-20 | -91 | Not started | [35 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Meet with Chief Nurse/Deputy Chief nurse to understand outcomes from review |  |  | Comms | 2016-04-15 | 2016-04-30 |  | 2016-05-20 | -20 | Not started | [105 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Create targeted communications so that front line staff understand what is required to complete the projects |  |  | Comms | 2016-04-15 | 2016-04-30 |  | 2016-05-20 | -20 | Not started | [105 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Create targeted stakeholder communications |  |  | Comms | 2016-04-01 | 2016-05-01 |  | 2016-05-20 | -19 | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Ensure all relevant policies such as 'safe staffing' are accessible from the intranet |  |  | Comms | 2016-04-01 | 2016-05-01 |  | 2016-05-20 | -19 | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Project 10: Midwives NER Phase 2
| B.20 |  | Communications plan outlined |  | 0 | Comms | 2016-01-25 | 2016-02-12 |  | 2016-05-20 | -98 | Not started | [24 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| C.15 |  | Communications Plan actioned |  | 0 | Comms | 2016-02-05 | 2016-02-19 |  | 2016-05-20 | -91 | Not started | [35 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Meet with Chief Nurse/Deputy Chief nurse to understand outcomes from review |  |  | Comms | 2016-04-15 | 2016-04-30 |  | 2016-05-20 | -20 | Not started | [105 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Create targeted communications so that front line staff understand what is required to complete the projects |  |  | Comms | 2016-04-15 | 2016-04-30 |  | 2016-05-20 | -20 | Not started | [105 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Create targeted stakeholder communications |  |  | Comms | 2016-04-01 | 2016-05-01 |  | 2016-05-20 | -19 | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Ensure all relevant policies such as 'safe staffing' are accessible from the intranet |  |  | Comms | 2016-04-01 | 2016-05-01 |  | 2016-05-20 | -19 | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Project 11: AHP Establishment Review
| B.22 |  | Communications plan outlined |  | 0 | Comms | 2016-01-25 | 2016-02-12 |  | 2016-05-20 | -98 | Not started | [24 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| C.16 |  | Communications Plan actioned |  | 0 | Comms | 2016-02-05 | 2016-02-19 |  | 2016-05-20 | -91 | Not started | [35 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Meet with Chief Nurse/Deputy Chief nurse to understand outcomes from review |  |  | Comms | 2016-04-15 | 2016-04-30 |  | 2016-05-20 | -20 | Not started | [105 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Create targeted communications so that front line staff understand what is required to complete the projects |  |  | Comms | 2016-04-15 | 2016-04-30 |  | 2016-05-20 | -20 | Not started | [105 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Create targeted stakeholder communications |  |  | Comms | 2016-04-01 | 2016-05-01 |  | 2016-05-20 | -19 | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Ensure all relevant policies such as 'safe staffing' are accessible from the intranet |  |  | Comms | 2016-04-01 | 2016-05-01 |  | 2016-05-20 | -19 | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| C.15 | Project 1: Day case Ward Establishment Review | Trust Board paper drafted | J Hall | 2016-04-01 | Comms | 2016-04-01 | 2016-04-30 |  | 2016-05-20 | -20 | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| D.5 | Project 1: Day case Ward Establishment Review | Financial budget adjustments validated | SFMs | 2016-03-12 | Comms | 2016-03-12 | 2016-04-12 |  | 2016-05-20 | -38 | Not started | [71 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| D.6 | Project 2: DDNG/ HoN / Matrons NER Phase 2 | Financial budget adjustments validated | SFMs | 2016-04-27 | Comms | 2016-04-27 | 2016-04-29 |  | 2016-05-20 | -21 | Not started | [117 empty] | 1 | 1 | 1
| D.6 | Project 3: Cancer CNS NER Phase 2 | Financial budget adjustments validated | SFMs | 2016-04-27 | Comms | 2016-04-27 | 2016-04-29 |  | 2016-05-20 | -21 | Not started | [117 empty] | 1 | 1 | 1
| D.6 | Project 4: CNS NER Phase 2 | Financial budget adjustments validated | SFMs | 2016-04-27 | Comms | 2016-04-27 | 2016-04-29 |  | 2016-05-20 | -21 | Not started | [117 empty] | 1 | 1 | 1
| D.6 | Project 5: PE and Clinical Teachers NER Phase 2 | Financial budget adjustments validated | SFMs | 2016-04-27 | Comms | 2016-04-27 | 2016-04-29 |  | 2016-05-20 | -21 | Not started | [117 empty] | 1 | 1 | 1
| D.6 | Project 6: Nurse / Midwives Consultants NER Phase 2 | Financial budget adjustments validated | SFMs | 2016-04-27 | Comms | 2016-04-27 | 2016-04-29 |  | 2016-05-20 | -21 | Not started | [117 empty] | 1 | 1 | 1
| D.6 | Project 7: Research Nurse NER Phase 2 | Financial budget adjustments validated | SFMs | 2016-04-27 | Comms | 2016-04-27 | 2016-04-29 |  | 2016-05-20 | -21 | Not started | [117 empty] | 1 | 1 | 1
| D.6 | Project 8: Bed Managers NER Phase 2 | Financial budget adjustments validated | SFMs | 2016-04-27 | Comms | 2016-04-27 | 2016-04-29 |  | 2016-05-20 | -21 | Not started | [117 empty] | 1 | 1 | 1
| D.6 | Project 9: Infection Control Nurses NER Phase 2 | Financial budget adjustments validated | SFMs | 2016-04-27 | Comms | 2016-04-27 | 2016-04-29 |  | 2016-05-20 | -21 | Not started | [117 empty] | 1 | 1 | 1
| D.6 | Project 10: Midwives NER Phase 2 | Financial budget adjustments validated | SFMs | 2016-04-27 | Comms | 2016-04-27 | 2016-04-29 |  | 2016-05-20 | -21 | Not started | [117 empty] | 1 | 1 | 1
| D.6 | Project 11: AHP Establishment Review | Financial budget adjustments validated | Finance Lead | 2016-08-15 | Comms | 2016-08-15 | 2016-09-12 |  | 2016-05-20 | 115 | Not started | bar: 2016-08-15 to 2016-09-12
Reducing Average unit cost pay - Nursing and midwifery
Project 1 Agency Caps
| A.5 |  | Standardise process for booking agency nurses, in and out of hours, across divisions |  |  | Jeanette Hetherington | 2016-02-08 | 2016-08-12 | Key Milestone | 2016-05-20 | 186 | Complete | [38 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-08-12
|  |  | Ensure that the standardised process is included on the Bank page on new intranet | intranet |  | Jeanette Hetherington | 2016-07-01 | 2016-08-01 |  | 2016-05-20 |  | Not started | bar: 2016-07-01 to 2016-08-01
| A.8 |  | Collaborate with Finance to design a weekly agency spend report that can be interpreted by the Nursing team |  |  | Jeanette Hetherington& Comms | 2016-02-08 | 2016-03-18 |  | 2016-05-20 |  | In Progress | [38 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Share the outcomes from the weekly agency spend report at the chief nurse surgery (information presented by ward) | chief nurse surgery |  | Comms | 2016-05-01 | 2017-01-01 |  | 2016-05-20 |  | Not started | [121 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2017-01-01
| A.10 |  | Identify appropriate steps to communicate the Trust requirement to use framework agencies for current non framework agency staff in order to maximise the shift to framework or bank or substantive |  |  | Comms | 2016-02-08 | 2016-03-18 |  | 2016-05-20 |  | In Progress | [38 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Create a communications plan to communicate the Trust requirement to use framework agencies for current non framework agency staff in order to maximise the shift to framework or bank or substantive |  |  | Jeanette Hetherington& Comms | 2016-04-01 | 31/04/2106 |  | 2016-05-20 |  | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2017-01-01
|  |  | Design a communications plan to proactively share achievement towards agency target |  |  | Comms | 2016-04-01 | 2016-05-01 |  | 2016-05-20 |  | In Progress | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| A.11 |  | Meet with Commissioner to work with them to agree plans for services in the event of staffing issues. |  |  | Jennie Hall | 2016-02-18 | 2016-03-18 |  | 2016-05-20 |  | In Progress | [48 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Share good news stories with external stakeholders re SGH agency performance | external stakeholder newsletter |  | Comms | 2016-06-01 | 2016-06-01 |  | 2016-05-20 |  | Not started | bar: 2016-06-01
| A.14 |  | Create a tool for managers to know how much money is available to spend on agency |  |  | Tak Pang | 2016-02-08 | 2016-02-29 |  | 2016-05-20 |  | In Progress | [38 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Communicate new tool to managers |  |  | HR/Comms | 2016-04-01 | 2016-04-30 |  | 2016-05-20 |  | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Ensure that new tool is included on Bank/HR page on the intranet | intranet |  | HR/Comms | 2016-07-01 | 2016-07-31 |  | 2016-05-20 |  | Not started | bar: 2016-07-01 to 2016-07-31
| B.6 |  | Retrospective bookings and authorisation of who worked to be identified and reported to Chief Nurse as a monitoring tool to ensure process can be improved |  |  | Chief Nurse | 2016-02-02 | 2016-03-31 |  | 2016-05-20 |  | Not started | [32 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Share the outcomes from the retrospective review of bookings and authorisation of who worked at the chief nurse surgery (information presented by ward) | chief nurse surgery |  | Chief Nurse/Comms | 2016-05-01 | 2017-01-01 |  | 2016-05-20 |  | Not started | [121 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2017-01-01
|  |  | Take steps to switch agency staff from non framework to framework agencies |  |  | DDNGs / HoNS | 2016-02-02 | 2016-02-12 |  | 2016-05-20 |  | Not started | [32 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| C.1 |  | Agreement of processes for booking agency nurses, in and out of hours, across divisions with DDNGs and HoNs |  |  | Hazel Tonge / DDNG / Jeanette Hetherington | 2016-02-02 | 2016-02-12 |  | 2016-05-20 |  | Not started | [32 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Share success to switch agency staff from non framework to framework agencies and agreement of process for booking agency nurses at Senior leaders | Snr leaders briefing |  | Comms | 2016-05-01 | 2017-01-01 |  | 2016-05-20 |  | Not started | [121 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2017-01-01
| C.4 |  | Communicate the Trust requirement to use Re communicate the requirement for staff to use framework agencies, extend this communication to non framework agency staff in order to encourage the maximum shift to framework or bank or substantive roles |  |  | Comms | 2016-02-02 | 2016-02-12 |  | 2016-05-20 |  | Not started | [32 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| C.7 |  | Chief Nurse to report to Trust Board on a monthly basis |  |  | Comms | 2016-02-02 | 2016-03-31 |  | 2016-05-20 |  | In progress | [32 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Chief Nurse to report to Chief Nurse Surgery on a monthly basis | chief nurse surgery |  | Chief Nurse Comms | 2016-03-31 | 2017-01-31 |  | 2016-05-20 |  | Not started | [90 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2017-01-01
|  |  | Create communications strategy for CQRG (Clinical Quality Reference Group) with Acute and Community attended by commissioners |  |  | Comms |  |  | 0 | 2016-05-20 | 0 | Not started
Project 2 Overseas recruitment
|  |  | Design exhibition materials for recruitment of 125 nurses in the Philippines |  |  | Comms | 2016-02-01 | 2015-03-31 |  | 2016-05-20 | -416 | In progress
|  |  | Work in partnership with HR to design 'welcome to SGH programme' for new overseas nurses |  |  | Comms | 2016-08-01 | 2016-09-01 |  | 2016-05-20 | 104 | Not started | bar: 2016-08-01 to 2016-09-01
|  |  | Communications team to review all materials used at recruitment fairs |  | professional identity | Comms | 2016-05-01 | 2016-05-31 |  | 2016-05-20 | 11 | Not started | [121 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-05-31
|  |  | Redesign of communications materials to incorporate 'professional identity workstream' |  |  | Comms | 2016-05-31 | 2016-07-01 |  | 2016-05-20 | 42 | Not started | bar: 2016-05-31 to 2016-07-01
|  |  | Business case to purchase IPad for recruitment fairs |  |  | Comms | 2016-05-15 | 2016-05-31 | 16 | 2016-05-20 | 11 | Not started | [135 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-05-31
0
Project 3 Management of E rostering
| A.2 |  | Heat map for rostering to be created. Expectation set that each area will create a roster 8 weeks in advance (communications team to share at F2F such as Snr leaders and Chief Nurse Surgery) |  | link | Hazel Tonge | 2016-01-01 | 2016-02-28 | 58 | 2016-05-20 | -82 | In progress |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| A.3 |  | Clear expectation on roster management standards sent for consultation amongst the Matrons, HoNs and ward leaders. Implementing to be agreed at the nursing board then issued to the nursing cohort by Jennie Hall (communications team to support) |  | link | Helene Anderson / Sian Weller / Jennie Hall | 2016-02-26 | 2016-02-29 | 3 | 2016-05-20 | -81 | In progress | [56 empty] | 1 | 1 | 1 | 1
|  |  | Communications support the project team to achieve previous 2 tasks |  | link | Comms | 2016-04-01 | 2016-04-30 | 29 | 2016-05-20 | -20 | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Stakeholder specific communications re benefits to trust/service/individual (8wk rostering) |  | link | Comms | 2016-05-01 | 2016-07-02 | 62 | 2016-05-20 | 43 | Not started | [121 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-07-02
|  |  | Ensure the HR area on the intranet consolidates and signposts to leave and bank polices, EOL online and provides clear instructions and guides for staff using the bank system |  |  | Comms, HR & Bank | 2016-05-01 | 2016-07-31 | 91 | 2016-05-20 | 72 | Not started | [121 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-07-31
| B.1 |  | The standards of roster management to be implemented on a month by month basis |  |  | ward leader / HON | 2016-03-01 | 2016-12-31 | 305 | 2016-05-20 | 225 | Not started | [60 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-12-31
| B.2 |  | 6-8 week roster lock down and rosters to be fully approved by agreed date |  |  | DDNGs | 2016-03-01 | 2016-12-31 | 305 | 2016-05-20 | 225 | Not started | [60 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-12-31
| B.3 |  | Rota is published for staff approval - Minimum of 4 weeks before roster start date |  |  | HoNs | 2016-03-01 | 2016-04-30 | 60 | 2016-05-20 | -20 | Not started | [60 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| B.4 |  | Matron approves rota for publishing - 4 weeks before roster start date |  |  | HoNs | 2016-03-01 | 2016-04-30 | 60 | 2016-05-20 | -20 | Not started | [60 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| B.5 |  | Ward Manager Approval - 6 weeks before roster start date |  |  | HoNs | 2016-03-01 | 2016-04-30 | 60 | 2016-05-20 | -20 | Not started | [60 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| B.6 |  | Rota is closed to staff requests - 8 weeks before roster start date |  |  | HoNs | 2016-03-01 | 2016-04-30 | 60 | 2016-05-20 | -20 | Not started | [60 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| B.7 |  | Live finalisation of the roster at the end of each day |  |  | HoNs | 2016-03-01 | 2016-04-30 | 60 | 2016-05-20 | -20 | Not started | [60 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| D.4 |  | Fill rate is above 90% |  |  | Hazel Tonge | 2016-04-01 | 2017-04-01 | 365 | 2016-05-20 | 316 | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2017-01-01
|  |  | Create communications plan to increase compliance and uptake of e-rostering & to ensure the previous 7 tasks are embedded throughout the organisations |  |  | Comms /Helene Anderson | 2016-04-01 | 2016-04-30 | 29 | 2016-05-20 | -20 | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Project 4 Mental Health Project
|  |  | Create RMN posts for 3-6 months to implement new process, provide guidance an monitor use of RMN's for 1:1 nursing |  |  |  | 2016-02-02 | 2016-04-02 | 60 | 2016-05-20 | -48 | In progress | [32 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Communicate new process and guidance to all nursing and medical staff | process |  | Gillian Tertois / Julie Goldie | 2016-04-02 | 2016-04-30 | 28 | 2016-05-20 | -20 | Not started | [92 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Communicate new policy to all nursing and medical staff |  |  | Gillian Tertois / Julie Goldie | 2016-04-02 | 2016-02-29 | -33 | 2016-05-20 | -81 | Not started
|  |  | Patient Experience Audit |  |  | Hazel Tonge | 2016-04-01 | 2017-04-01 | 365 | 2016-05-20 | 316 | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2017-01-01
|  |  | Provide support for patient experience audit and share outcomes with stakeholders |  |  | Comms | 2016-04-01 | 2017-04-01 | 365 | 2016-05-20 | 316 | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2017-01-01
Project 5 Direct entry student Nurses
|  |  | Create case studies for internal and external communications |  |  | Comms | 2016-09-01 | 2016-09-30 | 29 | 2016-05-20 |  | Not started | bar: 2016-09-01 to 2016-09-30
Project 6 Rotational Posts
|  |  | Share outcomes from project at Chief Nurse Surgery |  |  | Comms | 2016-09-01 | 2016-09-30 | 29 | 2016-05-20 |  | Not started | bar: 2016-09-01 to 2016-09-30
Project 7 Community Liaison
|  |  | Design communications plan that exploits creating links with European universities nursing schools to scope the possibility of joint training initiatives and long term international recruitment. |  |  | Comms | 2016-06-01 | 2016-07-01 | 30 | 2016-05-20 |  | Not started | bar: 2016-06-01 to 2016-07-01
Project 8 Professional Identity
| A.1 |  | Support the professional identity project is working to create a recognised identity for a St. Georges Nurse or Midwife. |  |  | AL & Comms | 2016-01-01 | 2016-07-01 | 182 | 2016-05-20 | 42 | In progress |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-07-01
|  |  | Produce concept design for SGH nurses badge |  |  | Comms | 2016-02-15 | 2016-03-15 | 29 | 2016-05-20 | -66 | In progress | [45 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Create internal and external competition for badge design |  |  | Comms | 2016-03-15 | 2017-04-30 | 411 | 2016-05-20 | 345 | In progress | [74 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2017-01-01
|  |  | Integrate the outcomes from the professional identity project in to the St Georges branding such as on website and/ recruitment and PR |  |  | Comms | 2016-05-01 | 2016-12-31 | 244 | 2016-05-20 | 225 | In progress | [121 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-12-31
Clinical administration
Consultant Job Planning
| A.1 |  | Communication to all consultants of activity job planning process |  |  | SMK | 2016-01-25 | 2016-01-29 | 4 | 2016-05-20 | -112 | completed | [24 empty] | 1 | 1 | 1 | 1 | 1
| A.2 |  | Draft research tariff changes and communicate (within Job Planning Guidance) |  |  | CL | 2016-02-01 | 2016-02-05 | 4 | 2016-05-20 | -105 | In progress | [31 empty] | 1 | 1 | 1 | 1 | 1
| A.3 |  | Draft Education tariff changes and communicate (within Job Planning Guidance) |  |  | CL | 2016-02-01 | 2016-02-05 | 4 | 2016-05-20 | -105 | In progress | [31 empty] | 1 | 1 | 1 | 1 | 1
| A.4 |  | Draft summary of tariff for clinical activities JP communication (within Job Planning Guidance) |  |  | CL | 2016-02-08 | 2016-02-12 | 4 | 2016-05-20 | -98 | In progress | [31 empty] | 1 | 1 | 1 | 1 | 1
| A.5 |  | Hold two evening workshops for Care group Lead/CD/DC FAQ session - invite sent |  |  | CL / NS | 2016-02-08 | 2016-02-26 | 18 | 2016-05-20 | -84 | In progress | [38 empty] | 1 | 1 | 1 | 1 | 1
| A.6 |  | Medical Board (use this as comms session) to Divisional Chairs |  |  | SMK | 2016-02-08 | 2016-02-26 | 18 | 2016-05-20 | -84 | completed | [38 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| C.1 |  | Implementation of job plan changes in Allocate |  |  | CL / Care Group leads | 2016-04-29 | 2016-06-20 | 52 | 2016-05-20 | 52 | Not started | [119 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-06-20
|  |  | Create communications plan to include the following |  |  | Comms | 2016-04-15 | 2016-05-01 | 16 | 2016-05-20 | -19 | Not started | [105 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Medical Director will communicate requirements and deliverables to divisional Chairs through Medical Board |  |  | Comms | 2016-04-15 | 2016-05-01 | 16 | 2016-05-20 | -19 | Not started | [105 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Fortnightly Medical Workforce Steering with Divisional Chair representation |  |  | Comms | 2016-04-15 | 2016-05-01 | 16 | 2016-05-20 | -19 | Not started | [105 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Divisional Chairs to lead divisions in delivering job planning through the medical management structure. This will be monitored by the Steering Group and COO at regular performance reviews. |  |  | Comms | 2016-04-15 | 2016-05-01 | 16 | 2016-05-20 | -19 | Not started | [105 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Care Group Lead to be reminded of job planning guidance and tariff (especially education and research guidelines) |  |  | Comms | 2016-04-15 | 2016-05-01 | 16 | 2016-05-20 | -19 | Not started | [105 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Care group leads who are job planning for the first time should be trained |  |  | Comms | 2016-04-15 | 2016-05-01 | 16 | 2016-05-20 | -19 | Not started | [105 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | All consultants in individual meetings to be reminded of job planning guidance |  |  | Comms | 2016-04-15 | 2016-05-01 | 16 | 2016-05-20 | -19 | Not started | [105 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Care group Leads and Medical HR will communicate to the Steering group the findings on safe staffing and hard recruit vacancies |  |  | Comms | 2016-04-15 | 2016-05-01 | 16 | 2016-05-20 | -19 | Not started | [105 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Regular support and reinforcement by AMD (HR) and Medical HR manager |  |  | Comms | 2016-04-15 | 2016-05-01 | 16 | 2016-05-20 | -19 | Not started | [105 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | To mandate across the Trust the implementation of Medirota and buddy up care groups to transition the new system into business-as-usual |  |  | Comms | 2016-04-15 | 2016-05-01 | 16 | 2016-05-20 | -19 | Not started | [105 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | To bank staff rota team to ensure process for booking bank staff through this team is effective (as this is not facilitated through MediRota) |  |  | Comms | 2016-04-15 | 2016-05-01 | 16 | 2016-05-20 | -19 | Not started | [105 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| B.3 |  | Divisions to report a clear plan to the Chief Nurse to make savings whilst maintaining quality and safety in line with the National guidance - Nursing and Midwifery Workforce Board | DDNG's |  | Project 1: Agency Cap | 2016-02-02 | 2016-02-27 | 25 | 2016-05-20 |  | In progress | [32 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| C.3 |  | Agreement with framework suppliers in relation to implementation of national rates | Jeanette Hetherington |  | Project 1: Agency Cap | 2016-02-02 | 2016-02-12 | 10 | 2016-05-20 |  | In progress | [32 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| D.1 |  | Agency spend in nursing is less than 10% | Jennie Hall |  | Project 1: Agency Cap | 2015-10-01 | 2016-04-01 | 183 | 2016-05-20 |  | In progress |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| D.2 |  | Agency spend in nursing is less than 8% | Jennie Hall |  | Project 1: Agency Cap | 2016-04-01 | 2017-04-01 | 365 | 2016-05-20 |  | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2017-01-01
| B.7 |  | Confirm which wards the overseas nurses will be working on with DDNGs and HoNS | Paul Silke |  | Project 2 :International recruitment | 2016-06-01 | 2016-09-30 | 121 | 2016-05-20 |  | Not started | bar: 2016-06-01 to 2016-09-30
| D.2 |  | Roster is fully approved 8 weeks in advance | Helene Anderson / DDNGs |  | Project 3: Management of rostering | 2016-04-01 | 2017-04-01 | 365 | 2016-05-20 |  | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2017-01-01
| D.1 |  | Monitoring spend on 1:1 RMN nursing | Tak Pang |  | Project 4: Mental Health Project | 2016-04-01 | 2017-04-01 | 365 | 2016-05-20 |  | In progress | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2017-01-01
| C.3 |  | Deliver 85% student nurses direct entry by September 2016 | Paul Silke |  | Project 5: Direct entry student nurses | 2016-09-01 | 2016-12-01 | 91 | 2016-05-20 |  | Not started | bar: 2016-09-01 to 2016-12-01
| C.1 |  | Map areas for future rotations | Robert Bleasdale |  | Project 6: Rotational posts | 2015-10-16 | 2015-12-17 | 62 | 2016-05-20 |  | In progress
1
|  | Safe Staffing | [10 empty] | 1
|  |  | Integrate safe staffing messages into consultant job planning messages |  |  | Comms | 2016-04-15 | 2016-05-01 | 16 | 2016-05-20 | -19 | Not started | [105 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
1
|  | Hard to recruit Medics |  |  | STANDARDRECRUITMENT | [7 empty] | 1
| A.2 |  | Confirmation of medical workforce and identification of hard to recruit vacancies from output of meeting 1 |  |  | Care Group leads | 2016-02-08 | 2016-02-26 | 18 | 2016-05-20 | -84 | Not started | [38 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Work with medical team to create external recruitment campaign |  |  | HR & Comms | 2016-07-01 | 2017-01-31 |  | 2016-05-20 | 256 | Not started | bar: 2016-07-01 to 2017-01-01
|  |  | Communications team to create standardised approach to support staff recruitment website/events/social media) |  |  | HR & Comms | 2016-07-01 | 2017-01-31 |  | 2016-05-20 | 256 | Not started | bar: 2016-07-01 to 2017-01-01
1
|  | Medical rostering software | [10 empty] | 1
|  |  | Communications to support the project team to rollout medical rostering software -support with guides and training |  |  | Comms | 2016-04-01 | 2016-04-30 | 29 | 2016-05-20 | -20 | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Stakeholder specific communications re benefits to trust/service/individual (8wk rostering) |  |  | Comms | 2016-05-01 | 2016-07-02 | 62 | 2016-05-20 | 43 | Not started | [121 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-07-02
|  |  | Ensure the HR area on the intranet consolidates and signposts to leave and bank polices, EOL online and provides clear instructions and guides for staff using the bank system |  |  | Comms, HR & Bank | 2016-05-01 | 2016-07-31 | 91 | 2016-05-20 | 72 | Not started | [121 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-07-31
1
|  | Spans & Layers | [10 empty] | 1
| C.33 |  | Hold workshop for Nursing and Midwifery task and finish group to review spans of control outputs |  |  | TT / GS | 2016-03-28 | 2016-04-01 | 4 | 2016-05-20 | -49 | Not started | [87 empty] | 1 | 1 | 1 | 1 | 1
| C.34 |  | Hold workshop for Divisional Admin and Clerical task and finish group to review spans of control outputs |  |  | TT / GS | 2016-03-28 | 2016-04-01 | 4 | 2016-05-20 | -49 | Not started | [87 empty] | 1 | 1 | 1 | 1 | 1
| C.35 |  | Hold workshop for AHP task and finish group to review spans of control outputs |  |  | TT / GS | 2016-03-28 | 2016-04-01 | 4 | 2016-05-20 | -49 | Not started | [87 empty] | 1 | 1 | 1 | 1 | 1
| C.36 |  | Hold workshop for Medical task and finish group to review spans of control outputs |  |  | TT / GS | 2016-03-28 | 2016-04-01 | 4 | 2016-05-20 | -49 | Not started | [87 empty] | 1 | 1 | 1 | 1 | 1
| C.37 |  | Hold workshop for Corporate Services Admin and Clerical task and finish group to review spans of control outputs |  |  | TT / GS | 2016-03-28 | 2016-04-01 | 4 | 2016-05-20 | -49 | Not started | [87 empty] | 1 | 1 | 1 | 1 | 1
| E.1 |  | Develop communications strategy and plan (conducted by central comms team) |  |  | Comms | 2016-01-16 | 2016-12-31 | 350 | 2016-05-20 | 225 | Not started | [87 empty] | 1 | 1 | 1 | 1 | 1
| E.2 |  | Review and amend communications plan (conducted by central comms team in conjunction with the Steering Group) |  |  | Comms | 2016-01-16 | 2016-12-31 | 350 | 2016-05-20 | 225 | Not started | [15 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-12-31
| E.3 |  | Implement communication plan (conducted by central comms team) |  |  | Comms | 2016-01-16 | 2016-12-31 | 350 | 2016-05-20 | 225 | Not started | [15 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-12-31
|  |  | Design communications plan/messaging to inform staff why we are making changes to the management structure |  |  | Comms | 2016-04-01 | 2016-04-30 | 29 | 2016-05-20 | -20 | Not started | [15 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-12-31
|  |  | Utilise main corporate comms channels to disseminate messaging |  |  | Comms | 2016-04-30 | 2016-10-31 | 184 | 2016-05-20 | 164 | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
[9 empty] | 0 | [90 empty] | 1 | 1 | 1 | 1 | 1
|  | South West London Bank | [97 empty] | 1 | 1 | 1 | 1 | 1
| A.6 |  | Comms plan to cover each workstream |  |  | Daniel Elkins | 2016-01-01 | 2016-03-30 | 89 | 2016-05-20 | -51 | Not started |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Contact communications teams from 5 partner trusts (marketing) |  |  | Comms/4 trusts | 2016-07-01 | 2016-07-31 | 30 | 2016-05-20 | 72 | Not started | bar: 2016-07-01 to 2016-07-31
|  |  | Agree joint media strategy and sign off protocols |  |  | Comms/4 trusts | 2016-07-01 | 2016-07-31 | 30 | 2016-05-20 | 72 | Not started | bar: 2016-07-01 to 2016-07-31
|  |  | Agree branding between all partners |  |  | Comms/4 trusts | 2016-07-01 | 2016-07-15 | 14 | 2016-05-20 | 56 | Not started | bar: 2016-07-01 to 2016-07-15
|  |  | Press and media opportunities (interviews with Wendy Brewer etc.) |  |  | Comms/Media | 2016-09-01 | 2016-11-01 | 61 | 2016-05-20 | 165 | Not started | bar: 2016-09-01 to 2016-11-01
|  |  | Internal SWL Bank campaign and awareness raising (through corp Comms) |  |  | Comms | 2016-07-01 | 2016-08-31 | 61 | 2016-05-20 | 103 | Not started | bar: 2016-07-01 to 2016-08-31
|  |  | Educate staff on the changes to SWL Bank - new pay scales etc. |  |  | Comms | 2016-07-01 | 2016-08-31 | 61 | 2016-05-20 | 103 | Not started | bar: 2016-07-01 to 2016-08-31
|  |  | Utilise new intranet for surveys in to the interest for joining SWL bank |  |  | Comms | 2016-08-01 | 2016-08-31 | 30 | 2016-05-20 | 103 | Not started | bar: 2016-08-01 to 2016-08-31
|  |  | Front of house displays to join SWL staff bank |  |  | Comms | 2016-08-01 | 2016-08-31 | 30 | 2016-05-20 | 103 | Not started | bar: 2016-08-01 to 2016-08-31
| D.1 |  | Seek reliable case studies |  |  | Daniel Elkins | 2016-10-01 | 2016-10-30 | 29 | 2016-05-20 | 163 | Not started | bar: 2016-10-01 to 2016-10-30
|  |  | Utilise case studies for local media and to continue internal campaigns |  |  | Comms | 2016-10-30 | 2016-10-01 | -29 | 2016-05-20 | 134 | Not started
|  |  | SWLBank launch media release |  |  | Comms | 2016-09-01 | 2016-09-01 | 0 | 2016-05-20 | 104 | Not started | bar: 2016-09-01
|  |  | SWL Bank launch internal communications |  |  | Comms | 2016-09-01 | 2016-09-01 | 0 | 2016-05-20 | 104 | Not started | bar: 2016-09-01
|  |  | MP briefings |  |  | Comms | 2016-10-01 | 2016-11-01 | 31 | 2016-05-20 | 165 | Not started | bar: 2016-10-01 to 2016-11-01
|  |  | Local authority briefings |  |  | Comms | 2016-10-01 | 2016-11-01 | 31 | 2016-05-20 | 165 | Not started | bar: 2016-10-01 to 2016-11-01
|  |  | OSC briefings |  |  | Comms | 2016-10-01 | 2016-11-01 | 31 | 2016-05-20 | 165 | Not started | bar: 2016-10-01 to 2016-11-01
|  |  | Work with DH & NHSE to announce new partnership |  |  | Comms | 2016-09-01 | 2016-09-01 | 0 | 2016-05-20 | 104 | Not started | bar: 2016-09-01
| D.6 | Project 1: SWL Bank | Implementation Phase | Jemma Ball |  | Jemma Ball | 2016-07-30 | 2016-12-31 | 154 | 2016-05-20 | 225 | Not started | bar: 2016-07-30 to 2016-12-31
| A.6 | Project 4: Increase Stag Pure Bank | SG Bank reaches its optimal size | Jeanette Hetherington |  | Jeanette Hetherington | 2016-09-01 | 2016-09-30 | 29 | 2016-05-20 | 133 | Not started | bar: 2016-09-01 to 2016-09-30
|  | Project 2: Implementation of rostering recommendations | [8 empty] | 0 |  | 1
| A.1 |  | Change roster policy to stipulate 6 weeks prior to start date |  | link | Sian Weller | 2016-04-01 | 2016-04-30 | 29 | 2016-05-20 | -20 | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| A.2 |  | 100% of rosters to be completed on time |  | link | Jennie Hall | 2016-04-30 | 2016-05-30 | 30 | 2016-05-20 | 10 | Not started | [120 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-05-30
|  |  | Communicate new roster policy to stakeholders |  | link | Comms | 2016-05-01 | 2016-07-01 | 61 | 2016-05-20 | 42 | Not started | [121 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-07-01
|  |  | Stakeholder specific communications re benefits to trust/service/individual (8wk rostering) |  | link | Comms | 2016-05-01 | 2016-07-02 | 62 | 2016-05-20 | 43 | Not started | [121 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-07-02
|  |  | Trust wide communications campaign on the use of e-rostering sustained over 6 months |  |  | Comms | 2016-05-01 | 2016-07-02 | 62 | 2016-05-20 | 43 | Not started | [121 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-07-02
1
|  | Project 3: Changes to workforce information | [6 empty] | 0 | 2016-05-20 | 0 |  | 1
| A.3 |  | Communications support on a decision on whether to move to ESR self service |  |  | Wendy Brewer & Comms | 2016-09-03 | 2016-09-30 | 27 | 2016-05-20 | 133 | Not started | bar: 2016-09-03 to 2016-09-30
1
|  | Project 4 Increase SGH Pure Bank | [6 empty] | 0 | 2016-05-20 | 0 |  | 1
| A.1 |  | Identify marketing partner |  |  | Jemma Ball | 2016-02-14 | 2016-02-28 | 14 | 2016-05-20 | -82 | Not started | [44 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Communications to support to agree marketing partner |  |  | Comms | 2016-02-14 | 2016-02-28 | 14 | 2016-05-20 | -82 | Not started | [44 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Communications team to support HR with branding and content guidelines |  |  | Comms | 2016-04-01 | 2016-05-01 | 30 | 2016-05-20 | -19 | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Integration of marketing campaign in to external corporate channels (Social media/Website |  |  | Comms | 2016-06-01 | 2016-07-01 | 30 | 2016-05-20 | 42 | Not started | bar: 2016-06-01 to 2016-07-01
| A.4 |  | Recruitment exercise commences |  |  | Comms | 2016-03-14 | 2016-07-30 | 138 | 2016-05-20 | 71 | Not started | [73 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-07-30
|  |  | Communications team to create standardised approach to support staff recruitment website/events/social media) |  |  | Comms | 2016-05-01 | 2016-07-01 | 61 | 2016-05-20 | 42 | Not started | [121 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-07-01
|  |  | Support internal rollout of recruitment exercise |  |  | Comms | 2016-03-14 | 2016-07-30 | 138 | 2016-05-20 | 71 | Not started | [73 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-07-30
Medical workforce review
Planning / Preparation
Activity Data Book Development
Communication
| A.1 |  | Communication to all consultants of activity job planning process |  |  | SMK | 2016-01-25 | 2016-01-29 | 4 | 2016-05-20 |  | completed | [24 empty] | 1 | 1 | 1 | 1 | 1
| A.2 |  | Draft research tariff changes and communicate (within Job Planning Guidance) |  |  | CL | 2016-02-01 | 2016-02-05 | 4 | 2016-05-20 |  | In progress | [31 empty] | 1 | 1 | 1 | 1 | 1
| A.3 |  | Draft Education tariff changes and communicate (within Job Planning Guidance) |  |  | CL | 2016-02-01 | 2016-02-05 | 4 | 2016-05-20 |  | In progress | [31 empty] | 1 | 1 | 1 | 1 | 1
| A.4 |  | Draft summary of tariff for clinical activities JP communication (within Job Planning Guidance) |  |  | CL | 2016-02-08 | 2016-02-12 | 4 | 2016-05-20 |  | In progress | [38 empty] | 1 | 1 | 1 | 1 | 1
| A.5 |  | Hold two evening workshops for Care group Lead/CD/DC FAQ session - invite sent |  |  | CL / NS | 2016-02-08 | 2016-02-26 | 18 | 2016-05-20 |  | In progress | [38 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| A.6 |  | Medical Board (use this as comms session) to Divisional Chairs |  |  | SMK | 2016-02-08 | 2016-02-26 | 18 | 2016-05-20 |  | completed | [38 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| C.1 |  | Issue updated guidance required |  |  | CL | 2016-02-08 | 2016-02-12 | 4 | 2016-05-20 |  | Not started | [38 empty] | 1 | 1 | 1 | 1 | 1
| C.2 |  | Update JP guidance for 2016/17 for next year |  |  | CL | 2016-06-21 | 2016-06-25 | 4 | 2016-05-20 |  | Not started | bar: 2016-06-21 to 2016-06-25
| C.3 |  | Development of 5 year workforce strategy |  |  | CL | 2016-06-22 | 2016-09-01 | 71 | 2016-05-20 |  | Not started | bar: 2016-06-22 to 2016-09-01
| D.1 |  | Link in to overarching communications plan for all Trust wide schemes |  |  | SMK | 2016-01-04 | 2016-06-25 | 173 | 2016-05-20 |  | Not started |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-06-25
Care Group Review (meetings 1 -3 databook validation)
Job Planning Analysis and Outcome
Junior Doctor Rota Review
Continue to work with the Medical director to alleviate concerns of Jnr Drs
Project 7: Rota Rollout
Job Planning Analysis and Outcome
| A.4 | Job Planning Analysis and Outcome | Calculate additional DCC investment or savings from output of meeting 2 for review at meeting 3 |  |  | CL / NS | 2016-06-07 | 2016-06-24 | 17 | 94 |  | Not started
| D.1 | Job Planning Analysis and Outcome | Savings calculated per cost code |  |  | Finance Lead | 2016-06-21 | 2016-07-06 | 15 | 106 |  | Not started
| B.1 | Junior Doctor Rota Review | Recommendations on alternative workforce or roles for medical workforce plan as output of meeting 3 |  |  | Care Group leads | 2016-04-29 | 2016-06-20 | 52 | 90 |  | Not started
| C.1 | Project 7: Rota Rollout | Rollout complete -1st August |  |  | CL | 2016-06-30 | 2016-08-01 | 32 | 132 |  | Not started
1
CLINCAL TRANSFORMATION | [12 empty] | 1
|  | Theatres Productivity | [10 empty] | 1
|  |  | Review of staff satisfaction experience |  |  | Working Group | 2016-04-30 | 2016-07-20
|  |  | Communicate to all theatre staff regarding strategy, vision, changes proposed |  |  | Comms | 2016-04-15 | 2016-05-15 |  | 2016-05-20 | -5 | Not started | [105 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Communication via one2ones regarding changes to T&C's and roles |  |  | Comms | 2016-04-15 | 2016-05-15 |  | 2016-05-20 | -5 | Not started | [105 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Staff wide communications regarding integration of theatre services and the effects on them and their roles. |  |  | Comms | 2016-04-21 | 2016-04-28 |  | 2016-05-20 | -22 | Not started | [111 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Use key corporate communications channels to inform of progress, updates and outcomes |  |  | Comms | 2016-04-01 | 2016-12-31 |  | 2016-05-20 | 225 | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-12-31
|  |  | Set up theatres team briefing sessions |  |  | Comms | 31/04/2016 | 2016-07-31 |  | 2016-05-20 | 72 | Not started
|  |  | Set up regular Face2face team meetings to dominate plans and progress |  |  | Comms | 31/04/2017 | 2016-08-01 |  | 2016-05-20 | 73 | Not started
|  |  | Inform GP's of relevant changes |  |  | Comms | 2016-09-01 | 2016-11-01 |  | 2016-05-20 | 165 | Not started | bar: 2016-09-01 to 2016-11-01
|  |  | Inform patients of changes to processes |  |  | Comms | 2016-09-01 | 2016-11-01 |  | 2016-05-20 | 165 | Not started | bar: 2016-09-01 to 2016-11-01
|  |  | Formal consultation with Theatres staff regarding job roles changes and T&C's |  |  | Comms | 2016-05-01 | 2016-08-31 |  | 2016-05-20 | 103 | Not started | [121 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-08-31
1
|  | Diagnostics | [10 empty] | 1
|  | Workstream 1A: Improve productivity of modalities | [10 empty] | 1
|  | Workstream 1B Increase productivity of reporting exams | [10 empty] | 1
|  | Workstream 2A: Increase capacity at QMH | [10 empty] | 1
|  | Workstream2B: Realise Integrated Management Structure | [10 empty] | 1
| A.3 |  | Communication from leadership team to proposed members about the purpose of the workstream and required attendance |  |  | SH/SG | 2016-01-25 | 2016-02-01 | 7 | 2016-05-20 | -109 | In progress | [24 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Inform staff of proposed changes |  |  | Comms | 2015-04-15 | 2015-05-31 | 46 | 2016-05-20 | -355 | Not started
|  |  | Communication with key internal stakeholders e.g. radiographers about progress, advantages and changes to ways of working |  |  | Comms | 2016-05-01 | 2016-05-31 | 30 | 2016-05-20 | 11 | Not started | [121 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-05-31
|  |  | Communications with community service staff |  |  | Comms | 2016-05-01 | 2016-05-31 | 30 | 2016-05-20 | 11 | Not started | [121 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-05-31
|  |  | Communicate outcomes of staff consultation |  |  |  | 2016-07-01 | 2016-08-01 | 31 | 2016-05-20 | 73 | Not started | bar: 2016-07-01 to 2016-08-01
|  |  | Disseminate information internally through transformation times, website and face2face meetings |  |  | Comms | 2016-04-30 | 2017-01-31 | 276 | 2016-05-20 | 256 | Not started | [120 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2017-01-01
|  |  | Setup diagnostic teams briefing sessions |  |  |  | 2016-04-30 | 2017-01-31 | 276 | 2016-05-20 | 256 | Not started | [120 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2017-01-01
|  |  | Communication specifically for consultants around change behaviour |  |  | Comms | 2016-04-30 | 2017-05-30 | 395 | 2016-05-20 | 375 | Not started | [120 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2017-01-01
|  |  | Medical chair meetings |  |  | Comms | 2016-04-30 | 2016-06-30 | 61 | 2016-05-20 | 41 | Not started | [120 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-06-30
|  |  | Inform external stakeholders about changes |  |  | Comms | 2016-05-01 | 2016-07-01 | 61 | 2016-05-20 | 42 | Not started | [121 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-07-01
|  |  | Communicate new process to external stakeholders |  |  | Comms | 2016-05-01 | 2016-07-01 | 61 | 2016-05-20 | 42 | Not started | [121 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-07-01
|  |  | GP newsletter |  |  | Comms | 2016-05-01 | 2016-07-01 | 61 | 2016-05-20 | 42 | Not started | [121 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-07-01
|  |  | Website content |  |  | Comms | 2016-05-01 | 2016-06-01 | 31 | 2016-05-20 | 12 | Not started | [121 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-06-01
|  |  | Promote new diagnostic services in the community |  |  | Comms | 2016-05-02 | 2016-11-01 | 183 | 2016-05-20 | 165 | Not started | [122 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-11-01
|  |  | Communications to internal stakeholders on change to processes and news ways of working |  |  | Comms | 2016-05-01 | 2016-11-01 | 184 | 2016-05-20 | 165 | Not started | [121 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-11-01
| D.5 |  | Benefits realisation and monitoring |  |  | SH | 2016-04-01 | 2017-03-31 | 364 | 2016-05-20 | 315 | Not started | #REF!
| Patient Flow Programme | [11 empty] | 1
|  | ED reducing attendances and streamlining processes | [10 empty] | 1
|  | Throughput processes on short stay wards : AMU, SAU, PAU (internal) | [10 empty] | 1
|  | Internal Processes | [10 empty] | 1
|  | Discharge Processes | [10 empty] | 1
|  | Avoiding attendances and admissions | [10 empty] | 1
|  | Discharge Pathways | [10 empty] | 1
|  |  | Understand the outcomes from the McKinsey workshop on patient flow communications |  |  | Comms | 2016-04-01 | 2016-04-15 |  | 2016-05-20 | -35 | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Provide dedicated resource to support the patient flow campaign |  |  | Comms | 2016-04-29 | 2016-04-29 |  | 2016-05-20 | -21 | Not started
|  |  | Create communications strategy for the patient flow programme to include the six key strands |  |  | Comms | 2019-04-01 | 2016-05-29 |  | 2016-05-20 | 9 | Not started
| Outpatients | [11 empty] | 1
| C.1 |  | Central communications plan - outline of key Trust wide messages drafted |  |  | LY & Improvement | 2016-01-18 | 2016-01-22 | 4 | 2016-05-20 | -119 | Complete | [17 empty] | 1 | 1 | 1 | 1 | 1
| C.2 |  | Meet comms team and discuss comms requirements |  |  | LY & Improvement | 2016-01-19 | 2016-01-23 | 4 | 2016-05-20 | -118 | Complete | [18 empty] | 1 | 1 | 1 | 1 | 1
| C.3 |  | Comms team draft comms plan |  |  | Roz Harvey & Comms | 2016-01-24 | 2016-02-19 | 26 | 2016-05-20 | -91 | Not Started | [23 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| C.4 |  | Comms plan agreed with Improvement team |  |  | RH & Comms | 2016-02-20 | 2016-03-04 | 13 | 2016-05-20 | -77 | Not Started | [50 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| C.5 |  | Central Comms plan implemented |  |  | RH & Comms | 2016-03-23 | 2016-04-11 | 19 | 2016-05-20 | -39 | Not Started | [82 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| D.1 |  | GP comms plan drafted (to include initial project overview briefing with GPs/CCGs and ERS/Changes to automated referrals) |  |  | GP Liaison lead/Imp | 2016-02-01 | 2016-02-29 | 28 | 2016-05-20 | -81 | Not Started | [31 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| D.2 |  | GP comms plan approved by OSB |  |  | GP Liaison lead/Imp | 2016-03-01 | 2016-03-16 | 15 | 2016-05-20 | -65 | Not Started | [60 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| D.3 |  | GP Comms plan implemented (this will be on-going during the duration of the programme) |  |  | GP Liaison lead/Imp | 2016-03-15 | 2016-03-17 | 2 | 2016-05-20 | -64 | Not Started | [74 empty] | 1 | 1 | 1
| E.1 |  | Template for local comms drafted |  |  | LY & Improvement | 2016-01-01 | 2016-01-12 | 11 | 2016-05-20 | -129 | Complete |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| E.2 |  | Key stakeholders identified (DDO/GM/Patient etc.) and contacted regarding comms plan |  |  | LY & Improvement | 2016-01-13 | 2016-01-20 | 7 | 2016-05-20 | -121 | Complete | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| E.3 |  | Agreement for distribution of local comms (OP clinical director/Divisional Meetings etc.) |  |  | LY & Improvement | 2016-01-19 | 2016-01-22 | 3 | 2016-05-20 | -119 | Complete | [18 empty] | 1 | 1 | 1 | 1
| E.4 |  | First draft of February communications complete and shared with CD/CWDT for comment |  |  | LY & Improvement | 2016-01-22 | 2016-01-30 | 8 | 2016-05-20 | -111 | Complete | [21 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| E.5 |  | February communications amended with comments |  |  | LY & Improvement | 2016-02-01 | 2016-02-04 | 3 | 2016-05-20 | -106 | Complete | [31 empty] | 1 | 1 | 1 | 1
| E.6 |  | Final draft of communications complete |  |  | LY & Improvement | 2016-02-02 | 2016-02-05 | 3 | 2016-05-20 | -105 | Complete | [32 empty] | 1 | 1 | 1 | 1
| E.7 |  | February communications distributed through agreed channels (Clinical director etc.) |  |  | LY & Improvement | 2016-02-06 | 2016-02-12 | 6 | 2016-05-20 | -98 | In progress | [36 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
| E.8 |  | Repeat this process on a monthly basis |  |  | LY & Improvement | 2016-02-09 | 2016-02-13 | 4 | 2016-05-20 | -97 | Complete | [39 empty] | 1 | 1 | 1 | 1 | 1
| F.1 |  | GP comms plan drafted (to include initial project overview briefing with GPs/CCGs and ERS/Changes to automated referrals) |  |  | GP Liaison lead/Imp | 2016-02-01 | 2016-02-29 | 28 | 2016-05-20 | -81 | Not started | [31 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| F.2 |  | GP comms plan approved by OSB |  |  | GP Liaison lead/Imp | 2016-03-01 | 2016-03-16 | 15 | 2016-05-20 | -65 | Not started | [60 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| F.3 |  | GP Comms plan implemented (this will be on-going during the duration of the programme) |  |  | GP Liaison lead/Imp | 2016-03-15 | 2016-03-17 | 2 | 2016-05-20 | -64 | Not started | [74 empty] | 1 | 1 | 1
|  |  | Introductory Outpatient Communications |  |  | OPD | 2016-03-01 | 2016-03-15 | 14 | 2016-05-20 | -66 | Complete | [60 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Email Newsletter |  |  | OPD | 2016-03-01 | 2016-03-15 | 14 | 2016-05-20 | -66 | Complete | [60 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Communication to early specialities in fix - Email newsletter |  |  | OPD | 2016-03-01 | 2016-03-15 | 14 | 2016-05-20 | -66 | Not started | [60 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Business rules draft - Face 2 face communications |  |  | OPD | 2016-03-01 | 2016-03-15 | 14 | 2016-05-20 | -66 | Not started | [60 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Speciality Fix Introduction - Face 2 face |  |  | OPD | 2016-03-01 | 2016-03-15 | 14 | 2016-05-20 | -66 | Not started | [60 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Business Rules - Face 2 face within speciality |  |  | OPD | 2016-03-01 | 2016-03-15 | 14 | 2016-05-20 | -66 | Not started | [60 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Speciality fix roll out - Face2 face within speciality |  |  | OPD | 2016-03-01 | 2016-03-15 | 14 | 2016-05-20 | -66 | Not started | [60 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Speciality fix communications pack - develop and deliver |  |  | OPD | 2016-03-02 | 2016-03-31 | 29 | 2016-05-20 | -50 | Not started | [61 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | final SLA - face2 face within speciality |  |  | OPD | 2016-03-02 | 2016-04-15 | 44 | 2016-05-20 | -35 | Not started | [61 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Trust wide SLA communications |  |  | Comms |  |  | 0 | 2016-05-20 | 0 | Not started | 1
|  |  | Email newsletter and via face to face forums e.g. Snr leaders, chief nurse |  |  | OPD | 2016-04-15 | 2016-05-01 | 16 | 2016-05-20 | -19 | Not started | [105 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | KPI' s shared - face2 face within speciality |  |  | OPD | 2016-04-15 | 2016-04-30 | 15 | 2016-05-20 | -20 | Not started | [105 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Website content and regular newsletter - Internal |  |  | Comms | 2016-04-16 | 2017-04-30 | 379 | 2016-05-20 | 345 | Not started | [106 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2017-01-01
|  |  | DNA Campaign (patients) |  |  | Comms | 2016-07-01 | 2016-12-31 | 183 | 2016-05-20 | 225 | Not started | bar: 2016-07-01 to 2016-12-31
|  |  | Patient portal - focus group for UAT |  |  | Comms | 2016-05-01 | 2016-07-01 | 61 | 2016-05-20 | 42 | Not started | [121 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-07-01
|  |  | Patient Pilot scheme running |  |  | Comms | 2016-06-01 | 2015-07-01 | -336 | 2016-05-20 | -324 | Not started
|  |  | Patient communications programme |  |  | Comms | 2016-05-01 | 2016-07-01 | 61 | 2016-05-20 | 42 | Not started | [121 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-07-01
|  |  | GP Communications Programme |  |  | Comms | 2016-06-01 | 2017-04-01 | 304 | 2016-05-20 | 316 | Not started | bar: 2016-06-01 to 2017-01-01
|  |  | GP liaison to facilitate GP engagement and communications (around changes in referral processes) |  |  | Comms | 2016-06-01 | 2017-04-01 | 304 | 2016-05-20 | 316 | Not started | bar: 2016-06-01 to 2017-01-01
| C.20 | Project 2: IT Fix | Handover model to outpatient team | 2016-07-30 |  | LY & Improvement | 2016-07-30 | 2016-08-30 | 31 | 2016-03-22 |  | Not started
| D.4 | Project 3: Outpatient Specialty Fix | DNA outcomes shared with specialty | 2016-04-12 |  | Speciality | 2016-04-12 | 2016-04-29 | 17 | 2016-03-22 |  | Not started
| D.5 | Project 3: Outpatient Specialty Fix | Specialty to complete New to F/Up analysis and agree plan to address any issue | 2016-04-12 |  | SE | 2016-04-12 | 2016-04-29 | 17 | 2016-03-22 |  | Not started
| E.7 | Project 3: Outpatient Specialty Fix | New templates GO LIVE as per speciality booking horizon ( possible 10-16 week booking horizon per specialty) | 2016-05-02 |  | Project 3: Outpatient Specialty Fix | 2016-05-02 | 2016-06-10 | 39 | 2016-03-22 |  | Not started
| G.3 | Project 3: Outpatient Specialty Fix | Specialty fix - Iclip/ errs/ triage | 2016-06-14 |  | Project 3: Outpatient Specialty Fix | 2016-06-14 | 2016-07-23 | 39 | 2016-03-22 |  | Not started
| H.3 | Project 3: Outpatient Specialty Fix | Specialty fix - Iclip/ errs/ triage | 2016-07-26 |  | Project 3: Outpatient Specialty Fix | 2016-07-26 | 2016-09-03 | 39 | 2016-03-22 |  | Not started
| I.3 | Project 3: Outpatient Specialty Fix | Specialty fix - Iclip/ errs/ triage | 2016-09-06 |  | Project 3: Outpatient Specialty Fix | 2016-09-06 | 2016-10-15 | 39 | 2016-03-22 |  | Not started
| J.3 | Project 3: Outpatient Specialty Fix | Specialty fix - Iclip/ errs/ triage | 2016-10-18 |  | Project 3: Outpatient Specialty Fix | 2016-10-18 | 2016-11-26 | 39 | 2016-03-22 |  | Not started
| K.3 | Project 3: Outpatient Specialty Fix | Specialty fix - Iclip/ errs/ triage | 2017-01-03 |  | Project 3: Outpatient Specialty Fix | 2017-01-03 | 2017-02-11 | 39 | 2016-03-22 |  | Not started
| L.3 | Project 3: Outpatient Specialty Fix | Specialty fix - Iclip/ errs/ triage | 2017-02-14 |  | Project 3: Outpatient Specialty Fix | 2017-02-14 | 2017-03-25 | 39 | 2016-03-22 |  | Not started
PORTFOLIO OPTIMISATION | [12 empty] | 1
|  | Fix, close, transfer | [10 empty] | 1
|  |  | Renal and Vascular | [9 empty] | 1
| B8.6 |  | Board meeting to review and approve findings (categorisation & next steps) |  |  | Board | 2016-03-03 | 2016-03-03 | 0 | 2016-05-20 | -78 | Not started | [62 empty] | 1
| C.3.2 |  | Media strategy developed prior to public engagement |  |  | Comms | 2016-03-03 | 2016-05-02 | 60 | 2016-05-20 | -18 | Not started | [62 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| C.4.1.5 |  | Key stakeholder mapping (patients, staff, other providers, commissioners, local authorities and regulators) |  |  | Central team/Comms | 2016-05-20 | 2016-07-09 | 50 | 2016-05-20 | 50 | Not started | [93 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| C.4.1.6 |  | Development of service specific comms plan (internal, external and media) |  |  | Central team/Comms | 2016-05-20 | 2016-07-09 | 50 | 2016-05-20 | 50 | Not started | [93 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Stakeholder mapping exercise |  |  | Comms | 2016-05-01 | 2016-06-01 | 31 | 2016-05-20 | 12 | Not started | [121 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-06-01
|  |  | Detailed communications plan development |  |  | Comms | 2016-05-01 | 2016-06-01 | 31 | 2016-05-20 | 12 | Not started | [121 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-06-01
|  |  | Define detailed messaging |  |  | Comms | 2016-06-01 | 2015-06-15 | -352 | 2016-05-20 | -340 | Not started
|  |  | Detailed media plan - positive and crisis messaging |  |  | Comms | 2016-06-01 | 2015-06-15 | -352 | 2016-05-20 | -340 | Not started
|  |  | Conversations with commissioners and potential partners around transfer |  |  | Comms | 2016-07-01 | 2016-08-31 | 61 | 2016-05-20 | 103 | Not started | bar: 2016-07-01 to 2016-08-31
|  |  | Crisis media plan development if commissioners discussion go external |  |  | Comms | 2016-09-01 | 2016-09-15 | 14 | 2016-05-20 | 118 | Not started | bar: 2016-09-01 to 2016-09-15
|  |  | Consultation process (if appropriate) |  |  | Comms | 2016-09-01 | 2016-11-30 | 90 | 2016-05-20 | 194 | Not started | bar: 2016-09-01 to 2016-11-30
|  |  | Paediatric medicine (CWDT division) | [5 empty] | 0 | 2016-05-20 | 0 |  | 1
| B8.6 |  | Board meeting to review and approve findings (categorisation & next steps) |  |  | Board | 2016-03-03 | 2016-03-03 | 0 | 2016-05-20 | -78 | Not started | [62 empty] | 1
| C.4.1.5 |  | Key stakeholder mapping (patients, staff, other providers, commissioners, local authorities and regulators) |  |  | Central team/Comms | 2016-05-20 | 2016-07-09 | 50 | 2016-05-20 | 50 | Not started | [93 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| C.4.1.6 |  | Key stakeholder mapping (patients, staff, other providers, commissioners, local authorities and regulators) |  |  | Central team/Comms | 2016-05-20 | 2016-07-09 | 50 | 2016-05-20 | 50 | Not started | [93 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Stakeholder mapping exercise |  |  | Comms | 2016-06-15 | 2016-07-15 | 30 | 2016-05-20 | 56 | Not started | bar: 2016-06-15 to 2016-07-15
|  |  | Detailed communications plan development |  |  | Comms | 2016-06-15 | 2016-07-15 | 30 | 2016-05-20 | 56 | Not started | bar: 2016-06-15 to 2016-07-15
|  |  | Define detailed messaging |  |  | Comms | 2016-07-01 | 2016-07-31 | 30 | 2016-05-20 | 72 | Not started | bar: 2016-07-01 to 2016-07-31
|  |  | Detailed media plan |  |  | Comms | 2016-07-01 | 2016-07-31 | 30 | 2016-05-20 | 72 | Not started | bar: 2016-07-01 to 2016-07-31
|  |  | Public/ staff consultation process (if appropriate) |  |  | Comms | 2016-09-15 | 2017-02-01 | 139 | 2016-05-20 | 257 | Not started | bar: 2016-09-15 to 2017-01-01
|  |  | Tranche 2 - Surgery, Gynaecology, Cardiac Surgery, Obstetrics | [5 empty] | 0 | 2016-05-20 | 0 | Not started | 1
| B8.6 |  | Board meeting to review and approve findings (categorisation & next steps) | [5 empty] | 0 | 2016-05-20 | 0 |  | 1
| C.4.1.5 |  | Board meeting to review and approve findings (categorisation & next steps) |  |  | Central team/Comms | 2016-03-03 | 2016-03-03 | 0 | 2016-05-20 | -78 | Not started | [62 empty] | 1
| C.4.1.6 |  | Key stakeholder mapping (patients, staff, other providers, commissioners, local authorities and regulators) |  |  | Central team/Comms | 2016-05-20 | 2016-07-09 | 50 | 2016-05-20 | 50 | Not started | [93 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Stakeholder mapping exercise |  |  | Comms | 2016-06-15 | 2016-07-15 | 30 | 2016-05-20 | 56 | Not started | bar: 2016-06-15 to 2016-07-15
|  |  | Detailed communications plan development |  |  | Comms | 2016-06-15 | 2016-07-15 | 30 | 2016-05-20 | 56 | Not started | bar: 2016-06-15 to 2016-07-15
|  |  | Define detailed messaging |  |  | Comms | 2016-07-01 | 2016-07-31 | 30 | 2016-05-20 | 72 | Not started | bar: 2016-07-01 to 2016-07-31
|  |  | Detailed media plan |  |  | Comms | 2016-07-01 | 2016-07-31 | 30 | 2016-05-20 | 72 | Not started | bar: 2016-07-01 to 2016-07-31
|  |  | Public/ staff consultation process (if appropriate) |  |  | Comms | 2016-09-15 | 2017-02-01 | 139 | 2016-05-20 | 257 | Not started | bar: 2016-09-15 to 2017-01-01
|  |  | Tranche 3 - CIU, Neurology, Clinical Haematology | [5 empty] | 0 | 2016-05-20 | 0 | Not started
| B8.6 |  | Board meeting to review and approve findings (categorisation & next steps) |  |  | Board | 2016-03-03 | 2016-03-03 | 0 | 2016-05-20 | -78 | Not started | [62 empty] | 1
| C.4.1.5 |  | Board meeting to review and approve findings (categorisation & next steps) |  |  | Central team/Comms | 2016-03-03 | 2016-03-03 | 0 | 2016-05-20 | -78 | Not started | [62 empty] | 1
| C.4.1.6 |  | Key stakeholder mapping (patients, staff, other providers, commissioners, local authorities and regulators) |  |  | Central team/Comms | 2016-05-20 | 2016-07-09 | 50 | 2016-05-20 | 50 | Not started | [93 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Stakeholder mapping exercise |  |  | Comms | 2016-09-15 | 2016-10-31 | 46 | 2016-05-20 | 164 | Not started | bar: 2016-09-15 to 2016-10-31
|  |  | Detailed communications plan development |  |  | Comms | 2016-09-15 | 2016-10-31 | 46 | 2016-05-20 | 164 | Not started | bar: 2016-09-15 to 2016-10-31
|  |  | Define detailed messaging |  |  | Comms | 2016-07-15 | 2016-08-15 | 31 | 2016-05-20 | 87 | Not started | bar: 2016-07-15 to 2016-08-15
|  |  | Detailed media plan |  |  | Comms | 2016-08-01 | 2016-08-31 | 30 | 2016-05-20 | 103 | Not started | bar: 2016-08-01 to 2016-08-31
|  |  | Public/ staff consultation process (if appropriate) |  |  | Comms | 2016-09-15 | 2017-02-01 | 139 | 2016-05-20 | 257 | Not started | bar: 2016-09-15 to 2017-01-01
COMMERCIAL
Neurosurgery
|  |  | Design and build Private Patients website |  |  | Comms | 2016-04-01 | 2016-07-01 | 91 | 2016-05-20 | 42 | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-07-01
|  |  | Face to face meetings - Private Patients team and nurses |  |  | Comms | 2016-04-30 | 2016-05-31 | 31 | 2016-05-20 | 11 | Not started | [120 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-05-31
|  |  | Create engagement and involvement messages |  |  | Comms | 2016-04-30 | 2016-05-31 | 31 | 2016-05-20 | 11 | Not started | [120 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-05-31
|  |  | All staff update on private patient Launch - By George Article & website content |  |  | Comms | 2016-04-30 | 2016-04-30 | 0 | 2016-05-20 |  | Not started | [120 empty] | 1
|  |  | Launch Lunch event for consultants, nurses and supinate Patient sort staff |  |  | Comms | 2016-05-31 | 2016-05-31 | 0 | 2016-05-20 | 11 | Not started | bar: 2016-05-31
|  |  | External Launch |  |  | Comms | 2016-05-31 | 2016-05-31 | 0 | 2016-05-20 | 11 | Not started | bar: 2016-05-31
|  |  | All Staff launch - Website and article content |  |  | Comms | 2016-06-01 | 2016-06-01 | 0 | 2016-05-20 | 12 | Not started | bar: 2016-06-01
|  |  | Managers 121's with teams - Q&A session |  |  | Comms | 2016-04-30 | 2016-04-30 | 0 | 2016-05-20 |  | Not started | [120 empty] | 1
|  |  | Managers 121's with teams - operational aspects |  |  | Comms | 2016-04-30 | 2016-05-31 | 31 | 2016-05-20 | 11 | Not started | [120 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-05-31
|  |  | External GP liaison - Private Patients newsletter, email and website content |  |  | Comms | 2016-05-31 | 2016-05-31 | 0 | 2016-05-20 | 11 | Not started | bar: 2016-05-31
|  |  | Marketing to insurance providers |  |  | Comms | 2016-04-10 | 2017-05-31 | 416 | 2016-05-20 | 376 | Not started | [100 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2017-01-01
|  |  | PR programme for Private Patients consultants |  |  | Comms | 2016-04-07 | 2016-05-07 | 30 | 2016-05-20 | -13 | Not started | [97 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | PR programme for Private Patients consultants |  |  | Comms | 2016-10-01 | 2016-10-31 | 30 | 2016-05-20 | 164 | Not started | bar: 2016-10-01 to 2016-10-31
|  |  | PR programme for Private Patients consultants |  |  | Comms | 2017-01-01 | 2017-01-31 | 30 | 2016-05-20 | 256 | Not started | bar: 2017-01-01
|  |  | Create media plan positive and crisis comms |  |  | Comms | 2016-04-30 | 2016-05-31 | 31 | 2016-05-20 | 11 | Not started | [120 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-05-31
Cardiac Surgery
|  |  | Design and build Private Patients website |  |  | Comms | 2016-04-01 | 2016-07-01 | 91 | 2016-05-20 | 42 | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-07-01
|  |  | Face to face meetings - Private Patients team and nurses |  |  | Comms | 2016-04-30 | 2016-05-31 | 31 | 2016-05-20 | 11 | Not started | [120 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-05-31
|  |  | Create engagement and involvement messages |  |  | Comms | 2016-04-30 | 2016-05-31 | 31 | 2016-05-20 | 11 | Not started | [120 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-05-31
|  |  | All staff update on private patient Launch - By George Article & website content |  |  | Comms | 2016-04-30 | 2016-04-30 | 0 | 2016-05-20 | -20 | Not started | [120 empty] | 1
|  |  | Launch lunch event for consultants, nurses and supinate Patient sort staff |  |  | Comms | 2016-05-31 | 2016-05-31 | 0 | 2016-05-20 | 11 | Not started | bar: 2016-05-31
|  |  | External launch |  |  | Comms | 2016-05-31 | 2016-05-31 | 0 | 2016-05-20 | 11 | Not started | bar: 2016-05-31
|  |  | All Staff launch - Website and article content |  |  | Comms | 2016-06-01 | 2016-06-01 | 0 | 2016-05-20 | 12 | Not started | bar: 2016-06-01
|  |  | Managers 121's with teams - Q&A session |  |  | Comms | 2016-04-30 | 2016-04-30 | 0 | 2016-05-20 | -20 | Not started | [120 empty] | 1
|  |  | Managers 121's with teams - operational aspects |  |  | Comms | 2017-04-30 | 2016-05-31 | -334 | 2016-05-20 | 11 | Not started
|  |  | External GP liaison - Private Patients newsletter, email and website content |  |  | Comms | 2016-05-31 | 2016-05-31 | 0 | 2016-05-20 | 11 | Not started | bar: 2016-05-31
|  |  | Marketing to insurance providers |  |  | Comms | 2016-04-10 | 2017-05-31 | 416 | 2016-05-20 | 376 | Not started | [100 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2017-01-01
|  |  | PR programme for Private Patients consultants |  |  | Comms | 2016-04-07 | 2016-05-07 | 30 | 2016-05-20 | -13 | Not started | [97 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | PR programme for Private Patients consultants |  |  | Comms | 2016-10-01 | 2016-10-31 | 30 | 2016-05-20 | 164 | Not started | bar: 2016-10-01 to 2016-10-31
|  |  | PR programme for Private Patients consultants |  |  | Comms | 2017-01-01 | 2017-01-31 | 30 | 2016-05-20 | 256 | Not started | bar: 2017-01-01
|  |  | Create media plan positive and crisis comms |  |  | Comms | 2016-04-30 | 2016-05-30 | 30 | 2016-05-20 | 10 | Not started | [120 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-05-30
Cardiology
|  |  | Design and build Private Patients website |  |  | Comms | 2016-04-01 | 2016-07-01 | 91 | 2016-05-20 | 42 | Not started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-07-01
|  |  | Face to face meetings - Private Patients team and nurses |  |  | Comms | 2016-04-30 | 2016-05-31 | 31 | 2016-05-20 | 11 | Not started | [120 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-05-31
|  |  | Create engagement and involvement messages |  |  | Comms | 2016-04-30 | 2016-05-31 | 31 | 2016-05-20 | 11 | Not started | [120 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-05-31
|  |  | All staff update on private patient Launch - By George Article & website content |  |  | Comms | 2016-04-30 | 2016-04-30 | 0 | 2016-05-20 | -20 | Not started | [120 empty] | 1
|  |  | Launch lunch event for consultants, nurses and supinate Patient sort staff |  |  | Comms | 2016-05-31 | 2016-05-31 | 0 | 2016-05-20 | 11 | Not started | bar: 2016-05-31
|  |  | External launch |  |  | Comms | 2016-05-31 | 2016-05-31 | 0 | 2016-05-20 | 11 | Not started | bar: 2016-05-31
|  |  | All Staff launch - Website and article content |  |  | Comms | 2016-06-01 | 2016-06-01 | 0 | 2016-05-20 | 12 | Not started | bar: 2016-06-01
|  |  | Managers 121's with teams - Q&A session |  |  | Comms | 2016-04-30 | 2016-04-30 | 0 | 2016-05-20 | -20 | Not started | [120 empty] | 1
|  |  | Managers 121's with teams - operational aspects |  |  | Comms | 2016-04-30 | 2016-05-31 | 31 | 2016-05-20 | 11 | Not started | [120 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-05-31
|  |  | External GP liaison - Private Patients newsletter, email and website content |  |  | Comms | 2016-05-31 | 2016-05-31 | 0 | 2016-05-20 | 11 | Not started | bar: 2016-05-31
|  |  | Marketing to insurance providers |  |  | Comms | 2016-04-10 | 2017-05-31 | 416 | 2016-05-20 | 376 | Not started | [100 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2017-01-01
|  |  | PR programme for Private Patients consultants |  |  | Comms | 2016-04-07 | 2016-05-07 | 30 | 2016-05-20 | -13 | Not started | [97 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | PR programme for Private Patients consultants |  |  | Comms | 2016-10-01 | 2016-10-31 | 30 | 2016-05-20 | 164 | Not started | bar: 2016-10-01 to 2016-10-31
|  |  | PR programme for Private Patients consultants |  |  | Comms | 2017-01-01 | 2017-01-31 | 30 | 2016-05-20 | 256 | Not started | bar: 2017-01-01
|  |  | Create media plan positive and crisis comms |  |  | Comms | 2016-04-30 | 2016-05-31 |  | 2016-05-20 | 11 | Not started | [120 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-05-31
Gibraltar Contract
|  |  | Disseminate all staff communications - website, newsletter, email, briefings |  |  | Comms | 2016-04-30 | 2016-07-01 |  | 2016-05-20 | 42 | Not started | [120 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-07-01
|  |  | Plan for media opportunities throughout 2016 |  |  | Comms | 2016-04-30 | 2016-07-02 |  | 2016-05-20 | 43 | Not started | [120 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-07-02
BACK OFFICE MODERNISATION
| Finance Restructure | [8 empty] | 2016-05-20
|  |  | Agree comms \ briefing notes \ Q&A |  |  | JB/AA | 2016-01-25 | 2016-02-01 |  | 2016-05-20 | -109 | Complete | [24 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Make offer \ contract letter for external posts |  |  | IL/HR | 2016-04-18 | 2016-04-22 |  | 2016-05-20 | -28 | Not started | [108 empty] | 1 | 1 | 1 | 1 | 1
|  |  | Ensure all contact information is updated on the intranet |  |  | Comms | 2016-07-01 | 2016-07-31 |  | 2016-05-20 | 72 | Not started | bar: 2016-07-01 to 2016-07-31
|  |  | Internal communications to all staff to update on the changes within fiancé |  |  | Comms | 2016-05-01 | 2016-05-31 |  | 2016-05-20 | 11 | Not started | [121 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-05-31
|  |  | Ensure any changes to processes are communicated to staff |  |  | Comms | 2016-05-01 | 2016-05-31 |  | 2016-05-20 | 11 | Not started | [121 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-05-31
Payroll options
|  |  | Set up and attend key stakeholder meetings (beginning of engagement process) |  |  | DJS | 2016-02-01 | 2016-03-29 |  | 2016-05-20 | -52 | Not started | [31 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Set up and attend key stakeholder meetings (beginning of engagement process) |  |  | DJS | 2016-02-01 | 2016-03-29 |  | 2016-05-20 | -52 | Not started | [31 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Communications team to meet with SRO to determine current position |  |  | Comms | 2016-04-15 | 2016-04-15 |  | 2016-05-20 | -35 | Not started | [105 empty] | 1
|  |  | Stakeholder meetings to discuss OBC and SS |  |  | DJS |  |  |  |  | 0 | Not started
|  |  | Design staff engagement plan for payroll staff to acknowledge the sensitivity and the effect on staff morale |  |  | Comms | 2016-04-16 | 2016-05-01 |  | 2016-05-20 | -19 | Not started | [106 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | OBC paper for IDG, EMT and Trust board |  |  | DJS | 2016-06-06 | 2016-06-27 |  | 2016-05-20 | 38 | Not started | bar: 2016-06-06 to 2016-06-27
|  |  | Share outcomes from board paper with trust staff (dates tbc final decision) |  |  | Comms | 2016-08-01 | 2016-08-31 |  | 2016-05-20 | 103 | Not started | bar: 2016-08-01 to 2016-08-31
|  |  | Ensure all changes to processes and procedures are shared with trust staff |  |  | Comms | 2016-08-31 | 2017-05-31 |  | 2016-05-20 | 376 | Not started | bar: 2016-08-31 to 2017-01-01
|  |  | Support the production of trust branded and standardised materials by provider |  |  | Comms | 2016-08-31 | 2017-05-31 |  | 2016-05-20 | 376 | Not started | bar: 2016-08-31 to 2017-01-01
Accounts payable
|  |  | Set up and attend key stakeholder meetings (beginning of engagement process) |  |  | DJS | 2016-02-01 | 2016-03-29 |  | 2016-05-20 | -52 | Not started | [31 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Communications team to meet with SRO to determine current position |  |  | Comms | 2016-04-15 | 2016-04-15 |  | 2016-05-20 | -35 | Not started | [105 empty] | 1
|  |  | Provide ongoing communications support as programme develops |  |  | Comms | 2015-04-01 | 2017-01-01 |  | 2016-05-20 | 226 | Not started |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2017-01-01
|  |  | Communications team to meet with HR to understand programme of work for staff interview skills/deployment programme and |  |  | Comms | 2016-04-15 | 2016-04-15 |  | 2016-05-20 | -35 | Not started | [105 empty] | 1
|  |  | Stakeholder meetings to discuss OBC and SS |  |  | DJS | 2016-04-15 | 2016-04-15 |  | 2016-05-20 | -35 | Not started | [105 empty] | 1
|  |  | Design staff engagement plan for payroll staff to acknowledge the sensitivity and the effect on staff morale |  |  | Comms | 2016-04-16 | 2016-05-01 |  | 2016-05-20 | -19 | Not started | [106 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | OBC paper for IDG, EMT and Trust board |  |  | DJS | 2016-06-06 | 2016-06-27 |  | 2016-05-20 | 38 | Not started | bar: 2016-06-06 to 2016-06-27
|  |  | Share outcomes from board paper with trust staff (dates tbc final decision) |  |  | Comms | 2016-08-01 | 2016-08-31 |  | 2016-05-20 | 103 | Not started | bar: 2016-08-01 to 2016-08-31
|  |  | Ensure all changes to processes and procedures are shared with trust staff |  |  | Comms | 2016-08-31 | 2017-05-31 |  | 2016-05-20 | 376 | Not started | bar: 2016-08-31 to 2017-01-01
|  |  | Support the production of trust branded and standardised materials by provider |  |  | Comms | 2016-08-31 | 2017-05-31 |  | 2016-05-20 | 376 | Not started | bar: 2016-08-31 to 2017-01-01
IM&T Outsourcing
|  |  | Set up and attend key stakeholder meetings (beginning of engagement process) |  |  | CH3 | 2016-01-11 | 2016-02-29 |  | 2016-05-20 | -81 | Not started | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Develop communications plan |  |  | JJC | 2016-01-11 | 2016-02-29 |  | 2016-05-20 | -81 | Not started | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Communications team to support the production of communications plan |  |  | Comms | 2015-05-01 | 2015-05-31 |  | 2016-05-20 | -355 | Not started
|  |  | Implement communications plan |  |  | JJC | 2015-05-30 | 2015-08-28 |  | 2016-05-20 | -266 | Not started
|  |  | Create media plan to share successes |  |  | Comms | 2015-05-30 | 2015-08-28 |  | 2016-05-20 | -266 | Not started
|  |  | Provide media support to external agencies to sign off press releases |  |  | Comms | 2015-05-30 | 2015-08-28 |  | 2016-05-20 | -266 | Not started
|  |  | Share outcomes from board paper with trust staff (dates tbc final decision) |  |  | Comms | 2016-09-01 | 2016-09-01 |  | 2016-05-20 | 104 | Not started | bar: 2016-09-01
|  |  | Ensure all changes to processes and procedures are shared with trust staff and key stakeholders |  |  | Comms | 2016-09-01 | 2017-04-01 |  | 2016-05-20 | 316 | Not started | bar: 2016-09-01 to 2017-01-01
|  |  | Support the production of trust branded and standardised materials by provider |  |  | Comms | 2016-09-01 | 2017-04-01 |  | 2016-05-20 | 316 | Not started | bar: 2016-09-01 to 2017-01-01
Recruitment
|  |  | Induct and train new staff on system |  |  | RMC | 2016-01-18 | 2016-01-25 |  | 2016-05-20 | -116 | In progress | [17 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Create communications plan for TRAC |  |  | Comms | 2016-05-01 | 2016-05-31 |  | 2016-05-20 | 11 | Not Started | [121 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-05-31
|  |  | Link TRAC to the standardised recruitment approach to support staff recruitment website/events/social media) |  | STANDARDRECRUITMENT | Comms | 2016-05-01 | 2016-05-31 |  | 2016-05-20 | 11 | Not Started | [121 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-05-31
MDT Occupational Health
|  |  | Provide ongoing communications support as programme develops |  |  | Comms | 2015-04-01 | 2017-01-01 |  | 2016-05-20 | 226 | Not Started |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2017-01-01
Estates optimisation and outsourcing
|  |  | Provide ongoing communications support as programme develops |  |  | Comms | 2015-04-01 | 2017-01-01 |  | 2016-05-20 | 226 | Not Started |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2017-01-01
Procurement
CIPs already identified and included in the Procurement tracker which are due to commence in 16/17 (£2.8m)
New 'ordinary course' CIPs - better prices on existing products, substitution for cheaper products, better ways of working; to include increased collaboration with SWL APs and other trusts.
Improved consumption management (behavioural change) on key categories of spend (e.g. legal services, translation);
Permanent inventory reduction;
Reduced use of consignment stocks, which typically carry inflated mark-ups (20-40%).
|  |  | Create quick guide to procurement policy |  |  | Comms | 2016-02-01 | 2016-02-11 |  | 2016-05-20 | -99 | Complete | [31 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Send pot that to all budget holders and Agresso requisitioners by email |  |  | Comms | 2016-02-01 | 2016-02-11 |  | 2016-05-20 | -99 | Complete | [31 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Send this to email distribution lists – HoNs, matrons & consultants etc. |  |  | Comms | 2016-02-01 | 2016-02-11 |  | 2016-05-20 | -99 | Complete | [31 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | IT Trainers to provide hand-outs out at the end of Agresso training sessions |  |  | Comms & IT | 2016-02-01 | 2016-02-11 |  | 2016-05-20 | -99 | In progress | [31 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Will include in EG for 4 weeks with a contact for questions and support |  |  | Comms | 2016-02-01 | 2016-03-31 |  | 2016-05-20 | -50 | In progress | [31 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Sara and team to attend key group meetings to present pot and Q&A (I'm sending Sara as list of these today) |  |  | Procurement | 2016-02-01 | 2016-04-01 |  | 2016-05-20 | -49 | In progress | [31 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | James Frain is scheduled to attend April Snr Leaders. |  |  | JF | 2016-02-01 | 2016-04-02 |  | 2016-05-20 | -48 | In progress | [31 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Will include a link to the homepage on the intranet for 4 weeks to raise profile. |  |  | Comms | 2016-02-01 | 2016-04-01 |  | 2016-05-20 | -49 | In progress | [31 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Provide dedicated support to procurement team to improve internal communications with staff communicate |  |  | Comms | 2016-02-01 | 2016-02-28 |  | 2016-05-20 | -82 | Not Started | [31 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Provide dedicated support to procurement team to support communicating with staff the changes to procurement processes |  |  | Comms | 2016-02-01 | 2016-02-28 |  | 2016-05-20 | -82 | Not Started | [31 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
1
INFRASTRUTURE | [12 empty] | 1
|  | Asset Disposal | [10 empty] | 1
|  | Project 1 Maybury Street Car Par Development | [7 empty] | 2016-05-20 |  |  | 1
|  |  | Staff consultation |  |  | Comms | 2016-05-01 | 2016-05-31 |  | 2016-05-20 | 11 | Not Started | [121 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-05-31
| A.12 |  | Pre application public consultation/local wards, Councillors etc. - Scale model and open days |  |  |  | 2016-05-15 | 2016-08-31 |  | 2016-05-20 | 103 | Not Started | [135 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-08-31
|  |  | Media Management |  |  | Comms | 2016-05-01 | 2016-08-31 |  | 2016-05-20 | 103 | Not Started | [121 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-08-31
|  |  | Develop media strategy and plan - |  |  | Comms | 2016-04-01 | 2016-04-30 |  | 2016-05-20 | -20 | Not Started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Engage with Press and local MP |  |  | Comms | 2106-05-15 | 2016-08-31 |  | 2016-05-20 | 103 | Not Started
| A.16 |  | 28 day consultation period - second out consultations, Planning Newsletter, undertake publicity if valid submissions |  |  | Comms | 2016-07-18 | 2016-07-19 |  | 2016-05-20 | 60 | Not Started | bar: 2016-07-18 to 2016-07-19
| A.18 |  | Consultation |  |  | HR | 2016-07-18 | 2016-09-09 |  | 2016-05-20 | 112 | Not Started | bar: 2016-07-18 to 2016-09-09
|  |  | Community involvement |  |  | Comms | 2016-07-15 | 2017-01-31 |  | 2016-05-20 | 256 | Not Started | bar: 2016-07-15 to 2017-01-01
|  |  | Local communicate and public meetings |  |  | Comms | 2016-07-15 | 2017-01-31 |  | 2016-05-20 | 256 | Not Started | bar: 2016-07-15 to 2017-01-01
|  |  | Q&A development |  |  | Comms | 2016-05-15 | 2016-05-31 |  | 2016-05-20 | 11 | Not Started | [135 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-05-31
|  |  | External website content development |  |  | Comms | 2016-05-15 | 2016-05-31 |  | 2016-05-20 | 11 | Not Started | [135 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-05-31
|  |  | Microsite/internal website content |  |  | Comms | 2016-05-15 | 2016-05-31 |  | 2016-05-20 | 11 | Not Started | [135 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-05-31
|  |  | Formal Engagement and consultation process |  |  | Comms | 2016-05-15 | 2017-01-31 |  | 2016-05-20 | 256 | Not Started | [135 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2017-01-01
|  |  | Decision notice issued |  |  |  | 2016-05-08 | 2016-05-09 |  | 2016-05-20 | -11 | Not Started | [128 empty] | 1 | 1
Project 2 Maybury Disposal
|  |  | Provide ongoing communications support as programme develops |  |  | Comms | 2015-04-01 | 2018-01-01 |  | 2016-05-20 | 591 | Not Started |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2017-01-01
Project 3: Community
|  |  | Provide ongoing communications support as programme develops |  |  | Comms | 2015-04-01 | 2018-01-01 |  | 2016-05-20 | 591 | Not Started |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2017-01-01
Project 4: Rest of main site
|  |  | Provide ongoing communications support as programme develops |  |  | Comms | 2016-04-01 | 2018-01-01 |  | 2016-05-20 | 591 | Not Started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2017-01-01
Infrastructure
Project 1: Soft FM Renegotiation work stream
|  |  | Provide ongoing communications support as programme develops |  |  | Comms | 2016-04-01 | 2018-01-01 |  | 2016-05-20 | 591 | Not Started
Project 2: Hard FM re-tender
|  |  | Provide ongoing communications support as programme develops |  |  | comms | 2016-04-01 | 2018-01-01 |  | 2016-05-20 | 591 | Not Started
Project 3: Run rate sticking
|  |  | Provide ongoing communications support as programme develops |  |  | Comms | 2016-04-01 | 2018-01-01 |  | 2016-05-20 | 591 | Not Started
Project 4: Review of Medical Equipment Leases and Maintenance Contracts
|  |  | Provide ongoing communications support as programme develops |  |  | Comms | 2016-04-01 | 2018-01-01 |  | 2016-05-20 | 591 | Not Started
Project 5: Commercial Retail
|  |  | Provide ongoing communications support as programme develops |  |  | Comms | 2016-04-01 | 2018-01-01 |  | 2016-05-20 | 591 | Not Started
MEDICINE OPTIMISATION
|  |  | Obtain copy of milestone plan for project (not supplied with DIP) |  |  | Comms | 2016-04-01 | 2016-04-15 |  |  |  | Not Started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Provide ongoing communications support as programme develops |  |  | Comms | 2016-04-01 | 2016-12-31 |  |  |  | Not Started | [91 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2016-05-29 to 2016-12-31

## Communications Channels
Communications Channels, Measurement and Anaylics
Digital Channels | Frequency | Method | Degree pf embedding change | Staff | Members | Commissioners | Influencers | Patients | Health partners | Public
Intranet | BAU | Informational | Awareness
Corporate website | Daily/Weekly updates | Informational | Awareness
Social media | BAU | Informational | Awareness
Twitter | BAU | Informational | Awareness
Facebook | BAU | Informational | Awareness
Plasma screens | Updated monthly or as required | Informational | Awareness
Screen savers | Can not update | Informational | Awareness
Corporate staff email messages | Ad-hoc | Informational/persuasive | Buy-in
eG, electronic newsletter | Weekly | Informational/persuasive | Understanding
By George (Digital version) | Bi-monthly | Informational/persuasive | Understanding
Text messaging | Ad-hoc | Informational | Awareness
Corporate F2F Meeting
Senior leaders breifing | Monthly | Dialogue Strategy | Buy-in
Ask Miles | Monthly | Informational/persuasive | Understanding
Chief Nurse Surgery | Bi-weekly | Dialogue Strategy | Buy-in
Consultants meeting | Monthly | Dialogue Strategy | Buy-in
All staff drop-in sessions | Ad-hoc | Informational/persuasive | Buy-in
Team brief | Monthly | Dialogue Strategy | Buy-in
Media Channels
Video | Ad-hoc |  |  | X | X | X | X | X | X
Plasma screens | Monthly |  |  | X | X | X | X | X | X
Print Channels (Also digitally produced)
The bi-annual gazette | Bi-annual | informational/persuasive | Understanding | X | X | X | X | X | X
By George | Bi-monthly | informational/persuasive | Understanding
GP quarterly newsletter | Quarterly | informational/persuasive | Understanding
Case studies
Patient stories and case studies |  |  |  | X | X | X | X | X | X
Staff stories and case studies
Surveys and consultations
Consultation and summary consultation documents |  |  |  | X | X | X | X | X | X
LIA
Staff FFT Survey
Patient experience and involvement team surveys
Internal Meetings and Events |  |  |  | X
Display
Front of house banner displays
Public roadshows
Street campaign
Corporate meetings |  |  |  | X
External Meetings and Events
Healthwatch/LINks to get responses from local community groups | [8 empty] | X
Members | [8 empty] | X
Governors | [8 empty] | X
Health and social care Overview and Scrutiny Committee (OSC) meetings | [8 empty] | X
Healthwatch/LINks meetings | [8 empty] | X
One-to-one briefings One-to-one briefings with high power stakeholders like MPs from Wandsworth, Merton, Lambeth and Sutton. | [8 empty] | X
Direct Communications
Campaigns
Meetings, letters, emails and telephone conversations
Press and Media
Local |  |  |  | X | X | X | X | X | X
Regional |  |  |  | X | X | X | X | X | X
National |  |  |  | X | X | X | X | X | X

## Internal Stakeholder Analysis
KEY (Type)
|  |  |  | Commitment/delivery |  | Dialogue & collaboration |  | Key players
|  |  |  | Involvement |  | Dialogue |  | Keep informed
| 2016/17 Programme - Communications Internal Stakeholder Analysis |  |  | Understanding |  | Informational/persuasive |  | Keep interested
| Project Name: All projects |  |  | Awareness |  | Informational
|  | Nursing and midwifery | Consultants and medical | Junior Drs | AHP’s | Management Band 7+ | Non Clinical | Band 2-6
PROGRAMME - WORKFORCE EFFECIENCY
Reducing Average unit cost pay - non-nursing and midwifery
Project 1 : Salary Sacrifice
Project 2 : Apprentices
Project 3: Non nursing Agency Reductions
Project 4: Local CEAs
Project 5: Payroll review
Nursing Establishment Review Phase 2 workstream
Phase 2 Nursing Bands 8+ senior nurses
Project 1: Day case Ward Establishment Review
Project 2: DDNG/ HoN / Matrons NER Phase 2
Project 3: Cancer CNS NER Phase 2
Project 4: CNS NER Phase 2
Project 5: PE and Clinical Teachers NER Phase 2
Project 6: Nurse / Midwives Consultants NER Phase 2
Project 7: Research Nurse NER Phase 2
Project 8: Bed Managers NER Phase 2
Project 9: Infection Control Nurses NER Phase 2
Project 10: Midwives NER Phase 2
Project 11: AHP Establishment Review
Reducing Average unit cost pay - Nursing and midwifery
Project 1 Agency Caps
Project 2 Overseas recruitment
Project 3 Management of E rostering
Project 4 Mental Health Project
Project 5 Direct entry student Nurses
Project 6 Rotational Posts
Project 7 Community Liaison
Project 8 Professional Identity
Clinical administration
Consultant Job Planning
Safe Staffing
Hard to recruit Medics
Medical rostering software
Spans & Layers
South West London Bank
Project 1 SWL
Project 2: Implementation of rostering recommendations
Project 3: Changes to workforce information
Project 4 Increase SGH Pure Bank
Medical workforce review
Project 1: Planning / Preparation
Project 2: Activity Data Book Development
Project 3: Communication
Project 4: Care Group Review (meetings 1 -3 databook validation)
Project 5: Job Planning Analysis and Outcome
Project 6: Junior Doctor Rota Review
Project 7: Rota Rollout
CLINCAL TRANSFORMATION
Theatres Productivity
Diagnostics
Patient Flow Programme
Outpatients
PORTFOLIO OPTIMISATION
Fix, close, transfer
COMMERCIAL
Neurosurgery
Cardiac Surgery
Cardiology
Gibraltar Contract
BACK OFFICE MODERNISATION
Finance Restructure
Payroll options
Accounts payable
IM&T Outsourcing
Recruitment
PROCUREMENT
New 'ordinary course' CIPs - better prices on existing products, substitution for cheaper products, better ways of working; to include increased collaboration with SWL APs and other trusts.
Improved consumption management (behavioural change) on key categories of spend (e.g. legal services, translation);
Permanent inventory reduction;
Reduced use of consignment stocks, which typically carry inflated mark-ups (20-40%).
INFRASTRUTURE
Asset Disposal
Project 1 Maybury Street Car Par Development
Project 2 Maybury Disposal
Project 3: Community
Project 4: Rest of main site
Infrastructure
Project 1: Soft FM Renegotiation work stream
Project 2: Hard FM re-tender
Project 3: Run rate sticking
Project 4: Review of Medical Equipment Leases and Maintenance Contracts
Project 5: Commercial Retail
MEDICINE OPTIMISATION

## External Stakeholder Analysis
| 2016/17 Programme - Communications External Stakeholder Review |  | KEY (Type)
| Project Name: All projects |  |  | Engage closely and influence activity |  | Commitment/accountability
|  |  |  | Keep informed |  | Involvement
|  |  |  | Keep satisfied |  | Understanding
|  |  |  | Monitor (low activity) |  | Awareness
PROGRAMME - WORKFORCE EFFECIENCY |  | GP | CCG | NHSE | Acute | Partner | Union | Patient | Public
Reducing Average unit cost pay - non-nursing and midwifery
Project 1 : Salary Sacrifice
Project 2 : Apprentices
Project 3: Non nursing Agency Reductions
Project 4: Local CEAs
Project 5: Payroll review
Nursing Establishment Review Phase 2 workstream
Nursing Establishment Review - Phase 2 Nursing Bands 8+ senior nurses
Project 1: Day case Ward Establishment Review
Project 2: DDNG/ HoN / Matrons NER Phase 2
Project 3: Cancer CNS NER Phase 2
Project 4: CNS NER Phase 2
Project 5: PE and Clinical Teachers NER Phase 2
Project 6: Nurse / Midwives Consultants NER Phase 2
Project 7: Research Nurse NER Phase 2
Project 8: Bed Managers NER Phase 2
Project 9: Infection Control Nurses NER Phase 2
Project 10: Midwives NER Phase 2
Project 11: AHP Establishment Review
Reducing Average unit cost pay - Nursing and midwifery
Project 1 Agency Caps
Project 2 Overseas recruitment
Project 3 Management of E rostering
Project 4 Mental Health Project
Project 5 Direct entry student Nurses
Project 6 Rotational Posts
Project 7 Community Liaison
Project 8 Professional Identity
Clinical administration
Consultant Job Planning
Safe Staffing
Hard to recruit Medics
Medical rostering software
Spans & Layers
South West London Bank
Project 1 SWL
Project 2: Implementation of rostering recommendations
Project 3: Changes to workforce information
Project 4 Increase SGH Pure Bank
Medical workforce review
Project 1: Planning / Preparation
Project 2: Activity Data Book Development
Project 3: Communication
Project 4: Care Group Review (meetings 1 -3 databook validation)
Project 5: Job Planning Analysis and Outcome
Project 6: Junior Doctor Rota Review
Project 7: Rota Rollout
CLINCAL TRANSFORMATION
Theatres Productivity
Diagnostics
Patient Flow Programme
Outpatients
PORTFOLIO OPTIMISATION
Fix, close, transfer
COMMERCIAL
Neurosurgery
Cardiac Surgery
Cardiology
Gibraltar Contract
BACK OFFICE MODERNISATION
Finance Restructure
Payroll options
Accounts payable
IM&T Outsourcing
Recruitment
PROCUREMENT | Procurement
INFRASTRUTURE
Asset Disposal
Project 1 Maybury Street Car Par Development
Project 2 Maybury Disposal
Project 3: Community
Project 4: Rest of main site
Infrastructure
Project 1: Soft FM Renegotiation work stream
Project 2: Hard FM re-tender
Project 3: Run rate sticking
Project 4: Review of Medical Equipment Leases and Maintenance Contracts
Project 5: Commercial Retail
MEDICINE OPTIMISATION

## Priorties and Objectives Plan (hidden)
April
All staff message from the Chairman - First reflections & key priorities | awareness
eG - Chairman - First reflections & key priorities | awareness
eG - Director of Estates - First reflections & key priorities | awareness
Intranet - Home page banner with link to message from chairman | awareness
Core brief - Topics to include to how we are addressing the current priorities, CQC inspection and £17m performance based gov funding & Transformation | understanding
Ask Miles - Advertised as an opportunity to present/discuss current priorities and to openly address the concerns and anxieties | understanding
Consultants meeting - Medical Director, Director of Estates & CIO , CCIO to present current priorities at Consultants meeting | buy-in
NEW Back to the floor - Board and execs to join at least one ‘taking the chief nurse surgery back to the floor’ visits (weekly visits to wards leading up to CQC inspection) | understanding
Senior Leaders Briefing & Chief Nurse Surgery - Director of Estates, CIO & CCIO to present current priorities | understanding
May
All staff message CEO – 2016/17priortites with story /narrative developed through the board | awareness
eG - 2016/17priortites /narrative developed through the board – feature on one of the six corporate objectives | awareness
Intranet - Strategy section created on exiting intranet | awareness
Social media – Utilise to engage on corporate priorities | awareness
Core brief - May team brief to include the organisational focus for 2016/17 and progress towards priorities
NEW Campaign launches utilising on and off line media to ensure that the campaign reaches all staff within the organisation – we envisage this will include a dedicated microsite, video, posters, banners, leaflets, email and social media
NEW internal newsletters launch with an opportunity to have regular features on staff wellbeing, quality and strategy to communicate change vision
Visual metaphor for strategy map completed and disseminated around the trust
Senior Leaders Briefing /Consultants meeting Chief Nurse Surgery - CEO & Director of strategy to present organisational focus for 2016/17 and explain how the vision will be executed. Transformation director to update
Senior Leaders Briefing /Consultants meeting Chief Nurse Surgery - Director of HR to present progress towards issues identified in the 2015 staff survey (communications strategy completed)
NEW Back to the floor - Board and execs to join at least one ‘taking the chief nurse surgery back to the floor’ visits (weekly visits to wards leading up to CQC inspection)
NEW Team meetings - Board and execs to join team meetings around the trust – communications team to identify meetings to join
Back to the floor Well-being walk about by Chair and council of governors to engage with staff on current priorities
June
All staff message CEO – Recognise and reward change. Communicate short term wins. Celebrate project achievements to achieved to boost moral
NEW internal newsletters Utilise voice of the professions and change leaders who will be the conduit for the vision
NEW internal newsletters dedicated strategy sections Communicate short term wins. Celebrate project achievements to achieved to boost morale
Social media – Utilise to engage on corporate priorities
Core brief - core brief to update on the organisational focus for 2016/17 and progress towards priorities and opportunity for thoughts on corporate objectives
Ask Miles - Advertised as an opportunity to discuss organisational focus for 2016/17
Campaign continues Board and execs to attend front of house stands
NEW Visual metaphor for strategy map completed and disseminated around the trust
Transformation communications to individual stakeholders continue
NEW 6 corporate objectives are bough to life and communicated via all internal channels
Senior Leaders Briefing /Consultants meeting Chief Nurse Surgery - CEO & Director of strategy to present – Are we on track? Communicate short term wins. Celebrate project achievements to achieved to boost morale
Senior Leaders Briefing /Consultants meeting Chief Nurse Surgery - CEO & Director of strategy to present – Are we on track? Communicate short term wins. Celebrate project achievements to achieved to boost morale
NEW Show and Tell day – Hyde Park Room – All board to attend. Visuals and posters banners etc to describe the trust objectives. Creative methods to engage staff vision. Ideally before CQC visit
NEW Back to the floor - Board and execs to join at least one ‘taking the chief nurse surgery back to the floor’ visits (weekly visits to wards leading up to CQC inspection
NEW transformation and awards launch
Back to the floor Well-being walk about by Chair and council of governors post CQC inspection
NEW Team meetings - Board and execs to join team meetings around the trust – communications team to identify meetings to join
July
All staff message & EG Chair to reflect upon first 3 months at the trust
All staff message & eG Director of Estates 3 months in posts how we have addressed the current priorities
New internal newsletters Utilise voice of the professions and change leaders who will be the conduit for the vision
New internal newsletters dedicated strategy sections Communicate short term wins. Celebrate project achievements to achieved to boost morale
Social media – Utilise to engage on corporate priorities
Core brief - June brief to include to the organisational focus for 2016/17 - transformation - progress towards priorities and opportunity for thoughts on corporate objectives
Campaign continues Microsite and digital resources updated to reflect current position
Transformation communications to individual stakeholders continues
NEW intranet launches
AMM
6 corporate objectives are bough to life and communicated via all internal channels
Senior Leaders Briefing /Consultants meeting Chief Nurse Surgery - CEO & Director of strategy to present – Are we on track? Communicate short term wins. Celebrate project achievements to achieved to boost morale
Senior Leaders Briefing /Consultants meeting Chief Nurse Surgery - CEO & Director of strategy to present – Are we on track? Communicate short term wins. Celebrate project achievements to achieved to boost morale
Team meetings - Board and execs to join team meetings around the trust – communications team to identify meetings to join
Future of St George’s – Big Conversation in mid July – are we on the right track and sense checking