## Sheet5
Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Date Site Ready To Start | Date of First Patient Recruited | Benchmark Met | Reasons for delay correspond to: | Comments
16/LO/1322 | 208946 | A Study to Evaluate the Efficacy of Maternal Immunization with RSV F Vaccine in Preventing RSV Lower Respiratory Tract Infection in Young Infants | 2016-05-24 | 2016-08-15 | 2016-09-09 | 2016-09-29 | 2016-09-30 | 2016-09-30 |  | No | Sponsor | Patients can only be recruited in RSV season for this study. Set-up delayed by sponsor and regulatory approvals which meant the study team only had eight days to recruit a patient which proved to be impossible
16/EE/0243 | 207331 | A 6-month, multicenter, phase 3, open-label extension safety study of OTO-104 given at 3-month intervals by intratympanic injection in subjects with unilateral Meniere's disease. | 2016-08-22 | 2016-09-22 | 2016-08-01 | 2017-11-01 | 2016-11-07 | 2016-11-10 | 2016-12-07 | No | NHS Provider | Complex study that took a while (5 weeks) for costings accountant to sort out and negotiate with the research team and the sponsor.
16/LO/0878 | 201070 | Prospective, multi-center study to evaluate the everlinQ endoAVF System when used to create an endovascular arteriovenous fistula (endoAVF) for patients who require vascular access for hemodialysis | 2015-12-21 | 2016-09-16 | 2016-09-16 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2017-02-02 | No | NHS Provider | The PI left after the study was approved so a new PI needed to be appointed. New PI was identified in Dec 2016 and first patient recruited in Feb 2017
16/SC/0416 | 210405 | A Phase 2b Randomised, Double-blind, Placebo-controlled Study to Evaluate the Safety and Efficacy of MEDI8897, a Monoclonal Antibody With an Extended Half-life Against Respiratory Syncytial Virus, in Healthy Preterm Infants | 2016-08-10 | 2016-10-25 | 2016-09-30 | 2016-10-26 | 2016-10-27 | 2016-11-22 | 2016-12-09 | Yes | NA | Target met
16/NE/0147 | 204478 | A Multicenter, Randomized, Double-Blind, Placebo-Controlled Phase III Study to Evaluate the Efficacy and Safety of Elafibranor in Patients with Nonalcoholic Steatohepatitis (NASH) and fibrosis | 2016-07-30 | 2016-07-30 | 2016-06-15 | 2016-10-13 | 2016-10-17 | 2016-11-08 |  | No | Both | Costing negotiations between sponsor and site caused delay to set-up
16/LO/0886 | 204525 | A Multicenter, Double-Blind, Placebo-Controlled, Randomized, Parallel-Group, Dose-Ranging Study to Evaluate the Safety and Efficacy of Intravenous Natalizumab (BG00002) in Acute Ischemic Stroke | 2016-04-29 | 2016-09-26 | 2016-09-26 | 2016-10-11 | 2016-10-11 | 2016-10-14 | 2017-05-22 | No | NHS Provider | Sudden and very early start of maternity leave of senior member in the Stroke research team affected recruitment to all new Stroke studies at the start of 2017. In addition, this is a difficult study to recruit to with a low recruitment target
16/WM/0317 | 206807 | Randomised Efficacy and Safety Trial with Oral S44819 after Recent ischemic cerebral Event. International, multicentre, randomised, double-blind placebo controlled phase II study. | 2016-08-12 | 2016-10-07 | 2016-10-07 | 2016-11-30 | 2016-11-30 | 2016-12-22 | 2017-03-06 | No | NHS Provider | Delays with set-up due to staff shortages in R&D office. In addition, sudden and very early start of maternity leave of senior member in the Stroke research team affected recruitment to all new Stroke studies at the start of 2017. In addition, this is a difficult study to recruit to with a low recruitment target
16/WS/0068 | 199202 | Quantitative Fibronectin to help Decision-making in women with Symptoms of Preterm Labour - QUIDS | 2016-08-12 | 2016-08-12 | 2016-07-13 | 2016-11-09 | 2016-11-16 | 2016-11-17 | 2016-12-02 | No | NHS Provider | Delay with contract sign-off due to staff shortages in R&D office. Research team recruited first patients within 30 days of site confirmed
17/LO/0182 | 213821 | A Prospective, Randomized, Multicenter Controlled Trial of CERAMENT?G as Part of Surgical Repair of Open Diaphyseal Tibial Fractures. | 2017-01-18 | 2017-03-31 | 2017-03-30 | 2017-07-06 | 2017-07-10 | 2017-07-13 |  | No | Both | Study delayed by trust's credit check procedures with sponsor, contract could not be signed until credit check came through. In addition, CTA insurance limit was too low.
16/LO/0585 | 188869 | Phase II Randomised, Double Blind, Placebo Controlled Trial of Neoadjuvant Artesunate in Stage II/III Colorectal Cancer (NeoART trial) | 2016-03-17 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-10-03 | 2016-10-03 | 2017-04-28 | No | Sponsor | Study recruitment was halted by the sponsor due to funding arrangements from Nov 2016 - Jan 2017. The research team then had a number of patients with inconclusive biopsies so they were not approached. The sponsor is submitting a protocol amendment to include some patients with inconclusive biopsies.
16/LO/0831 | 196728 | Efficacy, safety and impact on antimicrobial resistance of duration and dose of antibiotic treatment for children with Community-Acquired Pneumonia (CAP): a randomIsed controlled Trial | 2016-07-18 | 2016-11-11 | 2016-11-11 | 2017-01-19 | 2017-02-01 | 2017-02-01 | 2017-04-12 | No | NHS Provider | Delay in issuing capacity and capability due to delays with pharmacy approval as pharmacy was not notified of study during initial discussions so this delayed the set-up of the study.
16/NE/0415 | 217915 | A Phase 2a, Open-Label Study to Evaluate the Safety, Pharmacokinetics and Efficacy of the Combination of AL-335 and Odalasvir, with or without Simeprevir, in Treatment-Na?ve Subjects with Genotype 1, 2 or 3 Chronic Hepatitis C infection with or without compensated Child Pugh A Cirrhosis | 2016-07-28 | 2016-12-13 | 2017-02-28 | 2017-01-11 | 2017-03-28 | 2017-07-03 |  | No | Both | Delays with set-up and confirmation caused by delays with getting support from cardiology to perform a specialised test required in protocol. There were then further delays from sponsor to activate site, site was only activated 03/07/2017 and research team is now actively screening for patients.
16/LO/1355 | 168344 | InPACT trial- International Penile Advanced Cancer Trial (International Rare Cancers Initiative study) | 2015-10-12 | 2016-10-21 | 2016-10-11 | 2017-03-27 | 2017-03-30 | 2017-05-12 |  | No | Sponsor | Complex contract negotiations and Service level agreement between ourselves and the sponsor. After site confirmation, the sponsor only opened the site to recruitment on 12/05/2017. No patients recruited yet as this is a rare patient population and one potential patient declined to participate.
16/SC/0462 | 208830 | DRAFFT 2 ? Distal Radius Fracture Fixation Trial 2 | 2016-11-04 | 2016-12-09 | 2016-11-11 | 2017-02-08 | 2017-02-09 | 2017-03-02 |  | No | NHS Provider | Set-up delayed by approval from the CRF to support trial. After confirmation, the team had one screen failure and identified 2 more patients but due to staff and theatre availability, these patients could not be recruited.
16/LO/2153 | 217054 | A Randomised, Double-blind Placebo Controlled Trial Comparing the Effect of Intravenous Ferric Carboxymaltose on Hospitalisations and Mortality in Iron Deficient Patients Admitted for Acute Heart Failure (Affirm-AHF) | 2016-10-27 | 2017-02-28 | 2017-02-09 | 2017-03-06 | 2017-03-09 | 2017-03-23 | 2017-04-10 | Yes | NA | Target met
16/LO/0879 | 200503 | Response guided therapy with sofosbuvir and velpatasvir for 12 or 24 weeks in patients with genotype 3 chronic hepatitis C virus: is longer therapy worthwhile? | 2017-01-16 | 2017-01-31 | 371442 | 2017-01-31 | 2017-02-21 | 2017-05-22 | 2017-05-25 | No | Sponsor | Sponsor did not schedule SIV until 18th May, site was activated 22nd May and first patient was recruited on 24th of May 2017.
16/WM/0215 | 203334 | An Assessment of Humacyte's Human Acellular Vessel in Patients Needing Renal Replacement Therapy: A comparison with ePTFE grafts as conduits for Hemodialysis | 2016-07-19 | 2017-01-20 | 2016-07-19 | 2017-03-19 | 2017-04-06 | 2017-04-06 |  | No | NHS Provider | Original PI left so new PI had to be identified .Pharmacy approval then delayed as the protocol and pharmacy procedures are quite complex. Study since closed to recruitment as site failed to recruit any patients, this is due to changes in the transplant services at the hospital
16/SC/0391 | 208610 | A randomized, double-blind, double-dummy, parallel-group study comparing the efficacy and safety of ofatumumab versus teriflunomide in patients with relapsing multiple sclerosis. | 2016-07-20 | 2016-07-26 | 2016-10-13 | 2017-02-16 | 2017-02-21 |  | 2017-07-18 | No | Both | This is a very complicated CTIMP trial. Set-up was delayed as the costings process took several months to sort out with the different support departments in the trust. There were then further delays with the activation of the site by the sponsor as there were issues with the IMP supply
16/EM/0324 | 204032 | A Phase III Randomized, Placebo-Controlled Clinical Trial to Study the Safety and Efficacy of Suvorexant (MK-4305) for the Treatment of Insomnia in Subjects with Alzheimer?s Disease | 2016-07-11 | 2016-10-21 | 2016-12-28 | 2017-03-15 | 2017-03-17 | 2017-03-17 |  | No | NHS Provider | Prolonged costing and contract negotiations between site, sponsor and research team. After confirmation of capacity and capability, the research team has not been able to recruit a patient as they are struggling to find patients who meet the inclusion criteria required to enter the study.
16/LO/1810 | 209789 | A Phase 3, Randomized Study to Assess the Efficacy and Safety of Ublituximab in Combination with TGR-1202 Compared to Obinutuzumab in Combination with Chlorambucil in Patients with Chronic Lymphocytic Leukemia (CLL) | 2016-10-24 | 2016-10-24 | 2017-01-03 | 2017-01-31 | 2017-02-01 |  | 2017-02-03 | No | NHS Provider | Due to staffing issues, research team and costing team were not able to schedule a meeting for 6 weeks after the date site selected to discuss costings. The sponsor then changed the costing templates considerably requiring more negotiation.
16/LO/1784 | 211244 | MODULATE / IMM-101 in patients with metastatic cancer or unresectable cancer | 2016-09-13 | 2016-10-31 | 2016-12-13 | 2017-05-03 | 2017-05-11 |  | 2017-05-31 | No | NHS Provider | Costings process at site delayed set-up process. Costings accountant negotiated costs with the research team and a number of service departments including pathology, radiology, Clinical Research Facility, pharmacy and microsatellite phenotyping and this took nearly 6 months.
17/LO/0089 | 219229 | A Phase 2, Multicenter, Open-Label Study to Evaluate the Efficacy and Safety of Sofosbuvir/Velpatasvir for 12 Weeks in Subjects with Chronic HCV Infection Who are on Dialysis for End Stage Renal Disease | 2016-11-07 | 2017-01-27 | 2017-03-27 | 2017-04-11 | 2017-04-24 | 2017-05-08 |  | No | NHS Provider | Delays with obtaining radiology approval which delayed set-up of study. Site was then activated by sponsor 08/05/2017. We have recently screened 1 patient (on 13th July).
17/LO/0082 | 217324 | PuraStat; Post Market Performance during Vascular Surgery | 2017-03-13 | 2017-03-13 | 2017-03-15 | 2017-04-21 | 2017-04-28 | 2017-05-02 | 2017-06-14 | No | Neither | The main reason for missing the target was that the research team did not see any eligible patients within the first 5 weeks of activation. Negotiating contract with sponsor also caused slight delays in set-up.
15/NE/0415 | 189037 | A Phase III, randomized, double-blind, controlled, multicenter study of intravenous PI3K inhibitor copanlisib in combination with standard immunochemotherapy versus standard immunochemotherapy in patients with relapsed indolent non-Hodgkin?s lymphoma (iNHL) - CHRONOS-4 | 2016-09-09 | 2017-03-20 | 2017-01-20 | 2017-06-08 | 2017-06-12 | 2017-06-14 | 2017-06-15 | No | NHS Provider | Costing process delayed by site; support service approvals from cellular pathology and radiology took 2 months to come through.
17/YH/0116 | 225662 | Efficacy and safety of semaglutide 1.0 mg once-weekly versusliraglutide 1.2 mg once-daily as add-on to 1-3 oral antidiabeticdrugs (OADs) in subjects with type 2 diabetes | 2017-04-04 | 2017-04-27 | 2017-05-24 | 2017-06-15 | 2017-06-19 |  | 2017-06-27 | Yes | NA | Set-up delayed because of issues with service level agreement with Moorfields hospital but 70 day target met. First patient recruited 27/06/2017 and randomised on 10/07/2017
17/NW/0175 | 222859 | Phase 1b Open-Label, Dose Escalation Study of PRTX-100 in Adult Patients with Persistent/Chronic Immune Thrombocytopenia | 2017-03-07 | 2017-05-19 | 2017-05-19 | 2017-06-01 | 2017-07-06 |  |  | Within 70 Days |  | Set-up delayed by trust's credit check procedures, study is still within 70 day target
17/SC/0164 | 210735 | Early cryoprecipitate in major trauma haemorrhage: CRYOSTAT-2 | 2017-04-20 | 2017-06-08 | 2017-05-26 | 2017-07-05 | 2017-07-05 |  |  | Within 70 Days |  | Still within 70 days
16/SC/0604 | 214032 | A PHASE 3 MULTICENTER, RANDOMIZED, DOUBLE-BLIND, EXTENSION STUDY TO EVALUATE THE SAFETY OF DAILY ORAL DOSING OF TAFAMIDIS MEGLUMINE (PF-06291826) 20 MG OR 80 MG IN SUBJECTS DIAGNOSED WITH TRANSTHYRETIN CARDIOMYOPATHY (TTR-CM) | 2017-01-06 | 2017-06-30 | 2017-04-11 | 2017-06-30 | 2017-06-30 |  |  | Within 70 Days |  | Full validated document set only received 30/06/2017. This is ongoing from the ATTR-ACT study which is in follow up currently. There will be no new recruitment to the extension trial as it is only eligible to patients who complete 30 months of follow up under the existing trial. We have one remaining patient who will reach M30 in Dec 2017 which will be the very earliest that we can include a patient in the extension trial.
17/SW/0127 | 225959 | Flight-A multicentre randomised trial of First Line treatment pathways for newly diagnosed Immune Thrombocytopenia: Standard steroid treatment versus combined steroid and mycophenolate | 2016-11-07: 2017-06-19; 2017-01-27: 2017-06-19; 2017-03-27: 2017-07-03 |  | Within 70 Days |  | Study still in set-up and within 70 day timeline
16/EE/0358 | 212839 | Non CF Bronchiastasis-3636/0001 Queen's University Belfast | 2016-11-15 | 2016-12-14 | 2016-12-13 | 2017-02-17 | 2017-02-22 |  |  | No | NHS Provider | Delay in getting approval/support from the Clinical Research Facility. The research team has also struggled to recruit patients and there has been 14 screening failures since the site opened to recruitment
16/SS/0137 | 199347 | Alteplase-Tenecteplase Trial Evaluation for Stroke Thrombolysis (ATTEST 2) | 2016-11-07: 2017-01-26; 2017-01-27: 2017-04-12; 2017-03-27: 2017-02-10 |  | No | NHS Provider | Delays with setting up study because of staff shortages in the R&D office.
16/LO/1502 | 178292 | CTC-STOP: Utilising Circulating Tumor Cell (CTC) Counts to Optimise Systemic Therapy of Metastatic Prostate Cancer. | 2016-11-07: 2017-04-06; 2017-01-27: 2017-04-07; 2017-03-27: 2016-10-07 |  | No | NHS Provider | Ongoing delays with costings and contracts - study still in set-up
17/LO/0347 | 221524 | A Phase III Randomized, Double-blind Study to Evaluate Pembrolizumab plus Chemotherapy vs Placebo plus Chemotherapy as Neoadjuvant Therapy and Pembrolizumab vs Placebo as Adjuvant Therapy for Triple Negative Breast Cancer (TNBC) | 2016-11-07: 2017-04-03; 2017-01-27: 2017-04-11; 2017-03-27: 2017-05-05 |  | No | NHS Provider | Ongoing delays with obtaining pathology and radiology approvals, study still in set-up
16/EE/0357 | 206501 | Safety and efficacy of opicapone in clinical practice in Parkinson?s disease with wearing- off motor fluctuations | 2017-04-04 | 2017-05-04 | 2016-10-31 | 2017-07-18 | 2017-07-24 |  |  | Within 70 Days |  | Set-up delayed by costings and contracts process at site
16/NW/0517 | 188554 | A phase III study to determine the role of ixazomib as an Augmented Conditioning therapy in salvage autologous stem | 2016-11-07: 2016-07-29; 2017-01-27: 2017-06-05; 2017-03-27: 2016-10-27 |  | Within 70 Days |  | Ongoing delays with costings, study still in set-up
16/NE/0312 | 187560 | A double-blind, randomized, placebo-controlled study to investigate the efficacy and safety of cannabidiol (GWP42003-P,CBD) as add-on therapy in patients with tuberous sclerosis complex who experience inadequately-controlled seizures | 2016-11-07: 2017-02-14; 2017-01-27: 2017-06-26; 2017-03-27: 2017-02-22 |  | Within 70 Days |  | Study still in set-up