## Sheet1
Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | Date of First Patient Recruited | Benchmark Met | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Date Site Ready To Start | Reasons for delay correspond to:
16/SC/0416 | 210405 | A Phase 2b Randomised, Double-blind, Placebo-controlled Study to Evaluate the Safety and Efficacy of MEDI8897, a Monoclonal Antibody With an Extended Half-life Against Respiratory Syncytial Virus, in Healthy Preterm Infants | 2016-12-09 | Yes | 2016-08-10 | 2016-10-25 | 2016-09-30 | 2016-10-26 | 2016-10-27 | 2016-11-22 | Target met
16/WM/0317 | 206807 | Randomised Efficacy and Safety Trial with Oral S44819 after Recent ischemic cerebral Event. International, multicentre, randomised, double-blind placebo controlled phase II study. | 2017-03-06 | No | 2016-08-12 | 2016-10-07 | 2016-10-07 | 2016-11-30 | 2016-11-30 | 2016-12-22 | NHS Provider
17/LO/0182 | 213821 | A Prospective, Randomized, Multicenter Controlled Trial of CERAMENT?G as Part of Surgical Repair of Open Diaphyseal Tibial Fractures. |  | No | 2017-01-18 | 2017-03-31 | 2017-03-30 | 2017-07-06 | 2017-07-10 | 2017-07-13 | Both
16/LO/0831 | 196728 | Efficacy, safety and impact on antimicrobial resistance of duration and dose of antibiotic treatment for children with Community-Acquired Pneumonia (CAP): a randomIsed controlled Trial | 2017-04-12 | No | 2016-07-18 | 2016-11-11 | 2016-11-11 | 2017-01-19 | 2017-02-01 | 2017-02-01 | NHS Provider
16/NE/0415 | 217915 | A Phase 2a, Open-Label Study to Evaluate the Safety, Pharmacokinetics and Efficacy of the Combination of AL-335 and Odalasvir, with or without Simeprevir, in Treatment-Na?ve Subjects with Genotype 1, 2 or 3 Chronic Hepatitis C infection with or without compensated Child Pugh A Cirrhosis |  | No | 2016-07-28 | 2016-12-13 | 2017-02-28 | 2017-01-11 | 2017-03-28 | 2017-07-03 | Both
16/LO/1355 | 168344 | InPACT trial- International Penile Advanced Cancer Trial (International Rare Cancers Initiative study) | 2017-08-01 | No | 2016-10-12 | 2016-10-21 | 2016-10-11 | 2017-03-27 | 2017-03-30 | 2017-05-12 | Sponsor
16/SC/0462 | 208830 | DRAFFT 2 ? Distal Radius Fracture Fixation Trial 2 |  | No | 2016-11-04 | 2016-12-09 | 2016-11-11 | 2017-02-08 | 2017-02-09 | 2017-03-02 | NHS Provider
16/LO/2153 | 217054 | A Randomised, Double-blind Placebo Controlled Trial Comparing the Effect of Intravenous Ferric Carboxymaltose on Hospitalisations and Mortality in Iron Deficient Patients Admitted for Acute Heart Failure (Affirm-AHF) | 2017-04-10 | Yes | 2016-10-27 | 2017-02-28 | 2017-02-09 | 2017-03-06 | 2017-03-09 | 2017-03-23 | Target met
16/LO/0879 | 200503 | Response guided therapy with sofosbuvir and velpatasvir for 12 or 24 weeks in patients with genotype 3 chronic hepatitis C virus: is longer therapy worthwhile? | 2017-05-25 | No | 2017-01-16 | 2017-01-31 | 2016-12-20 | 2017-01-31 | 2017-02-21 | 2017-05-22 | Sponsor
16/WM/0215 | 203334 | An Assessment of Humacyte's Human Acellular Vessel in Patients Needing Renal Replacement Therapy: A comparison with ePTFE grafts as conduits for Hemodialysis |  | No | 2016-07-19 | 2017-01-20 | 2016-07-19 | 2017-03-19 | 2017-04-06 | 2017-04-06 | NHS Provider
16/EM/0324 | 204032 | A Phase III Randomized, Placebo-Controlled Clinical Trial to Study the Safety and Efficacy of Suvorexant (MK-4305) for the Treatment of Insomnia in Subjects with Alzheimer?s Disease |  | No | 2016-07-11 | 2016-10-21 | 2016-12-28 | 2017-03-15 | 2017-03-17 | 2017-03-17 | NHS Provider
16/LO/1810 | 209789 | A Phase 3, Randomized Study to Assess the Efficacy and Safety of Ublituximab in Combination with TGR-1202 Compared to Obinutuzumab in Combination with Chlorambucil in Patients with Chronic Lymphocytic Leukemia (CLL) | 2017-02-03 | No | 2016-10-24 | 2016-10-24 | 2017-01-03 | 2017-01-31 | 2017-02-01 | 2017-02-01 | Sponsor
16/LO/1784 | 211244 | MODULATE / IMM-101 in patients with metastatic cancer or unresectable cancer | 2017-05-25 | No | 2016-09-13 | 2016-10-31 | 2016-12-13 | 2017-05-03 | 2017-05-11 |  | NHS Provider
17/LO/0089 | 219229 | A Phase 2, Multicenter, Open-Label Study to Evaluate the Efficacy and Safety of Sofosbuvir/Velpatasvir for 12 Weeks in Subjects with Chronic HCV Infection Who are on Dialysis for End Stage Renal Disease |  | No | 2016-11-07 | 2017-01-27 | 2017-03-27 | 2017-04-11 | 2017-04-24 | 2017-05-08 | NHS Provider
17/LO/0082 | 217324 | PuraStat; Post Market Performance during Vascular Surgery | 2017-06-14 | No | 2017-03-13 | 2017-03-13 | 2017-03-15 | 2017-04-21 | 2017-04-28 | 2017-05-02 | Neither
17/YH/0116 | 225662 | Efficacy and safety of semaglutide 1.0 mg once-weekly versusliraglutide 1.2 mg once-daily as add-on to 1-3 oral antidiabeticdrugs (OADs) in subjects with type 2 diabetes | 2017-06-27 | Yes | 2017-04-04 | 2017-04-27 | 2017-05-24 | 2017-06-15 | 2017-06-19 | 2017-06-19 | Please Select...
17/NW/0175 | 222859 | Phase 1b Open-Label, Dose Escalation Study of PRTX-100 in Adult Patients with Persistent/Chronic Immune Thrombocytopenia |  | No | 2017-03-07 | 2017-05-19 | 2017-05-19 | 2017-06-01 | 2017-07-06 |  | NHS Provider
17/SC/0164 | 210735 | Early cryoprecipitate in major trauma haemorrhage: CRYOSTAT-2 | 2017-08-23 | No | 2017-04-20 | 2017-06-08 | 2017-05-26 | 2017-07-05 | 2017-07-05 | 2017-07-05 | Neither
16/SC/0604 | 214032 | A PHASE 3 MULTICENTER, RANDOMIZED, DOUBLE-BLIND, EXTENSION STUDY TO EVALUATE THE SAFETY OF DAILY ORAL DOSING OF TAFAMIDIS MEGLUMINE (PF-06291826) 20 MG OR 80 MG IN SUBJECTS DIAGNOSED WITH TRANSTHYRETIN CARDIOMYOPATHY (TTR-CM) |  | No | 2017-01-06 | 2017-06-30 | 2017-04-11 | 2017-06-30 | 2017-06-30 |  | Neither
16/EE/0358 | 212839 | Non CF Bronchiastasis-3636/0001 Queen's University Belfast |  | No | 2016-11-15 | 2016-12-14 | 2016-12-13 | 2017-02-17 | 2017-02-22 |  | NHS Provider
16/SS/0137 | 199347 | Alteplase-Tenecteplase Trial Evaluation for Stroke Thrombolysis (ATTEST 2) |  | Within 70 Days | 2017-01-26 | 2017-09-06 | 2017-02-10 |  |  |  | Within 70 Days
17/LO/0347 | 221524 | A Phase III Randomized, Double-blind Study to Evaluate Pembrolizumab plus Chemotherapy vs Placebo plus Chemotherapy as Neoadjuvant Therapy and Pembrolizumab vs Placebo as Adjuvant Therapy for Triple Negative Breast Cancer (TNBC) |  | No | 2017-04-03 | 2017-06-29 | 2017-05-05 | 2017-07-25 | 2017-07-31 | 2017-07-31 | Neither
16/EE/0357 | 206501 | Safety and efficacy of opicapone in clinical practice in Parkinson?s disease with wearing- off motor fluctuations |  | No | 2017-04-04 | 2017-04-24 | 2016-10-31 | 2017-07-18 | 2017-07-28 | 2017-08-02 | NHS Provider
16/NW/0517 | 188554 | A phase III study to determine the role of ixazomib as an Augmented Conditioning therapy in salvage autologous stem |  | No | 2016-07-29 | 2017-06-21 | 2016-10-27 |  |  |  | NHS Provider
16/NE/0312 | 187560 | A double-blind, randomized, placebo-controlled study to investigate the efficacy and safety of cannabidiol (GWP42003-P,CBD) as add-on therapy in patients with tuberous sclerosis complex who experience inadequately-controlled seizures |  | Within 70 Days | 2017-02-14 | 2017-09-27 | 2017-02-22 |  |  |  | Within 70 Days
15/LO/0638 | 176799 | Paclitaxel assisted balloon Angioplasty of Venous stenosis in haEmodialysis access: The PAVE trial. A multicentre double-blind randomised controlled trial in haemodialysis patients with a stenosis in a native arteriovenous fistula. | 2017-09-14 | No | 2017-01-09 | 2017-01-09 | 2016-09-21 | 2017-02-27 | 2017-03-14 | 2017-04-12 | Both
16/SC/0596 | 214948 | CONTRACT - CONservative Treatment of Appendicitis in Children ? a randomised controlled Trial (Feasibility) | 2017-03-02 | Yes | 2016-10-26 | 2017-01-11 | 2017-01-11 | 2017-01-23 | 2017-02-09 | 2017-03-01 | Target met
16/EE/0065 | 192416 | Cholecalciferol in Patients on Dialysis - SIMPLIFIED |  | No | 2017-02-24 | 2017-02-24 | 2016-07-29 | 2017-09-11 | 2017-09-27 |  | NHS Provider
16/LO/1812 | 211705 | Safety of tenofovir alafenamide (TAF) in patients with a history of tubulopathy on tenofovir disoproxil fumarate (TDF) |  | No | 2017-03-01 | 2017-03-01 | 2016-11-28 |  |  |  | NHS Provider
16/WA/0324 | 216581 | Study of preterm infants and neurodevelopmental genes (SPRING): a pilot investigation |  | No | 2017-04-10 | 2017-04-10 | 2017-02-24 |  |  |  | NHS Provider
16/LO/2173 | 139794 | The Response To Ajmaline Provocation in Healthy Subjects |  | No | 2016-12-01 | 2017-04-24 | 2017-04-24 |  |  |  | NHS Provider
17/LO/0849 | 222165 | A Phase 3, Randomized, Double-Blind, Placebo-Controlled Study Evaluating the Safety and Efficacy of Selonsertib in Subjects with Compensated Cirrhosis due to Nonalcoholic Steatohepatitis (NASH) |  | No | 2017-05-11 | 2017-05-24 | 2017-08-02 | 2017-09-13 | 2017-09-20 |  | NHS Provider
17/LO/0848 | 222163 | A Phase 3, Randomized, Double-Blind, Placebo-Controlled Study Evaluating the Safety and Efficacy of Selonsertib in Subjects with Nonalcoholic Steatohepatitis (NASH) and Bridging (F3) Fibrosis |  | No | 2017-02-20 | 2017-05-24 | 2017-08-02 | 2017-09-13 | 2017-09-19 |  | NHS Provider
16/EM/0459 | 213319 | A Phase 2b, Randomized, Double-blind, Placebo-controlled Study to Evaluate the Antiviral Activity, Clinical Outcomes, Safety, Tolerability, and Pharmacokinetics of Orally Administered Study Drug Regimens in Adult Subjects Hospitalized with Respiratory Syncytial Virus |  | No | 2016-09-28 | 2017-06-08 | 2017-03-29 | 2017-07-27 | 2017-08-02 |  | Sponsor
16/LO/1318 | 187932 | Nucleos(t)ide withdrawal in Hepatitis B virus infection (NUC-B) |  | No | 2017-06-07 | 2017-06-20 | 2016-09-21 |  |  |  | Sponsor
17/LO/0568 | 215024 | Motivating Structured walking Activity in Intermittent Claudication (MOSAIC) |  | No | 2017-01-16 | 2017-07-03 | 2017-04-27 |  |  |  | Neither
17/LO/0863 | 228208 | EU-Wide Cross-Sectional Observational Study of Lipid-Modifying Therapy Use in Secondary and Primary Care - DA VINCI | 2017-08-31 | Yes | 2017-02-07 | 2017-07-03 | 2017-05-30 | 2017-08-11 | 2017-08-18 |  | Target met
17/EE/0295 | 212856 | Prostaglandin insert (Propess) versus tran-scervical balloon catheter for out-patient labour induction: A randomised controlled trial of feasibility (PROBIT-F) |  | No | 2017-06-26 | 2017-07-12 | 2017-08-25 | 2017-09-22 | 2017-09-22 |  | NHS Provider
17/LO/0318 | 212350 | PILOT STUDY for The TIGHT-K STUDY. Arrhythmias on the cardiac intensive care unit - does maintenance of high-normal serum potassium levels matter? | 2017-09-20 | Yes | 2017-05-10 | 2017-07-24 | 2017-07-24 | 2017-09-12 | 2017-09-15 | 2017-09-15 | Target met
17/NE/0238 | 225047 | A Phase 1b, Open-label, Single-dose Study to Evaluate the Pharmacokinetics, Safety, and Tolerability of MK-7655A in Pediatric Subjects From Birth to Less Than 18 Years of Age With Confirmed or Suspected Gram-negative Infections |  | Within 70 Days | 2017-07-18 | 2017-08-20 |  | 2017-09-25 |  |  | Within 70 Days
17/WM/0241 | 224978 | BUMP - Blood pressure monitoring in high risk pregnancy to improve the detection and monitoring of hypertension |  | Within 70 Days | 2017-09-18 | 2017-09-18 | 2017-08-09 |  |  |  | Within 70 Days
17/YH/0040 | 209462 | CP-4-006 - A PHASE 3, OPEN-LABEL, RANDOMIZED, MULTICENTER, 12 MONTHS, EFFICACY AND SAFETY STUDY OF WEEKLY MOD-4023 COMPARED TO DAILY GENOTROPIN? - THERAPY IN PRE-PUBERTAL CHILDREN WITH GROWTH HORMONE DEFICIENCY |  | Within 70 Days | 2016-10-13 | 2017-09-21 | 2017-09-04 |  |  |  | Within 70 Days
17/LO/0237 | 226490 | An open-label, multi-center long-term safety roll-over study in patients with tuberous sclerosis complex (TSC) and refractory seizures who are judged by the Investigator to benefit from continued treatment with everolimus after completion of Study CRAD001M2304 (EXIST-3 |  | Within 70 Days | 2017-07-06 | 2017-09-26 | 2017-09-06 | 2017-09-28 | 2017-09-29 | 2017-09-29 | Within 70 Days
17/YH/0055 | 215194 | Multiple Interventions for Diabetic Foot Ulcer Treatment (MIDFUT) Trial |  | Within 70 Days | 2017-09-07 | 2017-09-29 | 2017-05-24 |  |  |  | Within 70 Days