## Sheet1
Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | Date of First Patient Recruited | Benchmark Met | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Date Site Ready To Start | Reasons for delay correspond to:
17/LO/0182 | 213821 | A Prospective, Randomized, Multicenter Controlled Trial of CERAMENT?G as Part of Surgical Repair of Open Diaphyseal Tibial Fractures. |  | No | 2017-01-18 | 2017-03-31 | 2017-03-30 | 2017-07-06 | 2017-07-10 | 2017-07-13 | Both
16/LO/2153 | 217054 | A Randomised, Double-blind Placebo Controlled Trial Comparing the Effect of Intravenous Ferric Carboxymaltose on Hospitalisations and Mortality in Iron Deficient Patients Admitted for Acute Heart Failure (Affirm-AHF) | 2017-04-10 | Yes | 2016-10-27 | 2017-02-28 | 2017-02-09 | 2017-03-06 | 2017-03-09 | 2017-03-23 | Target Met
16/LO/0879 | 200503 | Response guided therapy with sofosbuvir and velpatasvir for 12 or 24 weeks in patients with genotype 3 chronic hepatitis C virus: is longer therapy worthwhile? | 2017-05-25 | No | 2017-01-16 | 2017-01-31 | 2016-12-20 | 2017-01-31 | 2017-02-21 | 2017-05-22 | Sponsor
16/WM/0215 | 203334 | An Assessment of Humacyte's Human Acellular Vessel in Patients Needing Renal Replacement Therapy: A comparison with ePTFE grafts as conduits for Hemodialysis |  | No | 2016-07-19 | 2017-01-20 | 2016-07-19 | 2017-03-19 | 2017-04-06 | 2017-04-06 | NHS Provider
17/LO/0089 | 219229 | A Phase 2, Multicenter, Open-Label Study to Evaluate the Efficacy and Safety of Sofosbuvir/Velpatasvir for 12 Weeks in Subjects with Chronic HCV Infection Who are on Dialysis for End Stage Renal Disease |  | No | 2016-11-07 | 2017-01-27 | 2017-03-27 | 2017-04-11 | 2017-04-24 | 2017-05-08 | NHS Provider
17/LO/0082 | 217324 | PuraStat; Post Market Performance during Vascular Surgery | 2017-06-14 | No | 2017-03-13 | 2017-03-13 | 2017-03-15 | 2017-04-21 | 2017-04-28 | 2017-05-02 | Neither
17/YH/0116 | 225662 | Efficacy and safety of semaglutide 1.0 mg once-weekly versusliraglutide 1.2 mg once-daily as add-on to 1-3 oral antidiabeticdrugs (OADs) in subjects with type 2 diabetes | 2017-06-27 | Yes | 2017-04-04 | 2017-04-27 | 2017-05-24 | 2017-06-15 | 2017-06-19 | 2017-06-19 | Target Met
17/NW/0175 | 222859 | Phase 1b Open-Label, Dose Escalation Study of PRTX-100 in Adult Patients with Persistent/Chronic Immune Thrombocytopenia |  | No | 2017-03-07 | 2017-05-19 | 2017-05-19 | 2017-06-01 | 2017-07-06 |  | NHS Provider
17/SC/0164 | 210735 | Early cryoprecipitate in major trauma haemorrhage: CRYOSTAT-2 | 2017-08-23 | No | 2017-04-20 | 2017-06-08 | 2017-05-26 | 2017-07-05 | 2017-07-05 | 2017-07-05 | Neither
16/SC/0604 | 214032 | A PHASE 3 MULTICENTER, RANDOMIZED, DOUBLE-BLIND, EXTENSION STUDY TO EVALUATE THE SAFETY OF DAILY ORAL DOSING OF TAFAMIDIS MEGLUMINE (PF-06291826) 20 MG OR 80 MG IN SUBJECTS DIAGNOSED WITH TRANSTHYRETIN CARDIOMYOPATHY (TTR-CM) |  | No | 2017-01-06 | 2017-06-30 | 2017-04-11 | 2017-06-28 | 2017-06-30 |  | Neither
16/SS/0137 | 199347 | Alteplase-Tenecteplase Trial Evaluation for Stroke Thrombolysis (ATTEST 2) |  | No | 2017-01-26 | 2017-09-06 | 2017-01-11 | 2017-11-07 | 2017-11-13 | 2018-01-16 | Sponsor
17/LO/0347 | 221524 | A Phase III Randomized, Double-blind Study to Evaluate Pembrolizumab plus Chemotherapy vs Placebo plus Chemotherapy as Neoadjuvant Therapy and Pembrolizumab vs Placebo as Adjuvant Therapy for Triple Negative Breast Cancer (TNBC) | 2017-11-06 | No | 2017-04-03 | 2017-06-29 | 2017-05-05 | 2017-07-25 | 2017-07-31 | 2017-07-31 | Neither
16/EE/0357 | 206501 | Safety and efficacy of opicapone in clinical practice in Parkinson?s disease with wearing- off motor fluctuations |  | No | 2017-04-04 | 2017-04-24 | 2016-10-31 | 2017-07-18 | 2017-07-28 | 2017-08-02 | NHS Provider
16/NW/0517 | 188554 | A phase III study to determine the role of ixazomib as an Augmented Conditioning therapy in salvage autologous stem | 2017-11-23 | No | 2016-07-29 | 2017-06-21 | 2016-10-27 | 2017-10-12 | 2017-10-20 | 2017-10-24 | NHS Provider
16/SC/0596 | 214948 | CONTRACT - CONservative Treatment of Appendicitis in Children - a randomised controlled Trial (Feasibility) | 2017-03-02 | Yes | 2016-10-26 | 2017-01-11 | 2017-01-11 | 2017-01-23 | 2017-02-09 | 2017-03-01 | Target Met
16/LO/1812 | 211705 | Safety of tenofovir alafenamide (TAF) in patients with a history of tubulopathy on tenofovir disoproxil fumarate (TDF) |  | No | 2017-03-01 | 2017-03-01 | 2016-11-28 | 2017-09-21 | 2017-10-19 | 2018-01-09 | Both
16/LO/2173 | 139794 | The Response To Ajmaline Provocation in Healthy Subjects | 2017-10-22 | No | 2016-12-01 | 2017-04-24 | 2017-04-24 | 2017-10-02 | 2017-10-02 | 2017-10-02 | NHS Provider
17/LO/0849 | 222165 | A Phase 3, Randomized, Double-Blind, Placebo-Controlled Study Evaluating the Safety and Efficacy of Selonsertib in Subjects with Compensated Cirrhosis due to Nonalcoholic Steatohepatitis (NASH) |  | No | 2017-05-11 | 2017-05-24 | 2017-08-02 | 2017-09-13 | 2017-09-20 | 2017-10-31 | Both
17/LO/0848 | 222163 | A Phase 3, Randomized, Double-Blind, Placebo-Controlled Study Evaluating the Safety and Efficacy of Selonsertib in Subjects with Nonalcoholic Steatohepatitis (NASH) and Bridging (F3) Fibrosis |  | No | 2017-02-20 | 2017-05-24 | 2017-08-02 | 2017-09-13 | 2017-09-19 | 2017-09-19 | NHS Provider
16/EM/0459 | 213319 | A Phase 2b, Randomized, Double-blind, Placebo-controlled Study to Evaluate the Antiviral Activity, Clinical Outcomes, Safety, Tolerability, and Pharmacokinetics of Orally Administered Study Drug Regimens in Adult Subjects Hospitalized with Respiratory Syncytial Virus |  | No | 2016-09-28 | 2017-06-08 | 2017-03-29 | 2017-07-27 | 2017-08-02 | 2017-11-03 | Neither
16/LO/1318 | 187932 | Nucleos(t)ide withdrawal in Hepatitis B virus infection (NUC-B) |  | Within 70 Days | 2017-06-07 | 2017-11-01 | 2016-09-21 | 2017-12-01 | 2017-12-04 |  | Sponsor
17/LO/0568 | 215024 | Motivating Structured walking Activity in Intermittent Claudication (MOSAIC) |  | No | 2017-01-16 | 2017-07-03 | 2017-04-27 | 2017-07-03 | 2017-12-07 | 2018-01-22 | Sponsor
17/EE/0295 | 212856 | Prostaglandin insert (Propess) versus tran-scervical balloon catheter for out-patient labour induction: A randomised controlled trial of feasibility (PROBIT-F) | 2017-10-19 | No | 2017-06-26 | 2017-07-12 | 2017-08-25 | 2017-09-22 | 2017-09-22 | 2017-09-22 | NHS Provider
17/LO/0318 | 212350 | PILOT STUDY for The TIGHT-K STUDY. Arrhythmias on the cardiac intensive care unit - does maintenance of high-normal serum potassium levels matter? | 2017-09-20 | Yes | 2017-05-10 | 2017-07-24 | 2017-07-24 | 2017-09-12 | 2017-09-15 | 2017-09-15 | Target Met
17/NE/0238 | 225047 | A Phase 1b, Open-label, Single-dose Study to Evaluate the Pharmacokinetics, Safety, and Tolerability of MK-7655A in Pediatric Subjects From Birth to Less Than 18 Years of Age With Confirmed or Suspected Gram-negative Infections |  | No | 2017-07-18 | 2017-08-20 | 2017-10-05 | 2017-09-25 | 2017-10-10 | 2017-10-11 | Neither
17/YH/0040 | 209462 | CP-4-006 - A PHASE 3, OPEN-LABEL, RANDOMIZED, MULTICENTER, 12 MONTHS, EFFICACY AND SAFETY STUDY OF WEEKLY MOD-4023 COMPARED TO DAILY GENOTROPIN? - THERAPY IN PRE-PUBERTAL CHILDREN WITH GROWTH HORMONE DEFICIENCY |  | No | 2016-10-13 | 2017-10-11 | 2017-09-04 |  |  |  | NHS Provider
17/LO/0237 | 226490 | An open-label, multi-center long-term safety roll-over study in patients with tuberous sclerosis complex (TSC) and refractory seizures who are judged by the Investigator to benefit from continued treatment with everolimus after completion of Study CRAD001M2304 (EXIST-3 | 2017-10-18 | Yes | 2017-07-06 | 2017-09-26 | 2017-09-06 | 2017-09-28 | 2017-09-29 | 2017-09-29 | Target Met
17/YH/0055 | 215194 | Multiple Interventions for Diabetic Foot Ulcer Treatment (MIDFUT) Trial |  | No | 2017-09-07 | 2017-09-29 | 2017-05-24 | 2017-10-27 | 2017-11-16 | 2017-11-30 | Sponsor
17/EE/0040 | 222216 | Emergency Cerclage in Twin pregnancies at Imminent Risk of Preterm Birth: an Open-Label Randomised Controlled Trial | 2017-10-27 | No | 2017-01-05 | 2017-03-02 | 2017-03-02 | 2017-05-15 | 2017-05-15 | 2017-05-15 | NHS Provider
15/NE/0415 | 189037 | A Phase III, randomized, double-blind, controlled, multicenter study of intravenous PI3K inhibitor copanlisib in combination with standard immunochemotherapy versus standard immunochemotherapy in patients with relapsed indolent non-Hodgkin?s lymphoma (iNHL) - CHRONOS-4 | 2017-06-15 | No | 2016-09-09 | 2017-03-20 | 2016-01-20 | 2017-06-08 | 2017-06-12 | 2017-06-14 | NHS Provider
17/SW/0010 | 197027 | A randomised controlled trial of topical intranasal tranexamic acid versus placebo to reduce the need for nasal packing in patients presenting to the Emergency Department with spontaneous epistaxis. | 2017-12-06 | Yes | 2017-09-29 | 2017-10-17 | 2017-03-14 | 2017-11-20 | 2017-11-21 | 2017-12-05 | Target Met
17/LO/1670 | 206926 | Bipolar Catheter Ablation for the Treatment of Ventricular Arrhythmias |  | Within 70 Days | 2017-09-11 | 2017-11-10 | 2017-12-07 | 2017-12-07 | 2017-12-07 | 2017-12-07 | Target Met
17/EM/0301 | 209448 | Sedation AND Weaning In CHildren: the SANDWICH trial |  | Within 70 Days | 2017-07-27 | 2017-10-30 | 2017-09-29 | 2017-10-03 | 2017-12-13 |  | NHS Provider
16/HRA/5525 | 210175 | A definitive randomised controlled trial investigating two online wellbeing interventions to reduce NHS staff stress | 2017-12-08 | Yes | 2017-09-06 | 2017-10-27 | 2017-01-23 | 2017-11-22 | 2017-11-22 | 2017-12-08 | Please Select...
17/LO/0747 | 217203 | Novel Diagnostic and Genomic Markers in Unexplained Sudden Cardiac Death: A Translational Cardiac Pathology Study | 2017-07-10 | Yes | 2017-04-11 | 2017-05-09 | 2017-05-30 | 2017-06-26 | 2017-06-26 | 2017-06-26 | Target Met
17/SW/0081 | 218329 | Multicenter, Observational, Registry to Assess Outcomes of Patients Treated with the CE Marked Nellix? System for Endovascular Abdominal Aortic Aneurysm Repair? Nellix Registry Study: EVAS-Global |  | No | 2016-11-17 | 2017-09-04 | 2017-09-04 | 2017-10-05 | 2017-10-11 | 2017-10-11 | Neither
17/YH/0150 | 223266 | Babies born Early Antibody Response to Men B vaccination: BEAR Men B | 2017-10-11 | No | 2017-04-19 | 2017-05-12 | 2017-07-05 | 2017-08-01 | 2017-08-01 | 2017-08-02 | NHS Provider
17/WN/0270 | 224222 | Post-Market Clinical Follow-Up (PMCF) Study to evaluate the Safety and efficacy of the MID-C system in Adolescent idiopathic scoliosis (AIS) |  | No | 2017-06-20 | 2017-10-12 | 2017-08-30 |  |  |  | NHS Provider
17/LO/1289 | 226881 | A Phase 2b Randomized Study to Assess the Efficacy and Safety of the Combination of Ublituximab + TGR-1202 with or without Bendamustine and TGR-1202 alone in Patients with Previously Treated Non-Hodgkin?s Lymphoma. | 2017-11-09 | Yes | 2017-05-31 | 2017-10-10 | 2017-10-17 | 2017-11-06 | 2017-11-07 | 2017-11-07 | Target Met
17/LO/1046 | 227189 | The impact of different rates of administration of a fluid challenge on the proportion of responders and non responders in the post-operative patient | 2017-10-11 | Yes | 2017-06-13 | 2017-08-02 | 2017-08-02 | 2017-08-29 | 2017-09-04 | 2017-09-04 | Target Met
17/LO/1737 | 230759 | Clinical Utility of Magnetocardiography (MCG) in patients with electrical and structural cardiac abnormalities |  | Within 70 Days | 2017-09-29 | 2017-10-25 | 2017-10-25 |  |  |  | Target Met