## Sheet1
Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | Date of First Patient Recruited | Benchmark Met | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Date Site Ready To Start | Reasons for delay correspond to:
17/YH/0116 | 225662 | Efficacy and safety of semaglutide 1.0 mg once-weekly versus liraglutide 1.2 mg once-daily as add-on to 1-3 oral antidiabetic drugs (OADs) in subjects with type 2 diabetes | 2017-07-03 | Yes | 2017-04-04 | 2017-04-27 | 2017-05-24 | 2017-06-15 | 2017-06-19 | 2017-06-19 | Target Met
17/NW/0175 | 222859 | Phase 1b Open-Label, Dose Escalation Study of PRTX-100 in Adult Patients with Persistent/Chronic Immune Thrombocytopenia |  | No | 2017-03-07 | 2017-05-19 | 2017-05-19 | 2017-06-01 | 2017-07-06 |  | NHS Provider
17/SC/0164 | 210735 | CRYOSTAT-2: A multi-centre, randomised, controlled trial evaluating the effects of early high-dose cryoprecipitate in adult patients with major trauma haemorrhage requiring major haemorrhage protocol (MHP) activation | 2017-08-23 | No | 2017-04-20 | 2017-06-08 | 2017-05-26 | 2017-07-05 | 2017-07-05 | 2017-07-05 | Neither
16/SC/0604 | 214032 | A PHASE 3 MULTICENTER, RANDOMIZED, DOUBLE-BLIND, EXTENSION STUDY TO EVALUATE THE SAFETY OF DAILY ORAL DOSING OF TAFAMIDIS MEGLUMINE (PF-06291826) 20 MG OR 80 MG IN SUBJECTS DIAGNOSED WITH TRANSTHYRETIN CARDIOMYOPATHY (TTR-CM) |  | No | 2017-01-06 | 2017-06-30 | 2017-04-11 | 2017-06-28 | 2017-06-30 | 2017-06-30 | Neither
16/SS/0137 | 199347 | Alteplase-Tenecteplase Trial Evaluation for Stroke Thrombolysis (ATTEST 2) | 2018-02-21 | No | 2017-01-26 | 2017-09-06 | 2017-01-11 | 2017-11-07 | 2017-11-13 | 2018-01-16 | Sponsor
17/LO/0347 | 221524 | A Phase III Randomized, Double-blind Study to Evaluate Pembrolizumab plus Chemotherapy vs Placebo plus Chemotherapy as Neoadjuvant Therapy and Pembrolizumab vs Placebo as Adjuvant Therapy for Triple Negative Breast Cancer (TNBC) | 2017-11-06 | No | 2017-04-03 | 2017-06-29 | 2017-05-05 | 2017-07-25 | 2017-07-31 | 2017-07-31 | Neither
16/EE/0357 | 206501 | Opicapone in clinical practice |  | No | 2017-04-04 | 2017-04-24 | 2016-10-31 | 2017-07-18 | 2017-07-28 | 2017-08-02 | NHS Provider
16/NW/0517 | 188554 | A phase III study to determine the role of ixazomib as an Augmented Conditioning therapy in salvage autologous stem | 2017-11-23 | No | 2016-07-29 | 2017-06-21 | 2016-10-27 | 2017-10-12 | 2017-10-20 | 2017-10-24 | NHS Provider
16/LO/2173 | 139794 | An observational study into the variety of electrocardiographic responses to an ajmaline Provocation in healthy subjects. What are the genetic and structural variations dictating this response? | 2017-10-22 | No | 2016-12-01 | 2017-04-24 | 2017-04-24 | 2017-10-02 | 2017-10-02 | 2017-10-02 | NHS Provider
17/LO/0849 | 222165 | A Phase 3, Randomized, Double-Blind, Placebo-Controlled Study Evaluating the Safety and Efficacy of Selonsertib in Subjects with Compensated Cirrhosis due to Nonalcoholic Steatohepatitis (NASH) | 2017-11-16 | No | 2017-05-11 | 2017-05-24 | 2017-08-02 | 2017-09-13 | 2017-09-20 | 2017-10-31 | Both
17/LO/0848 | 222163 | A Phase 3, Randomized, Double-Blind, Placebo-Controlled Study Evaluating the Safety and Efficacy of Selonsertib in Subjects with Nonalcoholic Steatohepatitis (NASH) and Bridging (F3) Fibrosis |  | No | 2017-02-20 | 2017-05-24 | 2017-08-02 | 2017-09-13 | 2017-09-19 | 2017-09-19 | NHS Provider
16/EM/0459 | 213319 | A Phase 2b, Randomized, Double-blind, Placebo-controlled Study to Evaluate the Antiviral Activity, Clinical Outcomes, Safety, Tolerability, and Pharmacokinetics of Orally Administered Study Drug Regimens in Adult Subjects Hospitalized with Respiratory Syncytial Virus |  | No | 2016-09-28 | 2017-06-08 | 2017-03-29 | 2017-07-27 | 2017-08-02 | 2017-11-03 | Sponsor
16/LO/1318 | 187932 | Nucleos(t)ide withdrawal in HBeAg negative hepatitis B virus infection to promote HBsAg clearance. (NUC-B) | 2018-03-01 | No | 2017-06-07 | 2017-11-01 | 2016-09-21 | 2017-12-01 | 2017-12-04 | 2018-01-24 | Sponsor
17/LO/0568 | 215024 | A brief physiotherapist-led behaviour-change intervention to facilitate walking in older people with peripheral arterial disease: A randomised controlled trial | 2018-02-12 | No | 2017-01-16 | 2017-07-03 | 2017-04-27 | 2017-07-03 | 2017-12-07 | 2018-01-22 | Sponsor
17/EE/0295 | 212856 | Prostaglandin insert (Propess) versus tran-scervical balloon catheter for out-patient labour induction: A randomised controlled trial of feasibility (PROBIT-F) | 2017-10-19 | No | 2017-06-26 | 2017-07-12 | 2017-08-25 | 2017-09-22 | 2017-09-22 | 2017-09-22 | NHS Provider
17/LO/0318 | 212350 | PILOT STUDY for The TIGHT-K STUDY. Arrhythmias on the cardiac intensive care unit - does maintenance of high-normal serum potassium levels matter? | 2017-09-20 | Yes | 2017-05-10 | 2017-07-24 | 2017-07-24 | 2017-09-12 | 2017-09-15 | 2017-09-15 | Sponsor
17/SC/0345 | 225047 | A Phase 1b, Open-label, Single-dose Study to Evaluate the Pharmacokinetics, Safety, and Tolerability of MK-7655A in Pediatric Subjects From Birth to Less Than 18 Years of Age With Confirmed or Suspected Gram-negative Infections |  | No | 2017-07-18 | 2017-08-20 | 2017-10-05 | 2017-09-25 | 2017-10-10 | 2017-10-11 | Neither
17/YH/0040 | 209462 | A PHASE 3, OPEN-LABEL, RANDOMIZED, MULTICENTER, 12 MONTHS, EFFICACY AND SAFETY STUDY OF WEEKLY MOD-4023 COMPARED TO DAILY GENOTROPIN® - THERAPY IN PRE-PUBERTAL CHILDREN WITH GROWTH HORMONE DEFICIENCY |  | No | 2016-10-13 | 2017-10-11 | 2017-09-04 | 2018-01-17 | 2018-01-17 | 2018-03-07 | Both
17/LO/0693 | 226490 | An open-label, multi-center long-term safety roll-over study in patients with tuberous sclerosis complex (TSC) and refractory seizures who are judged by the Investigator to benefit from continued treatment with everolimus after completion of Study CRAD001M2304 (EXIST-3) | 2017-10-18 | Yes | 2017-07-06 | 2017-09-26 | 2017-09-06 | 2017-09-28 | 2017-09-29 | 2017-10-02 | Target Met
17/YH/0055 | 215194 | MIDFUT |  | No | 2017-09-07 | 2017-09-29 | 2017-05-24 | 2017-10-27 | 2017-11-16 | 2017-11-30 | Sponsor
17/SW/0010 | 197027 | A randomised controlled trial of topical intranasal tranexamic acid versus placebo to reduce the need for nasal packing in patients presenting to the Emergency Department with spontaneous epistaxis. | 2017-12-06 | Yes | 2017-09-29 | 2017-10-17 | 2017-03-14 | 2017-11-20 | 2017-11-21 | 2017-12-05 | Target Met
17/LO/1670 | 206926 | Bipolar Catheter Ablation for the Treatment of Ventricular Arrhythmias | 2018-02-12 | No | 2017-09-11 | 2017-11-10 | 2017-12-07 | 2017-12-07 | 2017-12-07 | 2017-12-07 | Neither
17/EM/0301 | 209448 | Sedation AND Weaning In CHildren: the SANDWICH trial | 2018-02-06 | No | 2017-07-27 | 2017-10-30 | 2017-09-29 | 2017-10-03 | 2017-12-13 | 2018-02-05 | Sponsor
16/HRA/5525 | 210175 | A definitive randomised controlled trial investigating two online wellbeing interventions to reduce NHS staff stress | 2017-12-08 | Yes | 2017-09-06 | 2017-10-27 | 2017-01-23 | 2017-11-22 | 2017-11-22 | 2017-12-08 | Target Met
17/LO/0747 | 217203 | Novel Diagnostic and Genomic Markers in Unexplained Sudden Cardiac Death: A Translational Cardiac Pathology Study | 2017-07-10 | Yes | 2017-04-11 | 2017-05-09 | 2017-05-30 | 2017-06-26 | 2017-06-26 | 2017-06-26 | Target Met
17/SW/0081 | 218329 | Multicenter, Observational, Registry to Assess Outcomes of Patients Treated with the CE Marked Nellix? System for Endovascular Abdominal Aortic Aneurysm Repair? Nellix Registry Study: EVAS-Global |  | No | 2016-11-17 | 2017-09-04 | 2017-09-04 | 2017-10-05 | 2017-10-11 | 2017-10-11 | Neither
17/YH/0150 | 223266 | Babies born Early Antibody Response to Men B vaccination: BEAR Men B | 2017-10-11 | No | 2017-04-19 | 2017-05-12 | 2017-07-05 | 2017-08-01 | 2017-08-01 | 2017-08-02 | NHS Provider
17/WN/0270 | 224222 | Post-Market Clinical Follow-Up (PMCF) Study to evaluate the Safety and efficacy of the MID-C system in Adolescent idiopathic scoliosis (AIS) |  | No | 2017-06-20 | 2017-10-12 | 2017-08-30 |  |  |  | Sponsor
17/LO/1289 | 226881 | A Phase 2b Randomized Study to Assess the Efficacy and Safety of the Combination of Ublituximab + TGR-1202 with or without Bendamustine and TGR-1202 alone in Patients with Previously Treated Non-Hodgkin?s Lymphoma. | 2017-11-08 | Yes | 2017-05-31 | 2017-10-10 | 2017-10-17 | 2017-11-06 | 2017-11-07 | 2017-11-07 | Target Met
17/LO/1046 | 227189 | The impact of different rates of administration of a fluid challenge on the proportion of responders and non responders in the post-operative patient | 2017-10-11 | Yes | 2017-06-13 | 2017-08-02 | 2017-08-02 | 2017-08-29 | 2017-09-04 | 2017-09-04 | Target Met
17/LO/1737 | 230759 | Clinical Utility of Magnetocardiography (MCG) in patients with electrical and structural cardiac abnormalities |  | No | 2017-09-29 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2018-03-19 |  | Neither
15/NS/0113 | 188563 | The clinical and cost effectiveness of surgical interventions for stones in the lower kidney: The PUrE RCTPercutaneous Nephrolithotomy (PNL), Flexible Ureterorenoscopy (FURS) and Extracorporeal Lithotripsy (ESWL) for lower pole Kidney stones | 2017-10-04 | No | 2017-02-06 | 2017-04-13 | 2016-06-09 | 2017-08-07 | 2017-08-07 | 2017-09-06 | Both
17/LO/0272 | 218251 | A Multi-Center, Open-Label, Extension Study of Ublituximab (TG-1101) in Combination with TGR-1202 for Patients Previously Enrolled in Protocol UTX-TGR-304 |  | No | 2017-05-16 | 2017-05-16 | 2017-05-31 | 2017-11-28 | 2017-11-30 | 2017-12-11 | NHS Provider
17/LO/0842 | 225526 | Naso-ethmoidal EEG recording - A pilot study | 2017-12-13 | No | 2017-05-03 | 2017-05-24 | 2017-08-23 | 2017-09-04 | 2017-09-04 | 2017-09-04 | NHS Provider
16/WS/0057 | 193580 | A randomised, open-label trial of a Multimodal Intervention (Exercise, Nutrition and Anti-inflammatory Medication) plus standard care versus standard care alone to prevent / attenuate cachexia in advanced cancer patients undergoing chemotherapy. | 2017-11-14 | No | 2016-12-16 | 2017-08-31 | 2016-08-04 | 2017-09-21 | 2017-10-05 | 2017-10-30 | Sponsor
16/LO/1502 | 178292 | CTC-STOP: Utilising Circulating Tumor Cell (CTC) Counts to Optimise Systemic Therapy of Metastatic Prostate Cancer. |  | No | 2017-04-07 | 2017-12-13 | 2016-10-07 | 2018-01-18 | 2018-01-24 | 2018-01-30 | Neither
17/EE/0240 | 223309 | Phase II Neoadjuvant study of AXItinib for reducing extent of venous tumour thrombus in clear cell renal cell cancer with Venous invAsion |  | No | 2017-06-04 | 2018-01-08 | 2017-08-25 |  |  |  | NHS Provider
16/NE/0312 | 187560 | A double-blind, randomized, placebo-controlled study to investigate the efficacy and safety of cannabidiol (GWP42003-P,CBD) as add-on therapy in patients with tuberous sclerosis complex who experience inadequately-controlled focal seizures |  | Within 70 Days | 2017-02-14 | 2018-01-24 | 2017-02-22 | 2018-02-28 | 2018-03-06 |  | Sponsor
17/YH/0120 | 208838 | A pragmatic multi-centre randomised controlled non inferiority, cost effectiveness trial comparing injections of collagenase into the cord to surgical correction in the treatment of moderate Dupuytren’s Contracture in adult patients |  | Within 70 Days | 2017-08-15 | 2018-02-05 | 2017-05-25 | 2018-02-06 | 2018-03-01 | 2018-03-28 | Within 70 Days
17/YH/0386 | 233803 | The Cryo AF Global Registry is a prospective, global, multi-center, observational post-market registry |  | Within 70 Days | 2017-08-23 | 2018-02-09 | 2018-01-11 | 2018-03-07 | 2018-03-12 |  | Sponsor
17/EM/0394 | 232904 | Effectiveness and acceptability of myo-inositol nutritional supplement in the prevention of gestational diabetes: a pilot placebo controlled double blind randomised trial |  | Within 70 Days | 2018-01-26 | 2018-02-19 | 2017-12-29 |  |  |  | NHS Provider
18/SW/0002 | 233850 | A Double-blind Randomized Controlled Trial to Assess the Lot-to-lot Consistency of Sci-B-Vac™ in Adults (CONSTANT | 2018-04-11 | Yes | 2017-11-06 | 2018-02-22 | 2018-02-20 | 2018-03-06 | 2018-03-14 | 2018-03-14 | Target Met
16/NS/0106 | 212541 | Reducing Asthma Attacks in Children using Exhaled Nitric Oxide as a biomarker to inform treatment strategy |  | Within 70 Days | 2017-12-22 | 2018-03-08 | 2017-04-04 |  |  |  | Within 70 Days
17/LO/1785 | 233570 | A Phase 3, Randomized, Double-Blind Study of Pembrolizumab plus Ipilimumab vs Pembrolizumab plus Placebo in Previously Untreated, Stage IV, Metastatic Non-small Cell Lung Cancer Subjects Whose Tumors are PD-L1 Positive (TPS ≥ 50%) (KEYNOTE-598) |  | No | 2017-10-17 | 2018-01-04 | 2018-01-03 |  |  |  | NHS Provider
17/LO/1592 | 225931 | AN OPEN-LABEL, MULTICENTER EXTENSION STUDY IN PATIENTS PREVIOUSLY ENROLLED IN A GENENTECH− AND/OR F. HOFFMANN-LA ROCHE LTD−SPONSORED ATEZOLIZUMAB STUDY |  | Within 70 Days | 2018-02-28 | 2018-03-20 | 2017-11-07 |  |  |  | Within 70 Days
17/LO/1149 | 220763 | A Phase 3, Multicenter, Randomized, Double-blind, Double-dummy, Active-controlled Study to Assess the Efficacy and Safety of Maribavir Compared to Valganciclovir for the Treatment of Cytomegalovirus (CMV) Infection in Hematopoietic Stem Cell Transplant Recipients |  | No | 2017-02-28 | 2017-11-09 | 2017-09-12 |  |  |  | NHS Provider
17/NW/0254 | 225698 | A Phase III, Randomized, Double-Blind, Placebo-Controlled Clinical Trial of Pembrolizumab (MK-3475) as Monotherapy in the Adjuvant Treatment of Renal Cell Carcinoma Post Nephrectomy (KEYNOTE-564) |  | No | 2017-05-10 | 2017-08-29 | 2017-07-17 | 2018-01-29 | 2018-01-31 | 2018-02-20 | Both
17/LO/1296 | 228157 | Observational Registry Characterizing the Performance and Feature Use of the GORE® TAG® Conformable Thoracic Stent Graft featuring ACTIVECONTROL System | 2017-12-06 | Yes | 2017-05-05 | 2017-09-29 | 2017-09-15 | 2017-11-03 | 2017-11-08 | 2017-12-06 | Target Met
17/NE/0061 | 215780 | CONVINCE - COLchicine for preventioN of Vascular Inflammation in Non-CardioEmbolic stroke) - a randomised clinical trial of low-dose colchicine for secondary prevention after stroke. | 2018-03-05 | No | 2017-10-13 | 2017-11-20 | 2017-07-25 | 2017-12-19 | 2018-02-06 | 2018-02-13 | NHS Provider
17/EE/0382 | 220851 | PRedicting Outcomes For Crohn’s dIsease using a moLecular biomarkEr (PROFILE) trial |  | No | 2017-10-10 | 2018-01-02 | 2017-11-02 |  |  |  | Sponsor
17/EE/0481 | 226412 | Pre-Implantation Trial of Histopathology In renal Allografts (PITHIA) |  | No | 2017-08-29 | 2018-01-08 | 2018-01-18 | 2018-01-08 | 2018-01-15 |  | Sponsor
17/NE/0377 | 233847 | A phase 3b, multicenter, prospective, randomized, double blind, placebo-controlled study to reduce the incidence of pre-dialysis hyperkalemia with Sodium Zirconium Cyclosilicate (DIALIZE) |  | No | 2017-10-10 | 2018-01-08 | 2018-02-19 |  |  |  | NHS Provider
17/WM/0241 | 224978 | Blood pressure monitoring in high risk pregnancy to improve the detection and monitoring of hypertension | 2018-03-06 | Yes | 2017-09-18 | 2018-01-15 | 2017-08-09 | 2018-02-08 | 2018-02-23 | 2018-03-01 | Target Met
17/YH/0393 | 234355 | Paediatric Use of the Abbott Sensor Based Glucose Monitoring System for 21 days – an Accuracy Evaluation | 2018-04-04 | Yes | 2017-09-07 | 2018-01-26 | 2018-02-07 | 2018-03-20 | 2018-03-22 | 2018-03-22 | Target Met
16/EE/0294 | 199550 | ComparIsoN oF Optimal Hypertension RegiMens (Part of the Ancestry Informative Markers in Hypertension (AIM HY) Programme – AIM HY-INFORM) | 2018-03-12 | Yes | 2017-07-26 | 2018-01-19 | 2016-11-01 | 2018-02-20 | 2018-02-21 | 2018-02-21 | Target Met
17/SC/0643 | 235558 | A Phase 3, Randomized, Double-blind Study of BMS-986205 Combined with Nivolumab versus Nivolumab in Participants with Metastatic or Unresectable Melanoma that is Previously Untreated. | 2018-02-19 | Yes | 2017-10-13 | 2018-01-23 | 2018-01-18 | 2018-02-14 | 2018-02-15 | 2018-02-16 | Target Met
18/NI/0011 | 239180 | Forward Pro study |  | Within 70 Days | 2017-12-01 | 2018-01-26 | 2018-02-22 | 2018-03-29 |  |  | Both
16/YH/0454 | 211679 | A prospective multi-centre observational study to evaluate the capabilities of a portable magnetocardiograph device to rule-out acute coronary syndrome in patients who present to the emergency department with chest pain symptoms consistent with ACS: MAGNET ACS | 2018-03-01 | Yes | 2017-10-17 | 2018-01-31 | 2016-12-06 | 2018-02-23 | 2018-02-26 | 2018-03-01 | Target Met
17/SC/0035 | 215985 | A Randomized, Double-Blind, Multicenter, Placebo-Controlled, Parallel-Group Phase III Study to Evaluate the Efficacy, Tolerability and Safety of Intramuscular Injections of PLX-PAD for the Treatment of Subjects with Critical Limb Ischemia (CLI) with Minor Tissue Loss who are Unsuitable for Revascularization |  | Within 70 Days | 2017-03-01 | 2018-01-31 | 2017-07-14 |  |  |  | NHS Provider
17/EM/0077 | 206480 | LACunar Intervention (LACI-2) Trial-2: Assessment of safety and efficacy of cilostazol and isosorbide mononitrate to prevent recurrent lacunar stroke and progression of cerebral small vessel disease. |  | Within 70 Days | 2017-09-27 | 2018-03-20 | 2017-07-24 |  |  |  | Within 70 Days
18/SC/0055 | 239091 | Evaluating the effect of immunisation with group B meningococcal vaccines on meningococcal carriage |  | Within 70 Days | 2018-03-09 | 2018-03-09 | 2018-03-05 |  |  |  | Within 70 Days