## Sheet1
Trial Number | Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | Date of First Patient Recruited | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Date Site Ready To Start | Reasons for delay correspond to:
1 | 16/NE/0312 | 187560 | A double-blind, randomized, placebo-controlled study to investigate the efficacy and safety of cannabidiol (GWP42003-P,CBD) as add-on therapy in patients with tuberous sclerosis complex who experience inadequately-controlled focal seizures | 2018-04-19 | 2017-02-14 | 2018-01-24 | 2017-02-22 | 2018-02-28 | 2018-03-06 | 2018-04-10 | Sponsor
2 | 17/YH/0120 | 208838 | A pragmatic multi-centre randomised controlled non inferiority, cost effectiveness trial comparing injections of collagenase into the cord to surgical correction in the treatment of moderate Dupuytren?s Contracture in adult patients | 2018-06-12 | 2017-08-15 | 2018-02-05 | 2017-05-25 | 2018-02-06 | 2018-03-01 | 2018-03-28 | Both
3 | 17/YH/0386 | 233803 | The Cryo AF Global Registry is a prospective, global, multi-center, observational post-market registry | 2018-07-04 | 2017-08-23 | 2018-02-09 | 2018-01-11 | 2018-03-07 | 2018-03-12 | 2018-05-25 | Both
4 | 17/LO/1741 | 232904 | Effectiveness and acceptability of myo-inositol nutritional supplement in the prevention of gestational diabetes: a pilot placebo controlled double blind randomised trial | 2018-04-19 | 2018-01-26 | 2018-02-19 | 2017-12-29 | 2018-04-12 | 2018-04-16 | 2018-04-17 | NHS Provider
5 | 18/NW/0015 | 233850 | A Double-blind Randomized Controlled Trial to Assess the Lot-to-lot Consistency of Sci-B-Vac? in Adults (CONSTANT | 2018-04-11 | 2017-11-06 | 2018-02-22 | 2018-02-20 | 2018-03-06 | 2018-03-14 | 2018-03-14 | Targets Met
6 | 16/NS/0106 | 212541 | Reducing Asthma Attacks in Children using Exhaled Nitric Oxide as a biomarker to inform treatment strategy - a randomised trial (RAACENO) | 2018-11-08 | 2017-12-22 | 2018-03-08 | 2017-04-04 | 2018-06-27 | 2018-06-28 | 2018-08-28 | Both
7 | 17/LO/1785 | 233570 | A Phase 3, Randomized, Double-Blind Study of Pembrolizumab plus Ipilimumab vs Pembrolizumab plus Placebo in Previously Untreated, Stage IV, Metastatic Non-small Cell Lung Cancer Subjects Whose Tumors are PD-L1 Positive (TPS = 50%) (KEYNOTE-598) | 2018-06-15 | 2017-10-17 | 2018-01-04 | 2018-01-03 | 2018-04-18 | 2018-04-20 | 2018-04-23 | NHS Provider
8 | 17/LO/1592 | 225931 | AN OPEN-LABEL, MULTICENTER EXTENSION STUDY IN PATIENTS PREVIOUSLY ENROLLED IN A GENENTECH- AND/OR F. HOFFMANN-LA ROCHE LTD-SPONSORED ATEZOLIZUMAB STUDY | 2018-07-27 | 2018-02-28 | 2018-03-20 | 2017-11-07 | 2018-05-23 | 2018-05-29 | 2018-07-11 | Sponsor
9 | 17/EE/0382 | 220851 | PRedicting Outcomes For Crohn's dIsease using a moLecular biomarkEr (PROFILE) trial | 2018-05-11 | 2017-10-10 | 2018-01-02 | 2017-11-02 | 2018-02-27 | 2018-05-08 | 2018-05-08 | Sponsor
10 | 17/NE/0377 | 233847 | A phase 3b, multicenter, prospective, randomized, double blind, placebo-controlled study to reduce the incidence of pre-dialysis hyperkalemia with Sodium Zirconium Cyclosilicate (DIALIZE) | 2018-07-19 | 2017-10-10 | 2018-01-08 | 2018-02-19 | 2018-04-30 | 2018-05-08 | 2018-05-15 | NHS Provider
11 | 17/WM/0241 | 224978 | Blood pressure monitoring in high risk pregnancy to improve the detection and monitoring of hypertension | 2018-03-06 | 2017-09-18 | 2018-01-15 | 2017-08-09 | 2018-02-08 | 2018-02-23 | 2018-03-01 | Targets Met
12 | 17/YH/0393 | 234355 | Paediatric Use of the Abbott Sensor Based Glucose Monitoring System for 21 days - an Accuracy Evaluation | 2018-04-04 | 2017-09-07 | 2018-01-26 | 2018-02-07 | 2018-03-20 | 2018-03-22 | 2018-03-22 | Both
13 | 16/EE/0294 | 199550 | ComparIsoN oF Optimal Hypertension RegiMens (Part of the Ancestry Informative Markers in Hypertension (AIM HY) Programme ? AIM HY-INFORM) | 2018-03-12 | 2017-07-26 | 2018-01-19 | 2016-11-01 | 2018-02-20 | 2018-02-21 | 2018-02-22 | Targets Met
14 | 17/SC/0643 | 235558 | A Phase 3, Randomized, Double-blind Study of BMS-986205 Combined with Nivolumab versus Nivolumab in Participants with Metastatic or Unresectable Melanoma that is Previously Untreated. | 2018-02-19 | 2017-10-13 | 2018-01-23 | 2018-01-18 | 2018-02-14 | 2018-02-15 | 2018-02-16 | Targets Met
15 | 18/NI/0011 | 239180 | Forward Pro study | 2018-05-01 | 2017-12-01 | 2018-01-26 | 2018-02-22 | 2018-03-29 | 2018-04-11 | 2018-04-30 | Both
16 | 16/YH/0454 | 211679 | A prospective multi-centre observational study to evaluate the capabilities of a portable magnetocardiograph device to rule-out acute coronary syndrome in patients who present to the emergency department with chest pain symptoms consistent with ACS: MAGNET ACS | 2018-03-01 | 2017-10-17 | 2018-01-31 | 2016-12-06 | 2018-02-23 | 2018-02-26 | 2018-03-01 | Targets Met
17 | 17/SC/0035 | 215985 | A Randomized, Double-Blind, Multicenter, Placebo-Controlled, Parallel-Group Phase III Study to Evaluate the Efficacy, Tolerability and Safety of Intramuscular Injections of PLX-PAD for the Treatment of Subjects with Critical Limb Ischemia (CLI) with Minor Tissue Loss who are Unsuitable for Revascularization |  | 2017-03-01 | 2018-01-31 | 2017-07-14 | 2018-05-01 | 2018-05-03 | 2018-05-23 | NHS Provider
18 | 17/EM/0077 | 206480 | LACunar Intervention (LACI-2) Trial-2: Assessment of safety and efficacy of cilostazol and isosorbide mononitrate to prevent recurrent lacunar stroke and progression of cerebral small vessel disease. | 2018-06-25 | 2017-09-27 | 2018-03-20 | 2017-07-24 | 2018-04-18 | 2018-04-27 | 2018-06-19 | Sponsor
19 | 18/SC/0055 | 239091 | Evaluating the effect of immunisation with group B meningococcal vaccines on meningococcal carriage | 2018-04-17 | 2018-03-09 | 2018-03-09 | 2018-03-05 | 2018-04-13 | 2018-04-13 | 2018-04-13 | Targets Met
20 | 18/YH/0014 | 224065 | External frame versus internal locking plate for articular pilon fracture fixation: a multi-centre randomised controlled trial | 2018-09-26 | 2018-02-20 | 2018-06-20 | 2018-02-13 | 2018-06-21 | 2018-07-02 | 2018-07-09 | Neither
21 | 18/YH/0017 | 231431 | Improving the safety and continuity of medicines management at care transitions | 2018-06-28 | 2018-03-14 | 2018-04-12 | 2018-03-01 | 2018-04-12 | 2018-05-04 | 2018-06-12 | Sponsor
22 | 17/NW/0014 | 201841 | A multicentre, randomised controlled pilot trial of standard care informed by results of an additional placental factor blood test versus standard care in women presenting with reduced fetal movement (RFM) at or after 36+0 weeks gestation. | 2018-08-06 | 2017-02-10 | 2018-05-30 | 2017-02-02 | 2018-06-18 | 2018-06-27 | 2018-07-25 | Sponsor
23 | 18/NE/0132 | 242937 | A PHASE III, RANDOMIZED, MULTICENTER, OPEN-LABEL, TWO-ARM STUDY TO EVALUATE THE PHARMACOKINETICS, EFFICACY, AND SAFETY OF SUBCUTANEOUS ADMINISTRATION OF THE FIXED-DOSE COMBINATION OF PERTUZUMAB AND TRASTUZUMAB & CHEMOTHERAPY IN PATIENTS WITH HER2 POSITIVE EARLY BREAST CANCER | 2018-10-30 | 2018-02-27 | 2018-06-07 | 2018-06-04 | 2018-09-07 | 2018-09-07 | 2018-09-13 | NHS Provider
24 | 16/WA/0156 | 204506 | Minimally invasive thoracoscopically-guided right minithoracotomy versus conventional sternotomy for mitral valve repair: a multicentre randomised controlled trial (UK Mini Mitral). |  | 2018-02-05 | 2018-06-05 | 2016-07-19 | 2018-07-09 | 2018-07-11 |  | NHS Provider
25 | 17/WS/0081 | 225638 | Quantitative Fibronectin to help Decision-making in women with Symptoms of Preterm Labour - Comparison with Partosure and Actim Partus - QUIDS 2 | 2018-08-24 | 2018-06-05 | 2018-07-17 | 2017-08-15 | 2018-08-06 | 2018-08-07 | 2018-08-09 | Targets Met
26 | 18/WA/0057 | 238648 | A Phase III, Randomized, Double-Blind, Active Comparator-Controlled Study to Evaluate the Efficacy and Safety of MK-8228 (Letermovir) Versus Valganciclovir for the Prevention of Human Cytomegalovirus (CMV) Disease in Adult Kidney Transplant Recipients |  | 2017-07-31 | 2018-03-22 | 2018-04-03 | 2018-05-09 | 2018-05-17 | 2018-07-02 | Both
27 | 17/NE/0149 | 224550 | A Randomized, Double-Blind, Placebo-Controlled Phase 3 Study of Rovalpituzumab Tesirine as Maintenance Therapy Following First-Line Platinum-Based Chemotherapy in Subjects with Extensive Stage Small Cell Lung Cancer (MERU) | 2018-08-13 | 2018-03-23 | 2018-05-10 | 2017-06-19 | 2018-07-17 | 2018-07-17 | 2018-07-23 | NHS Provider
28 | 17/SS/0082 | 222441 | Start or STop Anticoagulants | 2018-11-08 | 2017-11-17 | 2018-05-02 | 2017-10-05 | 2018-07-05 | 2018-07-16 | 2018-07-16 | Sponsor
29 | 17/EM/0281 | 229054 | A Phase III, randomized, multicenter, parallel-group, non-inferiority study evaluating the efficacy, safety, and tolerability of switching to dolutegravir plus lamivudine in HIV-1-infected adults who are virologically suppressed |  | 2018-01-12 | 2018-02-15 | 2018-02-15 | 2018-04-20 | 2018-04-27 | 2018-05-04 | Sponsor
30 | 18/WS/0172 | 251636 | A randomized, open-label, multi-center, controlled clinical study to compare MAR-CUTIS with Dermabond Advanced in closure of surgical incisions and lacerations =15cm |  | 2017-07-31: 2018-07-11; 2018-03-22: 2018-09-25 | Targets Met
31 | 18/EM/0228 | 248988 | A double blind, placebo-controlled study to assess the antiviral effect, safety and tolerability of inhaled PC786 for the treatment of acute respiratory syncytial virus (RSV) infection in adult hematopoietic stem cell transplant recipients |  | 2018-08-08 | 2018-09-25 | 2018-08-21 | 2018-12-10 | 2018-12-10 |  | NHS Provider
32 | 18/NW/0290 | 226529 | A Phase 1/2, Multicenter, Open-label, Study of FT-2102 as a Single Agent and in Combination with Azacitidine in Patients with Acute Myeloid Leukemia or Myelodysplastic Syndrome with an IDH1 R132 Mutation |  | 2017-07-31: 2018-07-03; 2018-03-22: 2018-08-06; 2018-04-03: 2018-06-20 | NHS Provider
33 | 17/WS/0147 | 184216 | PRECISION-Panc: Advancing personalised medicine treatment strategies for pancreatic cancer. |  | 2018-03-02 | 2018-07-10 | 2018-01-05 | 2018-12-11 | 2018-12-11 |  | NHS Provider
34 | 18/LO/0204 | 216147 | A phase II study of nivolumab monotherapy in patients with relapsed/refractory Hodgkin lymphoma, fit for autologous stem cell transplant, who fail to reach complete metabolic remission after first or second line salvage therapy |  | 2017-07-31: 2018-06-25; 2018-03-22: 2018-07-09; 2018-04-03: 2018-04-13 | Sponsor
35 | 17/EE/0340 | 213113 | INTERIM: a randomised phase II feasibility study of INTERmittent versus continuous dosing of oral targeted combination therapy In patients with BRAFV600 mutant stage 3 unresectable or metastatic Melanoma |  | 2018-05-21 | 2018-06-26 | 2017-11-28 | 2018-11-26 | 2018-11-26 |  | Both
36 | 18/SC/0240 | 230920 | A Phase III, multicentre, randomised, double-blind, placebo-controlled, parallel-group, efficacy, and safety study of gantenerumab in patients with prodromal to mild Alzheimer's Disease |  | 2018-01-30 | 2018-06-07 | 2018-06-07 | 2018-09-03 | 2018-10-16 | 2018-10-17 | NHS Provider
37 | 18/SW/0135 | 232687 | A Randomised Controlled Trial of Surgical versus Non-Surgical Treatment of Lateral Compression Injuries of the Pelvis with Complete Sacral Fractures (LC1) in the Non-fragility Fracture Patient - A Feasibility Study. |  | 2018-08-02 | 2018-09-17 | 2018-07-04 | 2018-09-19 | 2018-10-08 | 2018-10-31 | NHS Provider
38 | 16/SS/0070 | 202282 | PREvention of Complications to Improve Outcome in elderly patients with acute Stroke. A randomised, open, phase III, clinical trial with blinded outcome assessment | 2018-12-13 | 2018-03-15 | 2018-09-05 | 2017-06-05 | 2018-10-03 | 2018-10-05 | 2018-10-26 | Sponsor
39 | 18/LO/0555 | 237992 | Preventing Ovarian Cancer through early Excision of Tubes and late Ovarian Removal |  | 2018-08-15 | 2018-09-11 | 2018-04-19 | 2018-09-26 | 2018-09-26 | 2018-12-18 | Sponsor
40 | 18/LO/0012 | 225166 | Parallel-Group, Placebo-Controlled, Randomized Study Investigating the Effect of Intravenous Iso-osmolar Iodinated Contrast Material Iodixanol (Visipaque? Injection 320mgI/mL) on Renal Function in Adults with Chronic Kidney Disease (CKD) Stage III or Stage IV who have undergone Endovascular Aneurysm Repair (EVAR). |  | 2017-09-21 | 2018-03-13 | 2018-03-08 | 2018-06-28 | 2018-07-12 |  | Both
41 | 17/EE/0271 | 225013 | AceFIT ? Acetabular Fractures in older patients Intervention Trial. A feasibility study comparing three methods of treatment of acetabular fractures in older patients; surgical fixation versus surgical fixation and hip replacement versus non-surgical treatment. | 2018-11-04 | 2018-01-24 | 2018-07-25 | 2017-10-10 | 2018-09-14 | 2018-09-19 | 2018-10-29 | Sponsor
42 | 18/LO/0486 | 235388 | A randomised controlled trial of specialist physiotherapy for Functional Motor Disorder (Physio4FMD) | 2018-10-19 | 2017-09-18 | 2018-07-17 | 2018-03-29 | 2018-07-17 | 2018-09-18 | 2018-09-28 | Sponsor
43 | 18/NE/0214 | 245998 | A SINGLE ARM, OPEN LABEL MULTICENTRE EXTENSION STUDY TO EVALUATE THE EFFECTIVENESS AND SAFETY OF OCRELIZUMAB IN PATIENTS WITH MULTIPLE SCLEROSIS PREVIOUSLY ENROLLED IN A F. HOFFMANN-LA ROCHE SPONSORED OCRELIZUMAB PHASE IIIb/IV CLINICAL TRIAL | 2018-10-23 | 2018-03-07 | 2018-07-13 | 2018-07-11 | 2018-09-05 | 2018-09-13 | 2018-10-11 | Sponsor
44 | 18/LO/1069 | 244789 | A Study of the Safety and Efficacy of IMM-101 in Combination with Checkpoint Inhibitor Therapy in Patients with Advanced Melanoma | 2018-09-17 | 2018-02-07 | 2018-08-09 | 2018-08-09 | 2018-09-11 | 2018-09-11 | 2018-09-13 | Targets Met
45 | 18/LO/1192 | 248843 | A Phase 3b, Multicenter, Randomized, Blinded, Active-Controlled Study to Compare the Efficacy and Safety of Ustekinumab to that of Adalimumab in the Treatment of Biologic Na?ve Subjects with Moderately-to-Severely Active Crohn?s Disease | 2018-09-13 | 2018-03-20 | 2018-08-28 | 2018-08-24 | 2018-08-30 | 2018-09-10 | 2018-09-12 | Targets Met
46 | 16/EM/0322 | 202096 | A randomised-controlled trial of thrombolytic treatment with tenecteplase for acute ischaemic stroke upon awakening | 2018-12-31 | 2018-03-13 | 2018-07-06 | 2017-08-18 | 2018-08-06 | 2018-08-15 | 2018-09-04 | Sponsor
47 | 17/SC/0618 | 225232 | A first-in-human, two-part (open label, and randomised/double blind/placebo controlled), single-and repeat-dose study of CSJ137 in erythropoietin-treated chronic haemodialysis patients with functional iron-deficiency anaemia. |  | 2017-08-15 | 2018-06-12 | 2018-01-31 | 2018-07-17 | 2018-07-20 | 2018-10-04 | Both
48 | 18/SC/0360 | 239977 | Reducing Acquisition of CMV through antenatal Education: A feasibility study to assess an educational intervention to prevent cytomegalovirus infection in pregnancy | 2018-09-04 | 2018-05-13 | 2018-08-14 | 2018-08-14 | 2018-08-31 | 2018-08-31 | 2018-09-03 | Targets Met
49 | 18/SC/0412 | 250170 | A Phase III, Randomized, Double-blind Trial Comparing Trastuzumab Plus Chemotherapy and Pembrolizumab With Trastuzumab Plus Chemotherapy and Placebo as First-line Treatment in Participants With HER2 Positive Advanced Gastric or Gastroesophageal Junction Adenocarcinoma (KEYNOTE 811) |  | 2017-07-31: 2018-05-16; 2018-03-22: 2018-12-31; 2018-04-03: 2018-10-08 | Targets Met
50 | 18/LO/0165 | 224726 | POLEM: Avelumab plus 5-FU based chemotherapy as adjuvant treatment for stage 3 MSI-High or POLE exonuclease domain mutant colon cancer: A phase 3 randomised study. |  | 2017-07-31: 2018-04-27; 2018-03-22: 2018-12-20; 2018-04-03: 2018-05-09 | Targets Met
51 | 17/LO/0621 | 191390 | STandard versus Accelerated initiation of Renal Replacement Therapy in Acute Kidney Injury (STARRT-AKI): A Multi-Centre Randomized Controlled Trial |  | 2017-07-31: 2018-11-06; 2018-03-22: 2018-12-18; 2018-04-03: 2017-05-22 | Targets Met
52 | 18/SC/0155 | 236211 | A multicentre international randomized parallel group double-blind placebo-controlled clinical trial of EMPAgliflozin once daily to assess cardio-renal outcomes in patients with chronic KIDNEY disease |  | 2017-07-31: 2018-04-25; 2018-03-22: 2018-11-20; 2018-04-03: 2018-04-26 | NHS Provider
53 | 17/NI/0204 | 230772 | Nordic-Baltic-British Study on Optical Coherence Tomography Optimized Bifurcation Event Reduction |  | 2017-07-31: 2018-04-19; 2018-03-22: 2018-11-07; 2018-04-03: 2018-04-05 | Both
54 | 18/LO/1187 | 240011 | ATHENA (A Multicenter, Randomized, Double-Blind, Placebo-Controlled Phase 3 Study in Ovarian Cancer Patients Evaluating Rucaparib and Nivolumab as Maintenance Treatment Following Response to Front-Line Platinum-Based Chemotherapy) |  | 2017-07-31: 2018-03-22; 2018-03-22: 2018-10-23; 2018-04-03: 2018-09-11 | NHS Provider
55 | 18/LO/0512 | 196718 | An international multi-centre randomised phase II study to assess the efficacy of TAK228 in combination with intravenous weekly paclitaxel compared with weekly paclitaxel alone in women with advanced/recurrent epithelial ovarian, fallopian tube or primary peritoneal cancer (of clear cell, endometrioid and high grade serous type, and carcinosarcoma) |  | 2017-07-31: 2018-03-09; 2018-03-22: 2018-10-01; 2018-04-03: 2018-06-05 | NHS Provider
56 | 17/LO/1918 | 229435 | Does Neuromuscular Electrical Stimulation Improve the Absolute Walking Distance in Patients with Intermittent Claudication (NESIC) compared to best available treatment? A Multicentre Randomised Controlled Study. |  | 2018-10-02 | 2018-11-21 | 2018-01-29 | 2018-12-19 | 2018-12-19 |  | Targets Met
57 | 17/WS/0142 | 221370 | PRIMUS 001 - An adaptive phase II study of FOLFOX-A (FOLFOX and nab-paclitaxel) versus AG (nab-paclitaxel and gemcitabine) in patients with metastatic pancreatic cancer, with integrated biomarker evaluation |  | 2017-09-06 | 2018-12-12 | 2017-09-07 | 2018-12-17 | 2018-12-17 |  | Targets Met
58 | 17/EE/0240 | 223309 | Phase II Neoadjuvant study of AXItinib for reducing extent of venous tumour thrombus in clear cell renal cell cancer with Venous invAsion |  | 2017-09-06 | 2018-10-26 | 2017-08-25 | 2018-11-22 | 2018-11-22 | 2018-12-04 | Neither
59 | 18/LO/0133 | 228164 | Can patients with multiple breast cancers in the same breast avoid mastectomy by having multiple lumpectomies to achieve equivalent rates of local breast cancer recurrence? A randomised controlled feasibility study. |  | 2018-02-15 | 2018-06-14 | 2018-03-15 | 2018-10-23 | 2018-10-23 | 2018-10-25 | Both
60 | 18/WM/0037 | 228917 | A Multicenter, Randomized, Double-Blind, Placebo-Controlled Induction Study of the Efficacy and Safety of Upadacitinib (ABT-494) in Subjects with Moderately to Severely Active Crohn's Disease who have Inadequately Responded to or are Intolerant to Biologic Therapy |  | 2018-04-20 | 2018-10-22 | 2018-03-26 | 2018-11-15 | 2018-11-15 | 2018-12-04 | Neither
61 | 18/EE/0171 | 237302 | A double-blind, randomised, placebo-controlled, parallel group trial to evaluate the efficacy and safety of empagliflozin and linagliptin over 26 weeks, with a double-blind active treatment safety extension period up to 52 weeks, in children and adolescents with type 2 diabetes mellitus. |  | 2016-11-28 | 2018-08-09 | 2018-08-08 | 2018-11-26 | 2018-11-26 | 2018-12-03 | Sponsor
62 | 18/WM/0038 | 235048 | A Multicenter, Randomized, Double-Blind, Placebo-Controlled Induction Study of the Efficacy and Safety of Upadacitinib (ABT-494) in Subjects with Moderately to Severely Active Crohn's Disease Who Have Inadequately Responded to or are Intolerant to Conventional Therapies but Have Not Failed Biologic Therapy. |  | 2018-04-20 | 2018-10-22 | 2018-03-26 | 2018-11-15 | 2018-11-15 | 2018-12-04 | Sponsor
63 | 18/WM/0039 | 236159 | A Multicenter, Randomized, Double-Blind, Placebo-Controlled Maintenance and Long-Term Extension Study of the Efficacy and Safety of Upadacitinib (ABT-494) in Subjects with Crohn's Disease who Completed the Studies M14-431 or M14-433 |  | 2018-04-20 | 2018-10-22 | 2018-03-26 | 2018-11-15 | 2018-11-15 | 2018-12-04 | Neither
64 | 18/SC/0006 | 220480 | Brain Machine Interfaces based on subcortical LFP Signals for Neuroprosthetic Control and Neurofeedback Therapy | 2018-11-17 | 2018-07-02 | 2018-10-23 | 2018-06-12 | 2018-11-06 | 2018-11-09 | 2018-11-09 | Targets Met
65 | 18/YH/0223 | 243476 | Immunogenicity and Safety Study of an Investigational Quadrivalent Meningococcal Conjugate Vaccine in Infants and Toddlers when Administered Using a 1+1 Schedule in a National Immunization Schedule Having a Meningococcal Group B Vaccine as Standard of Care |  | 2018-01-19 | 2018-07-13 | 2018-07-09 | 2018-11-13 | 2018-11-14 | 2018-11-15 | Both
66 | 18/EM/0264 | 231952 | A 12 month, partially-blinded, active-controlled, multi-centre, randomized study evualting efficacy, safety, tolerability, Pharmacokinectics(PK) and pharmacodynamics (PD) of an anti-CD40 monoclonal antibody, CFZ533 in de novo and maintenance kidney transplant recipients (CIRRUS-1) |  | 2017-12-22 | 2018-10-16 | 2018-11-01 | 2018-11-09 | 2018-11-15 | 2018-11-21 | NHS Provider
67 | 17/NW/0639 | 233415 | Post-market Study of the Endurant ChEVAR Technique for the treatment of Juxtarenal Aortic Aneurysms with a Short Infrarenal Neck | 2018-04-13 | 2017-09-05 | 2018-01-26 | 2018-01-22 | 2018-02-08 | 2018-02-26 | 2018-03-27 | Both
68 | 18/EM/0184 | 233744 | Desmopressin for reversal of Antiplatelet drugs in Stroke due to Haemorrhage (DASH) |  | 2018-07-11 | 2018-11-09 | 2018-09-04 | 2018-11-27 | 2018-12-04 |  | Targets Met
69 | 18/NE/0023 | 230930 | Randomised, double-blind, placebo controlled multi-centre study to assess the efficacy, tolerability and safety of Enterosgel? in the treatment of Irritable Bowel Syndrome with Diarrhoea (IBS-D) in adults |  | 2017-12-12 | 2018-10-10 | 2018-02-27 | 2018-10-24 | 2018-10-24 |  | Sponsor
70 | 18/LO/0866 | 224730 | Prevention Of Hypertensive Injury to the Brain by Intensive Treatment after Intracerebral Haemorrhage: a pilot randomised trial of home telemetry-guided treatment |  | 2018-08-02 | 2018-10-03 | 2018-06-26 | 2018-11-05 | 2018-11-09 |  | Sponsor
71 | 18/SC/0024 | 219560 | Nail bed INJury Analysis (NINJA): Should the nail plate be replaced or discarded after nail bed repair in children? |  | 2017-10-01 | 2018-08-09 | 2018-02-20 | 2018-11-13 | 2018-12-10 |  | Both