## Sheet1
Trial Number | Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | Date of First Patient Recruited | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Date Site Ready To Start | Reasons for delay
1 | 17/NE/0325 | 227986 | EMPOWER: EMesis in Pregnancy - Ondansetron With mEtoclopRamide. |  | 2017-10-16 | 2018-10-15 | 2017-11-30 | 2018-10-26 | 2019-01-18 | 2019-05-21 | Both
2 | 18/EM/0228 | 248988 | A double blind, placebo-controlled study to assess the antiviral effect, safety and tolerability of inhaled PC786 for the treatment of acute respiratory syncytial virus (RSV) infection in adult hematopoietic stem cell transplant recipients |  | 2018-08-08 | 2018-10-30 | 2018-08-21 | 2018-12-10 | 2018-12-10 | 2018-12-10 | Both
3 | 17/WS/0210 | 231280 | A placebo controlled randomised trial of intravenous lidocaine in accelerating gastrointestinal recovery after colorectal surgery | 2019-09-25 | 2018-11-08 | 2018-12-07 | 2018-04-27 | 2019-01-10 | 2019-01-18 | 2019-08-01 | Both
4 | 18/WS/0172 | 251636 | A randomized, open-label, multi-center, controlled clinical study to compare MAR-CUTIS with Dermabond Advanced in closure of surgical incisions and lacerations =15cm | 2019-04-12 | 2018-07-11 | 2019-01-07 | 2019-01-03 | 2019-01-07 | 2019-01-17 | 2019-02-05 | Sponsor
5 | 18/LO/1567 | 242092 | A Randomised, Controlled, Open-label, Global Phase 3 Study Comparing the Efficacy of the anti-PD-1 Antibody BGB-A317 versus Chemotherapy as Second Line Treatment in Participants with Advanced Unresectable/Metastatic Esophageal Squamous Cell Carcinoma |  | 2018-09-25 | 2019-02-13 | 2018-11-28 | 2019-06-07 | 2019-06-07 | 2019-07-03 | Both
6 | 18/EM/0321 | 252536 | An Open-label, 8 Week Study to Compare the Comfort and Complexity of Five Treatment Regimens for CNTX 4975-05 Intra-articular Injection in Subjects with Chronic, Moderate-to-Severe Osteoarthritis Knee Pain | 2019-05-20 | 2018-09-25 | 2019-01-11 | 2018-12-18 | 2019-03-07 | 2019-03-13 | 2019-05-01 | Sponsor
7 | 18/EM/0264 | 231952 | A 12 month, partially-blinded, active-controlled, multi-centre, randomized study evualting efficacy, safety, tolerability, Pharmacokinectics(PK) and pharmacodynamics (PD) of an anti-CD40 monoclonal antibody, CFZ533 in de novo and maintenance kidney transplant recipients (CIRRUS-1) | 2019-09-20 | 2017-12-22 | 2018-10-16 | 2018-11-01 | 2018-11-09 | 2018-11-15 | 2018-11-21 | NHS Provider
8 | 18/LO/0512 | 196718 | An international multi-centre randomised phase II study to assess the efficacy of TAK228 in combination with intravenous weekly paclitaxel compared with weekly paclitaxel alone in women with advanced/recurrent epithelial ovarian, fallopian tube or primary peritoneal cancer (of clear cell, endometrioid and high grade serous type, and carcinosarcoma) |  | 2018-03-09 | 2018-10-01 | 2018-06-05 | 2019-02-11 | 2019-02-11 | 2019-02-12 | NHS Provider
9 | 18/SC/0155 | 236211 | A multicentre international randomized parallel group double-blind placebo-controlled clinical trial of EMPAgliflozin once daily to assess cardio-renal outcomes in patients with chronic KIDNEY disease | 2019-09-03 | 2018-04-25 | 2018-11-20 | 2018-04-26 | 2019-01-30 | 2019-02-05 | 2019-03-18 | Both
10 | 17/NI/0204 | 230772 | Nordic-Baltic-British Study on Optical Coherence Tomography Optimized Bifurcation Event Reduction | 2019-08-15 | 2018-04-19 | 2018-11-07 | 2018-04-05 | 2019-03-08 | 2019-03-12 | 2019-07-29 | Both
11 | 19/NW/0045 | 255691 | I8B-MC-ITSB; A Prospective, Randomized, Double-Blind Comparison of LY900014 to Humalog with an Open-Label Postprandial LY900014 Treatment Group in Children and Adolescents with Type 1 Diabetes PRONTO-Peds |  | 2018-10-30 | 2019-05-13 | 2019-04-10 | 2019-07-01 | 2019-07-09 | 2019-09-04 | Both
12 | 18/SS/0085 | 243640 | Alpha 2 agonists for sedation to produce better outcomes from critical illness (A2B Trial): A randomised, parallelgroup, allocation concealed, controlled, open, phase 3 pragmatic clinical and cost- effectiveness trial with internal pilot (A2B Trial) | 2019-07-29 | 2018-10-05 | 2019-03-19 | 2018-12-14 | 2019-06-10 | 2019-06-18 | 2019-07-18 | Both
13 | 18/EE/0222 | 233921 | A randomised controlled trial of very early versus delayed angiography +/-intervention on outcomes in patients with non ST-elevation myocardial infarction | 2019-07-19 | 2017-11-21 | 2019-02-08 | 2018-09-12 | 2019-03-26 | 2019-03-29 | 2019-04-11 | Both
14 | 18/WA/0108 | 235402 | ICONS II: Identifying Continence OptioNs after Stroke randomised controlled trial |  | 2019-05-01 | 2019-06-10 | 2018-04-03 | 2019-07-30 | 2019-08-01 | 2019-08-06 | NHS Provider
15 | 18/LO/0165 | 224726 | POLEM: Avelumab plus 5-FU based chemotherapy as adjuvant treatment for stage 3 MSI-High or POLE exonuclease domain mutant colon cancer: A phase 3 randomised study. |  | 2018-04-27 | 2019-02-01 | 2018-05-09 | 2019-04-15 | 2019-04-15 | 2019-05-10 | Both
16 | 17/SC/0165 | 220647 | A Phase 2, Double-Blind, Randomized, Placebo-Controlled Study Evaluating the Efficacy and Safety of Filgotinib in the Treatment of Small Bowel Crohn?s Disease (SBCD) |  | 2018-11-07 | 2019-02-07 | 2017-06-30 | 2019-06-25 | 2019-07-04 | 2019-07-31 | Both
17 | 18/LO/1187 | 240011 | A Multicenter, Randomized, Double-Blind, Placebo-Controlled Phase 3 Study in Ovarian Cancer Patients Evaluating Rucaparib and Nivolumab as Maintenance Treatment Following Response to Front-Line Platinum-Based Chemotherapy |  | 2018-03-22 | 2018-12-01 | 2018-09-11 | 2019-04-23 | 2019-04-23 | 2019-06-06 | NHS Provider
18 | 17/LO/1180 | 223814 | A phase Ib study of Pembrolizumab following Trans-Arterial chemoembolization in primary Liver carcinoma. | 2019-07-26 | 2018-07-18 | 2019-01-17 | 2018-01-19 | 2019-03-21 | 2019-03-21 | 2019-03-21 | Both
19 | 18/NE/0125 | 238346 | A three-arm randomised controlled trial to assess the effectiveness and cost-effectiveness of reverse shoulder arthroplasty versus hemiarthroplasty versus non-surgical care for acute three and four- part fractures of the proximal humerus in patients over 65 years of age ? Proximal Fracture Of the Humerus: Evaluation by Randomisation trial No.2 (PROFHER-2). |  | 2019-03-06 | 2019-03-25 | 2018-05-15 | 2019-06-24 | 2019-07-08 | 2019-08-29 | Both
20 | 19/EE/0122 | 253770 | A PHASE 3, RANDOMIZED, MULTICENTER, OPEN-LABEL, CROSSOVER STUDY ASSESSING SUBJECT PERCEPTION OF TREATMENT BURDEN WITH USE OF WEEKLY GROWTH HORMONE (SOMATROGON) VERSUS DAILY GROWTH HORMONE (GENOTROPIN?) INJECTIONS IN CHILDREN WITH GROWTH HORMONE DEFICIENCY | 2019-07-25 | 2019-02-21 | 2019-05-20 | 2019-05-20 | 2019-05-24 | 2019-05-28 | 2019-06-28 | Neither
21 | 18/LO/1184 | 239603 | Clinical Study Protocol M16-067: A Multicenter, Randomized, Double-Blind, Placebo-Controlled Induction Study to Evaluate the Efficacy and Safety of Risankizumab in Subjects with Moderately to Severely Active Ulcerative Colitis Who Have Failed Prior Biologic Therapy |  | 2018-08-14 | 2019-02-04 | 2018-12-20 | 2019-06-03 | 2019-06-04 | 2019-07-12 | Sponsor
22 | 19/WA/0140 | 251241 | The acceptability and feasibility of a Paediatric Intensive Care Unit (PICU) Storybook Intervention for children and their caregivers: A multiple-case series study | 2019-06-21 | 2019-04-09 | 2019-04-18 | 2019-05-08 | 2019-06-04 | 2019-06-04 | 2019-06-04 | NHS Provider
23 | 19/WM/0039 | 257987 | FLOW- Effect of semaglutide versus placebo on the progression of renal impairment in subjects with type 2 diabetes and chronic kidney disease |  | 2019-01-17 | 2019-03-18 | 2019-04-15 | 2019-06-11 | 2019-06-12 | 2019-06-12 | Neither
24 | 17/NW/0581 | 214739 | Does Interleukin-1 Receptor Antagonist Improve Outcome following aneurysmal Subarachnoid Haemorrhage (aSAH)? A Phase III trial | 2019-09-20 | 2018-12-03 | 2019-03-31 | 2018-08-07 | 2019-07-09 | 2019-07-15 | 2019-07-19 | Both
25 | 19/YH/0015 | 255446 | Beta Blockers or placebo for primary prophylaxis of oesophageal varices (BOPPP Trial). A blinded, multi-centre, clinical effectiveness and cost-effectiveness randomised controlled trial |  | 2018-09-06 | 2019-04-26 | 2019-04-24 | 2019-05-23 | 2019-05-30 | 2019-09-06 | NHS Provider
26 | 19/LO/0316 | 244931 | LESS-VT FLExAbility Sensor Enabled Substrate Targeted Ablation for the Reduction of VT (LESS-VT) Study | 2019-08-15 | 2018-09-07 | 2019-06-10 | 2019-05-31 | 2019-07-01 | 2019-07-04 | 2019-07-30 | Sponsor
27 | 18/YH/0136 | 214921 | A multi-centre, pilot, prospective, trial of DermaRep? Device in the treatment of venous leg ulcers |  | 2019-01-14 | 2019-05-09 | 2018-07-09 | 2019-05-23 | 2019-05-23 | 2019-05-23 | Neither
28 | 18/EE/0373 | 249396 | A Randomized, Double-Blind, Phase III Study of Pembrolizumab versus Placebo in Combination with Neoadjuvant Chemotherapy and Adjuvant Endocrine Therapy for the Treatment of High-Risk Early-Stage Hormone Receptor-Positive, Human Epidermal Growth Factor Receptor 2-Negative (HR+/HER2?) Breast Cancer (KEYNOTE-756) | 2019-09-19 | 2018-02-22 | 2019-02-28 | 2019-01-19 | 2019-06-05 | 2019-06-05 | 2019-06-06 | NHS Provider
29 | 18/EM/0298 | 251419 | A Phase 3b, Randomized, Double-blind, Placebo-controlled Study to Evaluate the Efficacy and Safety of TRC101 in Delaying Chronic Kidney Disease Progression in Subjects with Metabolic Acidosis | 2019-09-17 | 2018-06-11 | 2019-01-18 | 2018-11-21 | 2019-02-22 | 2019-02-27 | 2019-03-25 | NHS Provider
30 | 16/LO/1675 | 210329 | A Multicenter, Randomized, Double-Blind, Placebo-Controlled Study to Evaluate the Safety and Efficacy of ABT-494 for Induction and Maintenance Therapy in Subjects with Moderately to Severely Active Ulcerative Colitis |  | 2018-08-14 | 2019-01-10 | 2016-12-20 | 2019-05-03 | 2019-05-03 | 2019-07-12 | Both
31 | 16/LO/1676 | 211480 | A Phase 3 Multicenter, Open-Label Extension (OLE) Study to Evaluate the Long-Term Safety and Efficacy of ABT-494 in Subjects with Ulcerative Colitis (UC) |  | 2018-08-14 | 2019-01-10 | 2017-01-25 | 2019-05-03 | 2019-05-03 | 2019-07-12 | Both
32 | 18/LO/1185 | 239614 | Clinical Study Protocol M16-066: A Multicenter, Randomized, Double-Blind, Placebo-Controlled 52-Week Maintenance and an Open-Label Extension Study of the Efficacy and Safety of Risankizumab in Subjects with Ulcerative Colitis Who Responded to Induction Treatment in M16-067 or M16-065 |  | 2018-08-14 | 2019-02-01 | 2019-01-04 | 2019-06-03 | 2019-06-04 | 2019-07-12 | Sponsor
33 | 18/WM/0037 | 228917 | A Multicenter, Randomized, Double-Blind, Placebo-Controlled Induction Study of the Efficacy and Safety of Upadacitinib (ABT-494) in Subjects with Moderately to Severely Active Crohn's Disease who have Inadequately Responded to or are Intolerant to Biologic Therapy | 2018-12-19 | 2018-04-20 | 2018-10-22 | 2018-03-26 | 2018-11-15 | 2018-11-15 | 2018-12-04 | Sponsor
34 | 17/SS/0105 | 209066 | Multicentre, prospective randomized open label, blinded-endpoint (PROBE) controlled trial of thrombolysis with low dose Tenecteplase (TNK-tPA) versus standard of care in the prevention of disability at 3 months in minor ischemic stroke with proven acute symptomatic occlusion |  | 2018-03-09 | 2018-11-01 | 2018-04-27 | 2019-04-01 | 2019-04-10 | 2019-06-14 | Both
35 | 18/EM/0184 | 233744 | Desmopressin for reversal of Antiplatelet drugs in Stroke due to Haemorrhage (DASH) |  | 2018-07-11 | 2018-11-09 | 2018-09-04 | 2018-11-27 | 2018-12-04 | 2019-02-19 | Sponsor
36 | 17/NW/0460 | 225455 | A window of opportunity study to assess the biological effects of progesterone in premenopausal ER-positive, PgR-positive early breast cancer |  | 2018-09-19 | 2019-08-01 | 2019-08-01 | 2019-09-20 | 2019-09-20 |  | NHS Provider
37 | 16/SC/0631 | 209258 | A Long-Term Extension Study to Evaluate the Safety of Filgotinib in Subjects with Crohn?s Disease |  | 2019-03-26 | 2019-06-21 | 2017-01-17 | 2019-08-15 | 2019-08-19 | 2019-09-13 | Sponsor
38 | 18/EM/0383 | 253000 | A Phase 3, Randomized, Comparator-controlled Clinical Trial to Study the Efficacy and Safety of Pembrolizumab (MK-3475) in Combination with Bacillus Calmette- Guerin (BCG) in Participants with High-risk Non-muscle Invasive Bladder Cancer (HR NMIBC) that is Persistent or Recurrent Following BCG Induction (KEYNOTE-676) |  | 2018-03-07 | 2019-01-08 | 2019-01-08 | 2019-04-05 | 2019-04-05 | 2019-04-05 | Both
39 | 17/LO/0108 | 221119 | MAnagement of high bleeding risk patients post bioresorbable polymer coated STEnt implantation with an abbReviated versus prolonged DAPT regimen ? MASTER DAPT |  | 2018-11-27 | 2019-07-17 | 2017-04-10 | 2019-07-23 | 2019-07-29 | 2019-09-16 | Both
40 | 19/LO/0767 | 250759 | Post Market Registry of the IMPEDE and IMPEDE-FX Embolization Plugs | 2019-09-18 | 2019-02-04 | 2019-05-29 | 2019-05-29 | 2019-07-08 | 2019-07-08 | 2019-08-13 | Sponsor
41 | 18/WA/0092 | 230113 | Phase II multi-centre, double-blind, randomised trial of Ustekinumab in adolescents with new-onset type 1 diabetes | 2019-07-30 | 2018-10-19 | 2018-12-06 | 2018-09-21 | 2019-03-27 | 2019-04-09 | 2019-04-15 | NHS Provider
42 | 18/LO/0866 | 224730 | Prevention Of Hypertensive Injury to the Brain by Intensive Treatment after Intracerebral Haemorrhage: a pilot randomised trial of home telemetry-guided treatment | 2019-04-05 | 2018-08-02 | 2018-10-03 | 2018-06-26 | 2018-11-05 | 2018-11-09 | 2019-03-11 | Sponsor
43 | 18/SW/0207 | 250461 | Fatigue - Reducing its Effects through individualised support Episodes in Inflammatory Arthritis (FREE-IA): A Feasibility Study for a Randomised Controlled Trial | 2019-08-22 | 2019-02-19 | 2019-04-25 | 2018-10-30 | 2019-05-03 | 2019-05-03 | 2019-05-03 | NHS Provider
44 | 18/LO/1854 | 251689 | A Phase 3, randomized, double-blind clinical study of pembrolizumab (MK-3475) plus chemotherapy versus placebo plus chemotherapy as first-line treatment in participants with HER2 negative, previously untreated, unresectable or metastatic gastric or gastroesophageal junction adenocarcinoma (KEYNOTE-859) | 2019-04-18 | 2018-10-30 | 2019-01-22 | 2018-12-18 | 2019-03-18 | 2019-03-18 | 2019-03-26 | Both
45 | 18/WM/0274 | 250652 | Repeated measures case series to investigate the use of Colours and Symbols (CAS) as a low-tech supported communication tool, across 10 parameters, in comparison to supported communication alone by five people with aphasia (PwA) and their Speech and Language Therapists (SLTs | 2019-07-24 | 2019-04-01 | 2019-04-11 | 2018-10-22 | 2019-04-11 | 2019-06-06 | 2019-06-06 | Neither
46 | 18/WM/0038 | 235048 | A Multicenter, Randomized, Double-Blind, Placebo-Controlled Induction Study of the Efficacy and Safety of Upadacitinib (ABT-494) in Subjects with Moderately to Severely Active Crohn's Disease Who Have Inadequately Responded to or are Intolerant to Conventional Therapies but Have Not Failed Biologic Therapy. | 2019-09-30 | 2018-04-20 | 2018-10-22 | 2018-03-26 | 2018-11-15 | 2018-11-15 | 2018-12-04 | Neither
47 | 18/SC/0275 | 244088 | Non-invasive rapid assessment of non-alcoholic fatty liver disease (NAFLD) using Magnetic Resonance Imaging with LiverMultiScan (RADIcAL) |  | 2018-05-04 | 2019-08-02 | 2018-06-08 | 2019-08-28 | 2019-08-28 | 2019-09-13 | Sponsor
48 | 17/WS/0142 | 221370 | PRIMUS 001 - An adaptive phase II study of FOLFOX-A (FOLFOX and nab-paclitaxel) versus AG (nab-paclitaxel and gemcitabine) in patients with metastatic pancreatic cancer, with integrated biomarker evaluation | 2019-02-12 | 2017-09-06 | 2018-12-12 | 2017-09-07 | 2018-12-17 | 2018-12-17 | 2019-02-01 | Sponsor
49 | 19/LO/0236 | 230338 | The Effect of Higher Protein Dosing in Critically Ill Patients: A Multicenter Registry-based Randomized Trial - The EFFORT Trial |  | 2019-04-30 | 2019-07-30 | 2019-07-01 | 2019-08-09 | 2019-08-09 | 2019-08-11 | NHS Provider
50 | 18/WM/0039 | 236159 | A Multicenter, Randomized, Double-Blind, Placebo-Controlled Maintenance and Long-Term Extension Study of the Efficacy and Safety of Upadacitinib (ABT-494) in Subjects with Crohn's Disease who Completed the Studies M14-431 or M14-433 | 2019-04-03 | 2018-04-20 | 2018-10-22 | 2018-03-26 | 2018-11-15 | 2018-11-15 | 2018-12-04 | Neither
51 | 17/LO/0621 | 191390 | STandard versus Accelerated initiation of Renal Replacement Therapy in Acute Kidney Injury (STARRT-AKI): A Multi-Centre Randomized Controlled Trial | 2019-06-03 | 2018-11-06 | 2019-01-23 | 2017-05-22 | 2019-02-11 | 2019-02-19 | 2019-04-07 | NHS Provider
52 | 18/SC/0412 | 250170 | A Phase III, Randomized, Double-blind Trial Comparing Trastuzumab Plus Chemotherapy and Pembrolizumab With Trastuzumab Plus Chemotherapy and Placebo as First-line Treatment in Participants With HER2 Positive Advanced Gastric or Gastroesophageal Junction Adenocarcinoma (KEYNOTE 811) | 2019-07-16 | 2018-05-16 | 2018-12-31 | 2018-10-08 | 2019-01-30 | 2019-01-31 | 2019-01-31 | Neither
53 | 17/LO/1918 | 229435 | Does Neuromuscular Electrical Stimulation Improve the Absolute Walking Distance in Patients with Intermittent Claudication (NESIC) compared to best available treatment? A Multicentre Randomised Controlled Study. | 2019-02-18 | 2018-10-02 | 2018-11-21 | 2018-01-29 | 2018-12-19 | 2018-12-19 | 2019-01-23 | NHS Provider
54 | 18/NE/0023 | 230930 | Randomised, double-blind, placebo controlled multi-centre study to assess the efficacy, tolerability and safety of Enterosgel? in the treatment of Irritable Bowel Syndrome with Diarrhoea (IBS-D) in adults | 2019-02-04 | 2017-12-12 | 2018-10-10 | 2018-02-27 | 2018-10-24 | 2018-10-24 | 2019-01-17 | Sponsor
55 | 19/SC/0073 | 246299 | Segmental Tibial fractures, reamed Intramedullary nailing versus circular Frame external Fixation - a Feasibility study | 2019-07-04 | 2017-11-14 | 2019-05-02 | 2019-05-02 | 2019-05-08 | 2019-05-10 | 2019-05-28 | Sponsor
56 | 18/YH/0473 | 252065 | Phase II trial of interleukin-1 receptor antagonist in intracerebral haemorrhage: BLOcking the Cytokine IL-1 in ICH | 2019-08-23 | 2018-12-18 | 2019-05-16 | 2019-01-25 | 2019-07-24 | 2019-07-24 | 2019-08-06 | NHS Provider
57 | 19/EE/0185 | 260536 | FIRST-line support for Assistance in Breathing in Children (FIRST-ABC): A master protocol of two randomised trials to evaluate the non-inferiority of high flow nasal cannula (HFNC) versus continuous positive airway pressure (CPAP) for non-invasive respiratory support in paediatric critical care | 2019-08-28 | 2019-02-18 | 2019-06-26 | 2019-07-26 | 2019-07-31 | 2019-08-05 | 2019-08-19
58 | 18/LO/2070 | 246179 | A feasibility trial of serial prophylactic exchange blood transfusion (SPEBT) in pregnant women with sickle cell disease (SCD) aiming to improve maternal and infant outcomes |  | 2018-11-30 | 2019-08-06 | 2019-03-28 |  |  |  | Sponsor
59 | 18/LO/0612 | 235872 | CLEAR SYNERGY (OASIS 9): A 2x2 factorial randomized controlled trial of CoLchicine and spironolactonE in patients with ST elevation myocARdial infarction/SYNERGY Stent Registry ? Organization to Assess Strategies for Ischemic Syndromes 9 |  | 2018-12-19 | 2019-05-01 | 2018-07-16 | 2019-09-11 | 2019-09-17 | 2019-09-25 | Both
60 | 18/NE/0092 | 230286 | Early versus Late initiation of direct oral Anticoagulants in post-ischaemic stroke patients with atrial fibrillatioN (ELAN): an international, multicentre, randomised-controlled, two-arm, assessor-blinded trial | 2019-05-31 | 2018-08-23 | 2018-12-18 | 2018-08-13 | 2019-02-21 | 2019-03-01 | 2019-05-16 | Sponsor
61 | 19/LO/0555 | 255609 | Lateral compression type-1 fracture fixation in the elderly, a randomised controlled trial |  | 2017-12-04 | 2019-09-02 | 2019-07-17 | 2019-09-13 | 2019-10-03
62 | 19/NW/0158 | 259931 | SCIENCE Surgery or Cast for Injuries of the EpicoNdyle in Children?s Elbows:A multi-centre prospective randomised superiority trial of operative fixation versus non-operative treatment for medial epicondyle fractures of the humerus in children. |  | 2019-03-12 | 2019-06-18 | 2019-03-25 | 2019-08-01 | 2019-08-06 | 2019-08-09 | NHS Provider
63 | 18/YH/0236 | 230191 | PROtective ventilation with high versus low PEEP during one-lung ventilation for THORacic surgery ? PROTHOR: A randomized controlled trial |  | 2019-01-09 | 2019-07-14 | 2018-10-17 | 2019-08-13 | 2019-08-30 | 2019-08-30 | NHS Provider
64 | 17/EE/0240 | 223309 | Phase II neoadjuvant study of Axitinib for reducing extent of venous tumour thrombus in clear cell renal cell cancer with venous invasion. |  | 2017-09-06 | 2018-10-26 | 2017-08-25 | 2018-11-22 | 2018-11-22 | 2018-12-04 | Neither
65 | 19/EE/0052 | 249678 | A feasibility study investigating different interventions for the treatment of benign paroxysmal positional vertigo in acute traumatic brain injury patients |  | 2019-01-31 | 2019-06-03 | 2019-04-03 | 2019-06-03 | 2019-07-08 |  | Sponsor
66 | 19/YH/0094 | 256470 | A PHASE 4 RANDOMIZED CLINICAL TRIAL OF ANDEXANET ALFA [ANDEXANET ALFA FOR INJECTION] IN ACUTE INTRACRANIAL HEMORRHAGE IN PATIENTS RECEIVING AN ORAL FACTOR XA INHIBITOR | 2019-08-02 | 2019-01-15 | 2019-05-24 | 2019-06-19 | 2019-06-03 | 2019-06-25 | 2019-06-26 | Neither
67 | 19/LO/0128 | 234820 | Multicentre prospective double-blind randomised controlled trial of the effect of intravenous iron supplementation, with or without exercise training, in iron-deficient but not anaemic patients with chronic kidney disease on exercise capacity, fatigue, skeletal muscle metabolism and physical function status. |  | 2017-08-24 | 2019-04-08 | 2019-03-07 | 2019-07-30 | 2019-08-29 |  | Both
68 | 17/YH/0262 | 219133 | TReatment of Irritable bowel syndrome using Titrated ONdansetron Trial |  | 2019-03-01 | 2019-08-14 | 2017-11-07 |  |  |  | Sponsor
69 | 17/WM/0106 | 201079 | MOTILITY: Small bowel motility quantified by cine MRI as a predictor of long term response in patients with Crohn?s disease commencing biological therapy | 2019-04-18 | 2018-12-03 | 2019-01-28 | 2017-04-28 | 2019-03-05 | 2019-03-11 | 2019-03-19 | NHS Provider
70 | 19/EM/0149 | 254032 | Ofatumumab Open-Label Investigation of safety and effectiveness. An open-label single arm, multi-center trial, enrolling patients that have participated in an RMS study to evaluate long-term safety, tolerability and effectiveness |  | 2019-05-15 | 2019-09-10 | 2019-06-24
71 | 19/NW/0510 | 269112 | A Two-Part Study With a Birth Cohort (Observational Stage) for Early Diagnosis of Respiratory Syncytial Virus (RSV), Followed by an Optional Phase 2a, Randomized, Double-blind, Placebo-controlled Study (Interventional Stage) to Evaluate the Antiviral Activity, Clinical Outcomes, Safety, Tolerability, and Pharmacokinetics of JNJ-53718678 in Infants With Acute Respiratory Tract Infection due to RSV |  | 2019-06-07 | 2019-07-31 | 2019-09-25 |  |  |  | NHS Provider
72 | 18/SC/0242 | 238151 | A phase III randomised controlled trial of continuous beta-lactam infusion compared with intermittent beta-lactam dosing in critically ill patients. | 2019-06-28 | 2018-08-07 | 2018-10-09 | 2018-08-24 | 2019-06-14 | 2019-06-21 | 2019-06-21 | Sponsor
73 | 18/WM/0324 | 246654 | FORCE - Forearm fracture Recovery in Children Evaluation: A multi-centre prospective randomized equivalence trial of a soft bandage and immediate discharge versus current treatment with rigid immobilisation for torus fractures of the distal radius in children | 2019-05-01 | 2018-08-29 | 2019-01-14 | 2018-11-16 | 2019-01-17 | 2019-01-24 | 2019-02-07 | Neither
74 | 18/LO/1946 | 249357 | A Randomized, Double-Blind, Placebo-Controlled,Parallel-Group, Phase 3 Study of Baricitinib in Patients with Systemic Lupus Erythematosus |  | 2019-03-11 | 2019-08-08 | 2019-03-27 | 2019-09-09 | 2019-09-11 | 2019-09-11
75 | 19/SC/0415 | 269249 | A Phase 3 Randomized, Double-blind, Placebo-controlled Study to Evaluate the Safety and Efficacy of MEDI8897, a Monoclonal Antibody With an Extended Half-life Against Respiratory Syncytial Virus, in Healthy Late Preterm and Term Infants (MELODY) |  | 2019-03-18 | 2019-08-20 |  |  |  |  | NHS Provider
76 | 19/SC/0416 | 269256 | A Phase 2/3 Randomized, Double-blind, Palivizumab-controlled Study to Evaluate the Safety of MEDI8897, a Monoclonal Antibody with an Extended Half-life Against Respiratory Syncytial Virus, in High-risk Children |  | 2019-03-18 | 2019-08-20 |  |  |  |  | NHS Provider
77 | 18/SC/0146 | 226499 | Diabetic Peripheral Neuropathy Treatment with Dorsal Root Ganglion Stimulation ? a Randomised Controlled Trial. |  | 2019-03-06 | 2019-09-05 | 2018-06-04 | 2019-09-25 | 2019-09-27 | 2019-09-30
78 | 18/EE/0356 | 250087 | A Phase 3, Randomized, Open-label Study of NKTR-214 Combined with Nivolumab Versus Nivolumab in Participants with Previously Untreated Unresectable or metastatic Melanoma |  | 2018-09-10 | 2019-09-30 | 2019-09-30
79 | 18/SW/0121 | 239039 | Feasibility of a family-based nutrition and physical activity intervention in young people with familial hypercholesterolaemia: A mixed methods study |  | 2019-06-04 | 2019-08-13 | 2018-06-08 | 2019-09-25 | 2019-09-25 | 2019-09-27 | NHS Provider
80 | 18/LO/1293 | 244868 | Evaluation of safety and immunogenicity of meningococcal B and meningococcal ACWY vaccine in at risk population (ProPositive Study) | 2019-03-05 | 2018-07-03 | 2018-10-18 | 2018-10-18 | 2019-02-14 | 2019-02-14 | 2019-02-14 | Neither
81 | 19/LO/1240 | 263231 | A Phase 2b, Multicentre, Double-blind, Active-controlled, Randomised Study to Investigate the Efficacy and Safety of Different Combination Regimens Including JNJ-73763989 and/or JNJ-56136379 for the Treatment of Chronic Hepatitis B Virus Infection |  | 2019-07-05 | 2019-07-09 | 2019-08-22 | 2019-09-27 | 2019-09-27 |  | NHS Provider
82 | 19/NE/0077 | 258955 | A Multicenter, Randomized, Double-Blind, Placebo-Controlled, Two-Arm, Phase 2 Study of ME-401 in Subjects with Follicular Lymphoma After Failure of Two or More Prior Systemic Therapies |  | 2018-11-14 | 2019-07-16 | 2019-03-29 |  |  |  | NHS Provider
83 | 18/SC/0006 | 220480 | Brain Machine Interfaces based on subcortical LFP Signals for Neuroprosthetic Control and Neurofeedback Therapy | 2018-11-15 | 2018-07-02 | 2018-10-23 | 2018-06-12 | 2018-11-06 | 2018-11-09 | 2018-11-09
84 | 18/LO/2139 | 253844 | Oesophageal protection: a novel approach to improving the safety profile of catheter ablation for atrial fibrillation. A randomised controlled clinical trial | 2019-02-22 | 2018-09-13 | 2019-02-04 | 2019-02-19 | 2019-02-04 | 2019-02-21 | 2019-02-21
85 | 19/SC/0021 | 249552 | OPtimal TIMing of Anticoagulation after acute ischaemic Stroke: a randomised controlled trial (OPTIMAS Trial) | 2019-09-20 | 2019-07-30 | 2019-07-30 | 2019-04-04 | 2019-08-21 | 2019-08-30 | 2019-09-02
86 | 19/LO/0945 | 262119 | Pharmacokinetics of intramuscular tranexamic acid in trauma patients: a clinical trial | 2019-09-17 | 2019-07-31 | 2019-08-13 | 2019-08-06 | 2019-09-11 | 2019-09-11 | 2019-09-13
87 | 18/SW/0268 | 251667 | HYDROXYCHLOROQUINE FOR PREVENTION OF ABNORMAL GLUCOSE TOLERANCE AND DIABETES IN INDIVIDUALS AT-RISK FOR TYPE 1 DIABETES MELLITUS |  | 2019-01-16 | 2019-08-23 | 2019-03-11
88 | 18/NE/0296 | 248487 | CArvediloL versus variceal Band ligation in primary pREvention of variceal bleeding in liver cirrhosis |  | 2019-02-14 | 2019-09-23 | 2018-10-19
89 | 19/LO/0397 | 243173 | A Phase 2/3, Randomized, Double-blind, Placebo- and Active-controlled, Parallel-group, Multicenter Protocol to Evaluate the Efficacy and Safety of Guselkumab in Participants with Moderately to Severely Active Crohn's Disease |  | 2019-01-18 | 2019-09-09 | 2019-06-05
90 | 18/NW/0180 | 236218 | Sodium Valproate for Epigenetic Reprogramming in the Management of High Risk Oral Epithelial Dysplasia |  | 2018-07-23 | 2019-09-19 | 2018-09-03
91 | 18/WM/0070 | 236540 | The impact of Sleep Disorders in Patients with Type 2 Diabetes: A Cohort Study and Feasibility RCT | 2019-03-14 | 2018-10-09 | 2018-12-21 | 2018-05-24 | 2019-01-30 | 2019-02-11 | 2019-02-26 | Both